# Minutes: CM Standards WG, 11.06.2019

Attendance: Niklas (DRC), Jennifer (IOM), Hannah (IOM), Giovanna (NRC), Elena (Acted), Ingrid (IOM), Munmun (IOM), Frank (IOM). Brian (IOM).

| Agenda | Discussion | Action Point |
| --- | --- | --- |
| - Update on Phap proposal for online consultations. | - Several exchanges and meetings with Phap have taken place. Jennifer shared with the WG proposal received and summarized the discussions. Discuss focused on the tight timeline, sequencing of the webinars after the consultation (rather than BEFORE), translation into “non-UN languages” and engagement with national clusters to ensure that national CCCM partners had a chance to be in the consultation process. | WG fp (or Cluster coordinators) to reach out and ask national cluster coordinators about the need for translation (which languages) and if this could be potentially supported by national cluster partners who may be in a better position to translate the technical aspect of CM/humanitarian concepts. Changes to Phap proposal to be made and shared at next meeting on July 2, in Geneva. |
| - Update on concept note | - New concept note shared. Focus on application of the standards, vision for what are going to do and who is going to be involve. Discussion – WG liked the new vision for the application of the standards. Suggested to add national level dissemination, what it will mean to the different agencies, how indicators will become part of work to monitor and evaluate, brief staff, or other steps once document is finished. Liked commitment to revise on-line training component, and recommended further national level engagement (target 5 countries) to promote national level commitment of standards. Additional discussion on timeline for project overall, which is quite delayed and the need to flag this to the wider CM community/SAG so they are aware. DRC agreed to formal partnership in Standards as proposed in concept note and take a formal role in working group. | WG members to make comment on document by 14.6.19 |
| - AOB | - Iraq updated their SAG has endorsed field consultations to go ahead in both Baghdad and Erbil. | Frank to share profile of participants and dates once agreed. WG to support as needed (requested) in finalization of their consultations. |

Next meeting in 3 weeks – early July.

#