## Sheet1
Timeframe (in months)
|  | Status | Focal Point(s) | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 |  | 2021-11-01 | 2021-12-01
0. Working Group |  |  | IOM, DRC
Regular calls with members
| TOR revised | on track
| Workplan for 2021 | in process | JCK, TS
| Minutes circulated, uploaded on Website |  | BM,AA
Colloboration with other clusters
| Presentation at annual retreat | [13 empty] | Retreat?
| HSP application | awaiting approval
1.Publication of Standards |  |  | JCK
| Copy edit | requested PRF
| Design | requires funding | w/ River Valley Publication
| Layout | requires funding
| Proofreading | requires funding
| Publiation | requires funding
2. Dissemination of Standards |  |  | WG
| FAQ on indicators | on-going | Alisa and Brian
| Review and endorsement by cluster and SAG | needs formal approval | ACTED, DRC, NRC
| Discussion on who "owns the standards" , LOGO, and input around dessimnation | to be presented at SAG | SAG, WG
| Protocol for launch | requires funing | TS, WG
3. Use, Application, Monitoring
| Pilot Countires | on-going | Nigeria, Somalia, Chad?
| Link with Case Studies (webinar) | on-going | Elena
| translation | requires funding | IOM LAC (Spanish), Action Aid (Bangla),
| capacaity building materials | requires funding | ?