## Resource Mobilization tracker
Resource Mobilization Tracker - Debre Berhan the Response Plan | [7 empty] | Timelines
No | Activities/Tasks/Services | Responsible Government Agency/Cluster | Who Will follow up/Implement | TOTAL $$ ASK | Available Partners | Resources Available from Partners | TOTAL GAP | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | Progress |  |  |  | Remarks
| SITE PREPARATION ACTIVITIES BEFORE RELOCATING IDPs | [6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Target | Started | Ongoing | Completed
1 | Land Use Agreement or Land Use Authorization | Local Authorities/Mayor/ZDRMO | Protection (Brook)/CCCM | 3000 |  | 200 | 2800
2 | Site Planning | CCCM/ZDRMO | CCCM (John) + ESNFI + WASH
3 | Site preparation & levelling | Local Authorities/Mayor/ZDRMO | CCCM + Site Planner UNHCR
| Road grading/levelling & compacting | Local Authorities/Mayor/ZDRMO | CCCM + Site Planner + Loc.Auth
4 | Construction of shelters | Shelter Cluster/UNHCR/ZDMRC? | UNHCR? ESNFI
5 | Construction of latrine and showers | WASH cluster/ Bureau of water | UNICEF/PLAN?
6 | Tapping into the main water pipeline | WASH cluster/ Bureau of water | UNICEF/PLAN?
6 | Construction of Solid waste disposal site | WASH cluster / Bureau of water
7 | Construction of water tap stands/handwashing points | WASH cluster/ Bureau of water |  | 5000 | DORCAS PLAN | 500 | 4500
9 | Construction of health facilities/Mobile health Shed | Health cluster/Health Bureau | [25 empty] | 199
10 | Construction and equiping of child friendly spaces | Child Protection/UNICEF? Plan?
11 | Construction of women/girl Safe Spaces | UNFPA? ZDMRC
12 | Construction of temporary learning centres | Educ cluster/Bureau of Educ
13 | Construction of distribution centre | Food Cluster/RDMRC
14 | Community Information Centres | CCCM/Protection/NDRMC
15 | Construction of relocation site reception centres (if needed) | Protection
17 | Provision / Connecting to the main electricity grid | LocAuth/Mayor/ZDRMO
18 | Construction of drainage cluverts on road intersections | LocAuth/Mayor/ZDRMO/CCCM
19 | Construction of surface drainage system | Government/CCCM
20 | Construction security sentry points | Government
B | COMMUNITY CONSULTATION PROCESSES BEFORE RELOCATING IDPs
21 | Training of camp coordination and camp management teams | CCCM | [25 empty] | Toeksn are matched with the family registration list
22 | Consultation meetings with displaced persons | Protection / ZDRMC
23 | Consultation meetings with Host community | Protection / ZDRMC
24 | Go and see visits | Protection / ZDRMC
25 | Information dessemination on the relocation | Protection / ZDRMC
26 | Registration of persons willing to be relocated | Protection / ZDRMC
27 | Prioritization and identification of EVIs and persons with special needs | Protection / ZDRMC
28 | Issuance of shelter tokens | Shelter Cluster/RDMRC
29 | Issuance of essential household item- NFIs | Shelter Cluster/WASH Cluster
30 | Transportation for both displaced persons and their household items | Bureau of transportation
31 | Provision of COVID 19 PPE materials | Health Cluster / PLAN?
32 | Provision of Ambulance and emergency care during relocation | Red Cross/Bureau of Health
33 | Provision of security | Government/Police?
34 | Enhancement of self governance structures | ZDMRC/CCCM
35 | Provision of food package for relocation | Food Cluster/ZDMRC
36 | Provision of nutritional support | Nutrition cluster
37 | Provision of NFIs/Dignity and sanitation kits | Governement
38 | Rehabilitation /Decommissioning of collective centers | Shelter/WASH/Education
39 | Construction of youth centres | Protection
40 | Identification and construction of market stalls | CCCM/ZDRMC
41 | Establishment of water committees | WASH/ Bureau of water
42 | Establishment of IDP committees | Protection/CCCM/
43 | Establishment of Information centres | Protection/CCCM
44 | Establishment of Protection desk | Protection
45 | Environment protection and enhancement | CCCM/WASH & Camp Comm.

## Per Cluster
Resource Mobilization Tracker - Debre Berhan the Response Plan Requirements to Establish a Site and 6 months Operations | [27 empty] | Timelines
A | Establishing A Camp : Infrastructure Needed | Responsible Agency/Partner | No. of Units Required | Unit Cost $ | Total Est. Cost $ | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | Progress |  |  |  | Remarks | Partners on the Ground | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | Progress |  |  |  | Unit Cost USD | Total Cost USD | Remarks
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Target | Started | Ongoing | Completed |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Target | Started | Ongoing | Completed
1 | CCCM Cluster
1.1 | Site preparation & levelling & compaction | Site Planner (John) | 1 | 5000 | 5000
1.2 | Construction security sentry points |  | 2 | 500 | 1000 | [21 empty] | DEC, PLAN,
1.3 | Construction of surface drainage system |  | 1 | 2000 | 2000
1.4 | Provision of electricity and back up systems |  | 1 | 2000 | 2000
1.5 | Const. of Reception Center at relocation site |  | 1 | 500 | 500
1.6 | Construction of communal kitchen |  | 16 | 1000 | 16000
1.7 | TOTAL CCCM Cluster Ask |  |  |  | 26500
2 | Emergency SHELTER / NFI Cluster
2.1 | Shelter design |  | 0 | 0 | 0
2.2 | Construction of shelters
2.3 | Marking of shelter
2.4 | Provision of Tokens to HH for relocation
2.5 | TOTAL ESNFI Cluster Ask
|  | Responsible Agency/Partner | No. of Units Required | Unit Cost $ | Total Est. Cost $
3 | WASH Cluster
3.1 | Connecting the site to the main water pipeline | PLAN, DORCAS | 2500 | 12500 | 12500 | [20 empty] | 50mm pipeline black @1usd/m
3.2 | Construction of latrines | PLAN, DORCAS | 50 | 750 | 37500 | [20 empty] | 199 latrines say 200 doors M/F 1 stance - 4 doors
3.3 | Construction of showers | PLAN, DORCAS | 50 | 500 | 25000
| Construction of Solid waste disposal site | PLAN, DORCAS
3.4 | Construction of watre points | PLAN, DORCAS
3.5 | TOTAL WASH Cluster Ask |  |  |  | 75000
4 | HEALTH Cluster
4.1 | Construction of mobile health facility/ies
4.2 | TOTAL HEALTH Cluster Ask
5 | EDUCATION Cluster | [24 empty] | Toeksn are matched with the family registration list
5.1 | Construction of temporary learning centres |  | 2 | 500 | 1000
5.2 | Construction & equiping of CFS |  | 2 | 500 | 1000
5.3 | TOTAL EDUCATION Cluster Ask
6 | FOOD Cluster
6.1 | Construction of distribution centre
6.2 | Provision of Food pack before relocation
6.3 | TOTAL FOOD Cluster Cluster Ask
7 | PROTECTION Cluster
7.1 | Construction of women safe spaces |  | 2 | 500 | 1000
7.2 | Establish CFM Desk and
7.3 | TOTAL PROTECTION Cluster Ask
B | Care & Maintenance: Operational Activities Required
CCCM Cluster
| Training of camp coordination and camp managements teams | [25 empty] | IOM/UNHCR/ANE
Consultation meetings with displaced persons
Consultation meetings with Host community
Go and see visits
Information dessemination on the relocation
Registration of persons willing to be relocated
Identification and construction of market stalls
Establish Camp Committee
Establishment of Camp Information centres
WASH Cluster
Transportation for both displaced persons and their household items
Provision of NFIs/Dignity and sanitation kits
Establishment of water committee
ESNFI Cluster
Issuance of shelter tokens
Enhancement of self governance structures
Issuance of essential household item- NFIs
Establishment of ESNFI committee
PROTECTION Cluster
Prioritization and identification of EVIs and persons with special needs
Provision of security
Establishment of Protection desk
Civil documentation
Transportation for both displaced persons and their household items
HEALTH Cluster
Provision of COVID 19 PPE materials
Provision of Ambulance and emergency care during relocation
Conduct Mobile health clinics
FOOD Cluster
Provision of food
Provision of nutritional support
EDUCATION Cluster
School repairs and rehabilitation assessment
Manning the TLC
Manning the CFS