## Shelter CCCM
Shelter/NFI/CCCM Cluster - Workplan for 2017 (Jan - May)
Last updated: 08 January 2017
Activity | Details of activity | Responsible person(s) | Support/resources required | January | Jan | Feb | June | July |  |  |  |  | March | April | May | Notes and Update on progress - to be reviewed at each SAG meeting
Objective 1: Provide life-saving and life-sustaining shelter solutions and Non-Food Items support to the most vulnerable in liveable and dignified settings
Update Cluster Strategy - Shelter CCCM | Review 2015 strategy and align to 2017 YHRP and Protection Cluster | Coord Team+SAG |  |  | X | X | [9 empty] | Protection Cluster is actively engaged Note: Strategy to cover 2017-2019
Complete Technical Guidance Notes | Reactivate Technical Working Group | Coord Team+Cluster members |  |  | X
| Compile guidance with TWiG and complete draft Guidance Docs | Coord Team+TWiG members |  | x | X | X | [9 empty] | Note: 7 (documents) tech guidence notes require urgent finalisation
| Draft Return packages and guidence of intervention | Coord Team+TWiG members |  |  |  | X | [6 empty] | X
| Cash for Rent SOPs - produce and disseminate as priority | Coord Team |  |  | X | X | [6 empty] | X
| Define referal mechanism of Cash for Rent to Livelihoods activities | Coord Team | [10 empty] | X |  |  | Protection and Emergency Employment and Community Rehabilitation Clusters to be engaged
| Review overall drafts & finalise | Coord Team & SSS/Geneva |  | x | X | X | [6 empty] | X
| Circulate as cluster guidence | Cluster Coord Team |  | x |  | X | [6 empty] | X | X
Objective 2: Ensure access to basic services for the most vulnerable living in collective centres and spontaneous settlements
(Post) Distribution Monitoring + Warehouses | Contingency stock coordination | Cluster Coord Team |  |  | X | X | [6 empty] | X | X | X
| NFI matrix and gap analysis | Cluster Coord Team |  |  | X | X | [6 empty] | X | X | X
| Complete NFI distribution monitoring | Cluster & Coord Team |  |  | X | X
| Emergency Shelter Monitoring | Cluster & Coord Team |  |  | X | X | X | X | X | X | X | X | X
Protection Mainstreaming | See Objective 3 |  |  |  |  | X | [6 empty] | X
Gender Mainstreaming | See Objective 3 | [11 empty] | X | X
Objective 3: Strenghten accountability towards affected populations through seeking feedback, and addressing concerns about the response
Update Cluster Strategy for CCCM | Review 2017 strategy and align to 2017 YHRP | Coord Team+SAG |  |  | X | X
Develop Technical Guidance for Collective Centres | Develop package of assessments; recommended upgrades; protection considerations | SAG | Activation of TWiG if expertise is available in country |  |  | X | [6 empty] | X |  |  | Coord Team has sought quotations for translating Collective Centres Guidelines into Arabic.
Collective Centre Monitoring (Remote Community Managemnet) | Develop more detailed database of Collective Centres | Coord Team - IMO |  |  | X | X | [6 empty] | X | X | X
| Develop CC monitoring tool for use by partners | SAG | CCCM / GVA |  |  | X | [6 empty] | X | X | X
Protection Mainstreaming | Conduct one day workshop for Cluster | Cluster Gender Focal Points and GenCap Advisor | 2 additional trainers from other clusters |  |  | X | [8 empty] | X
| Promote continued use of IASC Gender & Age Marker for Monitoring | Cluster | Gen Cap Advisor |  | X | X | [6 empty] | X | X | X
Gender mainstreaming | Conduct one day workshop for Cluster | Cluster Gender Focal Points and GenCap Advisor | 2 additional trainers from other clusters |  |  | X | [8 empty] | X
| Promote continued use of IASC Gender & Age Marker for Monitoring | Cluster | Gen Cap Advisor |  | X | X | [6 empty] | X | X | X
Objective 4: Enhance the capacity of authorities, communities and humanitarian actors in Shelter, NFI and CCCM programs
CCCM Training | Conduct workshop for Cluster | Coord Team | UNHCR Trainer in country | [9 empty] | X | X
| Dessimantion of Guidelines in Arabic | Coord Team |  |  |  | X | X | X | X | X | X | X | X
Shelter specific technical guidence work-shops | Conduct workshop for Cluster | Coord Team |  |  |  | X | X | X | X | X | X | X | X | X | X
Information Management Training | National & Sub-national training | Coord Team |  |  |  | X | [8 empty] | X
Distribution Training | Promote on-the-job training for national partners | Cluster | Agencies willing to collaborate at distribution sites |  |  | X | X | X | X | X | X | X | X | X | X
| Disseminate guidelines and best practices | TWiG |  |  |  | X | [9 empty] | Draft guidelines available - review and finalise
General Cluster Cooridnation Work
| Regular reporting | Cluster members |  |  | X | X | [6 empty] | X | X | X
| Revise Cluster ToR | SAG+Coord Team |  |  |  | X | [6 empty] | X
Information Management | Produce regular IM products such as 3Ws, Fact Sheets & | Coord Team with input from Cluster partners |  |  | X | X | X | X | X | X | X | X | X | X | X
| Gaps and Needs Analysis - prioritisation of responses | Coord Team with support from IOM and Cluster partners |  |  | X | X | X | X | X | X | X | X | X | X | X | Develop harmonised methoodolgy for analysis of data collected and support Cluster partners
Advocacy | Key Shelter/CCCM messaging for Cluster | Coord Team & Cluster partners |  |  | X | X | [9 empty] | Shelter / Collective Centre Advocacy Document drafted and shared with SAG
| Produce regular advocacy paper to HCT/ICCM/ donors and relevant partners on the current protection situation (including needs and gaps). | Inter Cluster |  |  |  | X | X | X | X | X | X | X | X | X | X
Contingency Planning | Review and update Cluster plans | SAG | Scenaros - cluster input |  |  | X | X | X | X | X | X | X | X

## Sheet1
Objective 1: Provide life-saving and life-sustaining shelter solutions and Non-Food Items support to the most vulnerable in liveable and dignified settings
Objective 2: Ensure access to basic services for the most vulnerable living in collective centres and spontaneous settlements
Objective 3: Strenghten accountability towards affected populations through seeking feedback, and addressing concerns about the response
Objective 4: Enhance the capacity of authorities, communities and humanitarian actors in Shelter, NFI and CCCM programs