## Hoja1
Example Protocol Gantt Chart
Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Step 0 - IEC TWIG formed
Step 1 - Understanding the Context
External communciation: relase of basic IEC - how to use tarps
External communication: cluster press release - failure mechanism seen
Step 2- Define IEC Preliminary Objectives
Internal communication: We need to comunicate on X
Step 3 - Indentify Stakeholders and Audiences
Step 4 - Engagement Pathways Analysis
Internal communciation: this is how people want to ne communicated with
Internal communication: guidenace on model house programmes
Step 5 - Develop Detailed IEC for Audience/Stakeholder Groups and Engagement Pathways
Internal communciation: written release of detailed messafes - draft
External communciation: radio phone-in talk shows
Internal communciation: basic draft of leaflets on messafes for trailing in X area
Step 6 - Define 'Roll-Out' Strategy and Confirme IEC Objectives
External communciatio: posters and detailed leaflets on concrete blockwork houses
Step 7 - Define Monitoring, Revision and Evaluation Framework