Shelter Cluster Coordination Meeting

Typhoon Rolly and Ulysses

20th November 2020

_______________________________________________________

Minutes of Meeting

Participants:

Mark Mauro Victorio, SCC, Chair

Jacopo Margutti, SC IM Coordinator

Ajab-Aram Macapagat, World Vision

Arnaldo Arcadio, CRS

Conrad Navidad, IOM, CCCM

Kim Acupan, Build Change

Jolly Anne Gibe, HfH

Marilou Pia, Shelterbox Phi.

Vince Delector, Samaritan’s Purse

Rosemarie Palencia, Shelterbox Phil.

Summary of discussion:

- Updates on Typhoon Rolly and Ulysses

  - The SCC presented updates for Typhoon Rolly and Ulysses.

  - Typhoon Rolly (Goni)

    - More than 2 million people are affected; 189,217 houses were damaged, which 40,080 Totally and 149,211 Partially; There are 17,320 families displaced.

    - Priority area is Bicol Region

    - Provision of shelter assistance is ongoing from the Government, NGOs and Private Sectors

    - Many displaced families are returning and started to repair damaged shelters using assistance provided by different agencies and salvage materials.

    - DSWD and DHSUD will give Emergency Shelter Assistance (ESA) to families affected by Typhoon Rolly (Php 5,000 Partially/Php 10,000 Totally)

  - Typhoon Ulysses (Vamco)

    - More than 3 million people are affected; 65,914 houses were damaged which 6,091 Totally and 59,823 Partially; There are 74,928 families displaced in Regions II, III, NCR, CALABARZON & V.

    - Severely affected areas are Region II, III, NCR and V

    - Provision of Food and NFIs are ongoing from the Government, NGOs and Private Sectors

    - Displaced families are returning and started to clean and repair damaged shelters

    - Assessment is ongoing (Gov’t and HCT)

- Updates from the ICCG meeting (November 16, 2020)

  - The SCC provided updates to cluster members about the recent ICCG meeting.

    - The Central Emergency Response Fund (CERF) approved the request of the HCT for a $3 million rapid response funding for Typhoon Rolly, as shared by the RC/HC

    - There ongoing assessment in Region 2 for Typhoon Ulysses, facilitated by the Office of the Civil Defense (OCD) and HCT that started last Thursday, November 19, 2020

    - Possible revision of HNP document to include Typhoon Ulysses.

- Updates on the Humanitarian Needs and Priorities

  - The SCC shared the current HNP for Super Typhoon Goni that was launched last November 9, 2020.

Key figures for shelter section:

Target Areas: Albay and Catanduanes

People Target: 60,000

6,000 destroyed houses (30K people)

6,000 damaged houses (30K people)

Funding Requirements

$ 10M

- Shelter Cluster Partners Operational Updates

  - Ongoing and Planned shelter activities for Typhoon Rolly and Ulysses.

    - ShelterBox Philippines – Will provide emergency shelter assistance targeting families with totally damaged houses in Municipalities of Baras and Bato in Catanduanes and Municipality of Pili in Camarines Sur. Tapped the Philippine Navy to transport items from Cebu going to Bicol Region. The distribution will commence on Monday or Tuesday next week.

    - Samaritan’s Purse – The team is already in Catanduanes conducting validation for the target barangays. The distribution will start in the first week of December, covering 200 families with shelter repair kits amounting between Php 12,000 to Php 15,000.

    - World Vision – The team already in Albay and Catanduanes and has distributed 1,850 emergency shelter kits (Tarps and Fixing ropes) and NFI (kitchen Sets, Blanket, Mosquito Nets, and Matts) to 2,262 families in Municipalities of Tiwi and Guinobatan in Albay and Municipality of Virac in Catanduanes. Next plan it to distribute shelter repair kits worth Php 8,000 and additional cash assistance and will continue to distribute emergency shelter kits and NFIs in Albay, Catanduanes, Cagayan, and Isabela.

    - IOM – Has been distributing tarpaulins, ropes, and solar lamps in Albay, Catanduanes, and Camarines Sur since November 5. In Total, IOM has distributed 1,500 shelter grade tarpaulins in Catanduanes and 1,800 shelter grade tarps, ropes, and solar lamps in Albay and Camarines Sur. IOM also coordinated with APSEMO in Albay and recommended to support Geographically Isolated and Disadvantaged Areas (GIDA) such as Cagraray Island in Albay. There are 28 barangays in urgent need of kitchen sets since most families are just borrowing cooking pots (Kaldero). They also coordinated with EDMERO in Camarines Sur and recommended Aplayan Island and other island barangays and encourage partners to support these areas and coordinate with the LGU and local agencies. The plan for the next weeks and months under CERF is to distribute emergency shelter kits. Furthermore, IOM is finalizing all the CERF documents and will publish a Call for Proposal (CfP) to partners next week. The CfP will support 800 families with shelter repair kits with complementing cash assistance worth 4,500. The total budget is 350,000 USD or 17 million pesos. CfP will come with SRK BoQ

    - CRS – Provided local partner the Social Action Center (SAC) Legaspi with emergency shelter kits and tools for 835 families. Social mobilization is ongoing, and the initial target areas are Municipalities of Malilipot and Bacacay in Albay, which are on the pacific coast who felt the initial impact of typhoon Rolly. The tools will be distributed in 1 set per two families to lessen sharing and mitigate the spread of COVID-19. The plan for the coming weeks is to distribute Household and Hygiene items in Albay through cash or voucher depending on the result of cash and market assessment. Further, they will be piloting 10 emergency shelters in Albay. While in Catanduanes, they will provide emergency shelter and tools to 835 families as well.

    - Habitat for Humanity Philippines - At present, no immediate response for Typhoon Rolly and Ulysses, but looking for implementing permanent shelter for typhoon Ulysses affected families either in NCR or CALABARZON.

  - 3W template and report.

    - SCC shared the new template for the 4W and informed that the next round of reporting is on the first week of December and advised to directly submit the report to the shelter cluster copying OCHA.

    - SCC presented the 4W dashboard can be accessed through this link  Typhoon Goni Operational Presence

- AOB

    - SCC informed partners that the Shelter Cluster Field Focal Point for Albay is the Social Action Center – Diocese of Legaspi (SAC Legaspi) and the Hub Coordinator is Fr. Rex Paul Arjona and can be contacted through this email address, AlbayCoord.phil@sheltercluster.org.

    - SCC share that the Global Shelter Cluster has a dedicated website for Typhoon Rolly and Ulysses and be accessible through this link https://www.sheltercluster.org/response/typhoon-goni-2020

    - Partners agreed that shelter coordination meetings would be every two weeks.

Action Points:

    - The shelter cluster coordinator will share with partners the IOM Call for Proposal for CERF next week.

    - Shelter cluster partners will submit 4W reports using the new shelter template. The next round of reporting is in the first week of December.

    - The SCC will announce to partners the schedule for the Hub Shelter Cluster Coordination meeting in Albay.

    - Will follow up and finalize the SC Field Focal Point for Catanduanes.

Source: DSWD DROMIC Report as of Nov 19, 2020

Source: DSWD DROMIC Report as of Nov 19, 2020