## Stakeholdermapping
StakeholderRegister and Mapping
Kambulukire Village
(the following columns can be completed while discussing or after having worked on the Stakeholderanalysis template)
Stakeholder Group (groups can be modified based on the context; add as much lines as needed) | Stakeholder Name | Department, Influence Level, Area of work, etc. | Contact Details (Phone, Email, Address, etc.) | Role (what is their task or job related to the affected community) | Stake (what role does or can this stakeholder play in the project) | Our Expectation (what do we want or need from this stakeholder?) | Impact (how does the project impact them? High, Medium, Low) | Influence (how much influence do they have over the project? High, Medium, low) | Key concerns (What is important to the Stakeholder? Motivation, Expectation, Incentive) | Motivation (what could the stakeholder specifically expect from the project?) | Supporter (how could satekeholder contribute to the Project?) | Opponent (how could the stakeholder block the project? ) | Attitude (Perceived attitude towards the project or risk if not engaged) | Communication method (which is the most commonly used and more efficiente communication method used by this stakeholder?) | Actions (Posible strategy for engaging the stakeholder and enhancing their support)
Affected Community | Jenala | Traditional Authority | Formal physical village locations like Traditional Authority Jenala, Group Village Headmen Bona and Ndungunya | Alerting communities when disaster has happened | The stakeholder can influence communities to under devepment and also key in making bylaws and enforcing change
Community overseer, responsible for making bi-laws for a the particular community, delegates to GVHs and VHs
| Bona and Ndungunya 1 | Group Village Headmen | 0996112024 | Overall overseer to a group of villages as delegated by the Tradional Authority | Has the ability to make bylaws and enforce them on communities,
| Njobvu | Group Village Head |  | The role of hoseholds is to locally mobilise low cost resources, man power | Currently, the evacuation camp that is in Phalombe is under the area of GVH Njobvu and as such will host all affected communities. | Households that are affected prepare their own rescue operating procedures by vacating to better places like schools, churches that are created as evacuation centres. Other affected
Authorities | District Council | Council with its Service Committees, Secretariat, DRR Office, Housing, Water Department, Social Welfare | Ministry of Local Government | · Ensuring that communities are taken care of during a disaster by moving members and their belongings to safety. | · A key partner in planning and executing
|  |  | Capitol Hill, Private Bag 338 Lilongwe 3. | · Mobilising resources to provide portable water, food security as well as mainstreaming sanitation and hygiene to reduces illnesses that are associated with disasters like diarrhoea and malaria | · Help in mobilising communities when disasters happen.
|  |  | P.O. Box 30312, Capital City, Malawi |  | · Mobilising resources to help communities from government as well as Non-governmental Organisations, They also safegurd materials when assistance come from external donars.
(+265) 01 745 362
info@mlgrd.gov.mw
|  | Area Development Committees (ADC), Village Development Committees (VDCs) and Civil Protection Committees | Formal physical village locations like | Taking tasks assigned to affected households is done collaboratively amongest all sectors. The core duty of operations at field level is directed by sectors through VCPCs and local leaders | Important in reaching individuals at grassroots and noting the right beneficiaries for the program
implementing council resolutions and provides technical guidance
Providers, Suppliers, Construction workers |  | Skilled bricklayer |  | To provide materials and services to demanded situation | Key in constructing recovery structures
|  | SORISTIPA artisan association (TEVETA) |  | training to local artisans | Identifying skilled labour for sustainable structures
| Indian shops, local suppliers, local builders and other district and relevant officers who defines plans for structures. | Indian shops, builders and designers provide services and materials to help in the work | Limbe, Blantyre and Phalombe shops. | To provide materials and services to demanded situation. | The role of providers is to timely provide timely resources within a stated period. | Providing quality materials for the project for sustainance
Local organisations or associations | WFP through ADRA | Non-Governmental Organisation |  | Food for Asset creation through catchment management | Will help in creating road drainages, dykes, check dams and terraces to control flooding
| Evangelical Lutheran Development Services | Non-Governmental Organisation |  | Food Security, Enhancing Income at Household Level and Renewable Energy | Will be key in recovery programming for affected individuals
| CADECOM | Non-Governmental Organisation | P.O Box 5565, Limbe | Ensuring food security, WASH and Protection mainstreaming is done and distributing food and non-food items | Part and parcel of planning and coordination of shelter activities in line with partners
Influencers, opinion leaders | Members of Parliament | Political figures |  | Provision of emergency support to the affected population | Influence relocation of people from hot spots to safe spots
Influence structural designs adoptation
| Ward counsellors | Political figures |  | Provision of emergency support to the affected population | Influence relocation of people from hot spots to safe spots
Influence structural designs adoptation
| Civil Protection Committees |  |  | Registering affected people | Coming with early warning systems
|  |  |  | Custodians of relief items | Registering affected people
Promoting human rights of affected individuals
Information hub between DoDMA office and grassroots
Communication Media | Phones, church leaders, leaflets, public address systems, drama,songs, poetry, one on one, radios, mobile vans, mobile screen. | Publicity of the messages on the impending and occuring disasters | MBC, Radio Maria, Mzati radio. | Allerting people on resque operations by making awareness meetings, sensitizations nd other notification strategies. | Does communication at all levels where communication is done when need arises. | Communications provides a tool of safety to affected households.
Education | Primary School |  |  | Basic child education | Basic child education
Assembly point for communities
Youth Clubs
Other |  | Private Clinic |  | Health Care | Providing basic medications | Gathering place; Sensitization
Health talks on outbreak (Cholera) preventation
Provision of pyscho-social support
|  | Miseu Folo market 5km away |  | Provision of material basic need | Provision of material basic need | Gathering place; Sensitization
|  | Public Hospital (10 km) |  | Health Care | Providing basic medications | Gathering place; Sensitization
Health talks on outbreak (Cholera) preventation
Provision of pyscho-social support

## Stakeholderanalysis I
Stakeholderanalysis
(Place the names of the stakeholder in this graphic based on their level of interest of the projects impact and their influence or power to influence or support the project. This is best to be done in a Working Group Session with flipcharts discussing and agreeing on the position of every stakeholder identified)
INFLUENCE / POWER
High
Medium
Low | [5 empty] | INTEREST / PRIORITY
0 | Low |  |  | Medium | High
|  | MONITOR | (minimum effort) | low influence/ low interest
|  | KEEP INFORMED | (show consideration) | low influence/ high interest
|  | KEEP SATISFIED | (meet their needs) | high influence/ low interest
|  | MANAGE CLOSELY | (key player) | high influence/ high interest

## Stakeholderanalysis II
Stakeholderanalysis II
(once defined the Stakeholderanlaysis I table, try to link the different stakholders, analysing the level of influence amongst them; You can also discuss on strategies to move stakholders from the left side (low interest) into the right side (high interest); This excercice will help to complete stakeholdermapping table and define the Strategy; this is best done in a Working Group session with flipcharts; find below an example on how to link them)

## PESTLE anlaysis
PESTEL Analysis
A good tool to use to help you identify all your stakeholders is PESTLE. By considering each of these categories and how they relate to your project, you can then identify stakeholders. For example when thinking about the Legal aspect, you may realise a contract for services is needed. This will require input from our Legal team, so clearly they are a stakeholder. (from the 'Stakeholder analysis and management toolkit' , University of Manchester; https://www.alnap.org/help-library/stakeholder-analysis-toolkit)
The factors explored in a PESTLE Analysis include:
| THEMATIC | COMMENT | STAKEHOLDERS
P | Political | Extent to which political factors influence the market and accordingly the project. This would include new taxes, regulationes, construction codes, political strategies, etc.
E | Economic | This includes overall economic forces that could affect the project, such as inflation rates, interest rates, foreign exchange rates, or economic growth patterns.
S | Social | These factors look the social environment of the market, such as cultural trends, demographics and population analysis. Also important to this part of the analysis are attitudes and shared beliefs of the target consumer, including those around health, work, leisure, money, family and religion.
T | Technological | These factors include advancements in technology which could influence your product, either positively or negatively. Examples include communication technology, automation, legislation around technology and intellectual property, as well as competitor technology development.
L | Legal | This includes current and future legal and regulatory requirements impacting a product. These factors can include laws around consumer protection, labor, health and safety, taxes and trade regulations in the individual countries where the product will be sold.
E | Environmental | These factors include all those that influence or are determined by the surrounding environment. This aspect of the PESTLE is most important for industries such as tourism, farming, and agriculture. Examples of factors to analyze from an environmental angle are climate, weather, geographical location, and climate changes.
Note on C6: User: Comments or explanations need to be addapted to be more specific the shelter and building environment/constructin activities