GSC Strategic Advisory Group (SAG) Meeting Notes

Date: 31st  October 2019

Participants: Australian Red Cross, CARE International, Catholic Relief Services, Danish Refugee Council, Habitat for Humanity, IFRC, InterAction, IOM, Norwegian Refugee Council, UNHCR

Excused: ACTED/IMPACT Initiatives, Save the Children

Key Action Points of the Meeting

| Action Point | Who | Deadline |
| --- | --- | --- |
| 1.1.G.1. Prepare a “pipeline-break” analysis of what the surge and remote support team has achieved and what would be the consequences of not continuing this support in terms of what we did last year, what we could be doing and what we won’t be able to do because of running out of funding. | All agencies hosting GSC surge capacity and remote support. | For GSC meeting |
| 1.3.G.6. Develop case studies on transition to shelter and settlements recovery coordination: Nepal, Fiji, Iraq and Ukraine. | CRS, IFRC/ Australian Red Cross, UNHCR | November |
| 1.4.G.4. Prepare a discussion paper on the quality of shelter coordination support services and response in merged CCCM and Shelter Clusters compared to non-merged clusters. | NRC and DRC | November |
| Action Points: 2.1.G.1. (Advocacy & Communication). |  |  |
| - Increase ability to explain importance of shelter. Draw on agency capacity and expertise around Advocacy to help train us how to do this to different audiences for different purposes. Invite an Advocacy expert to the July SAG meeting to advice on way forward. (CARE, UNHCR) Share the GSC advocacy strategy with them in advance. - Identify key messages – prioritize and draw out top 5(?) messages - Think of simple process to define what advocacy can be done by whom and with what level of agreement and sign off. - Draw on Interaction work around importance of shelter - Identify pro bono assistance to work on marketing/messaging on importance of shelter to help sell complex ideas/concepts | Agencies with good advocacy teams CARE, UNHCR, other SAG members GSLA/SAG Interaction SAG agencies with private sector departments | Immediate November December |
| Action Points: 2.2.G.5. – Donor consultation group; - Work with DCG in defining who within their organizations is the access point/decision makers on key topics related to shelter - Map Agency access to donors on specific S&S related issues | GSCLA/SAG SAG agencies | October October |
| 2.3.G.4 – Link to 1.1.G.1. |  |  |
| - Revisit/Reboot consortium. Group the proposed activities and draw out the relevance as per field/global/WG/etc - Conduct basic assessment of field priorities – prioritize consortium activities needed/requested by field - Work on building knowledge/base capacity aside from further guidance – knowledge management element | CWG CWG/GSCLA CWG/GSCLA | Oct Oct December |
| Minutes of the GSC Meeting to be shared with SAG member before the SAG retreat in December | SAG Co-chairs | December |
| Action points: 3.1.G.4. – Organize a mini SAG meeting to review existing tools and guidance and decide on way forward Those who want to be part of the mini-SAG to look at evidence gaps and research questions to send an email to SAG co-chairs. UNHCR is contracting a bit of time from Oxford Brookes to look at this. Liaise with Interaction on the Academics-Practitioners initiative. UNHCR to discuss bilaterally with Interaction. | CARE, IMPACT, NRC, Save the Children, IOM + other agencies | December |
| Action points: 3.1.G.4. – Consider / Reflect on developing guidance and tools for shelter baseline (park it until 3.1.G.4 above advances) | CARE, IMPACT, NRC, Save the Children, IOM + other agencies | Pending on the above |
| Action points: 3.1.G.4. – Develop guidance and tools for real time outcome monitoring (pending on the above) | Based on 2019 discussions | 2020 |
| Action points: 3.1.G.4. – Ensure linkages between the brainstorming efforts on outcome monitoring and the vulnerability classification WG | Vulnerability classification WG | Immediate |
| Action points: 3.1.G.8. – Download and use the application and provide feedbacks (to Neil and Hannoa) | SAG | Immediate |
| Action points: 3.1.G.8. – Communication regarding the app to ensure it is used | Support team | December |
| Action points: 3.1.G.9. – Establish linkages/synergies between the vulnerability classification WG and SPHERE / Disability WG / DTM Pass this point on to the Vulnerability Classification WG | Vulnerability classification WG | Immediate |
| Action points related with 3.2.G.2. – Evidence on multi sectoral importance of shelter – look at the work of Interaction and discuss pending issues at the SAG retreat in December. | SAG agencies | December SAG retreat |
| Action points: 3.3.G.5. – Website – SAG members to send feedback on website to support team | SAG | Ongoing |
| Action points: 3.3.G.8. – Communities of Practice – Liaise with RedR on knowledge point and monitor how it is used and it could replace our online tools | Support team | June |
| Include a discussion on participation at the GSC Meeting in the session of the December SAG Retreat | SAG co-chairs | Dec SAG Retreat |
| Please share topics to discuss at the SAG retreat. | SAG members | November SAG Teleconference |
| Send comments on the GSC submission for a networking event at the WUF | SAG agencies | 31st October |
| Discuss how we use the event strategically at the SAG retreat | SAG agencies | SAG retreat |
| Cash WG leads to discuss with CLAs regarding the opportunity to roll-out the outcome indicators for multi-purpose cash grants. | Cash WG leads and CLAs | By the SAG retreat |
| Next SAG Meeting to be moved one week before so it is not too close to the SAG retreat | SAG co-chairs | Immediate |

- Welcome, revision of the minutes, and revision of agenda

No changes to the meeting agenda were suggested. The Chair went through the Action Points from the previous SAG Meeting providing an update on progress made to date. Pending Action Points are as follows:

| Action Point | Who | Deadline |
| --- | --- | --- |
| 1.1.G.1. Prepare a “pipeline-break” analysis of what the surge and remote support team has achieved and what would be the consequences of not continuing this support in terms of what we did last year, what we could be doing and what we won’t be able to do because of running out of funding. | All agencies hosting GSC surge capacity and remote support. | For GSC meeting |
| 1.3.G.6. Develop case studies on transition to shelter and settlements recovery coordination: Nepal, Fiji, Iraq and Ukraine. | CRS, IFRC/ Australian Red Cross, UNHCR | November |
| 1.4.G.4. Prepare a discussion paper on the quality of shelter coordination support services and response in merged CCCM and Shelter Clusters compared to non-merged clusters. | NRC and DRC | November |
| Action Points: 2.1.G.1. (Advocacy & Communication). |  |  |
| - Increase ability to explain importance of shelter. Draw on agency capacity and expertise around Advocacy to help train us how to do this to different audiences for different purposes. Invite an Advocacy expert to the July SAG meeting to advice on way forward. (CARE, UNHCR) Share the GSC advocacy strategy with them in advance. - Identify key messages – prioritize and draw out top 5(?) messages - Think of simple process to define what advocacy can be done by whom and with what level of agreement and sign off. - Draw on Interaction work around importance of shelter - Identify pro bono assistance to work on marketing/messaging on importance of shelter to help sell complex ideas/concepts | Agencies with good advocacy teams CARE, UNHCR, other SAG members GSLA/SAG Interaction SAG agencies with private sector departments | Immediate November December |
| Action Points: 2.2.G.5. – Donor consultation group; - Work with DCG in defining who within their organizations is the access point/decision makers on key topics related to shelter - Map Agency access to donors on specific S&S related issues | GSCLA/SAG SAG agencies | October October |
| 2.3.G.4 – Link to 1.1.G.1. |  |  |
| - Revisit/Reboot consortium. Group the proposed activities and draw out the relevance as per field/global/WG/etc - Conduct basic assessment of field priorities – prioritize consortium activities needed/requested by field - Work on building knowledge/base capacity aside from further guidance – knowledge management element | CWG CWG/GSCLA CWG/GSCLA | Oct Oct December |

On 1.3.G.6. UNHCR is advancing on Iraq and Ukraine. Fiji is under discussion with Australian RC. Regarding Nepal, CRS can update the Shelter Projects case study. Cecilia hosted a conversation on recovery coordination at the GSC Meeting. Notes on that session should be shared in case there are other action points. There is also a case study on Fiji in Shelter Projects that could be updated.

On 1.4.G.4. NRC and DRC are advancing some work, aiming to complete something by December or at least to be able to report progress on it by the SAG retreat.

Regarding Interaction study on the importance of shelter, a consultant is engaged on it. Report expected sometime in December, will be shared with the SAG for feedback. Perhaps that could be the key theme for the next edition of the SoHSS, the wider impact of shelter.

Regarding 2.2.G.5.1), the CLAs met with ECHO and USAID at the GSC Meeting.

- October Shelter week

The satisfaction survey of the GSC Meeting showed that 96% of the 55 respondents felt that the GSC Meeting achieved its purpose.

Some of the sessions on the second day were on the shelter sectorial content, becoming a bit more blurred with the Shelter Meeting. Consider if we want to have more time on technical, sectorial discussions, perhaps through one day GSC Meeting and two days on the technical, sectorial content.

Generally went well. Regarding planning, we spent about 3 SAG Meetings discussing and preparing and in the end much of it didn’t happen. Maybe reconsider if we need to spend that time planning when we know it won’t happen because we don’t have the time or the budget.

We managed to get a lot of participation from governments and partners, that worked and should do more of it next year.

The Ignite Talk was enjoyable, perhaps it would be better to start off the two days with the Ignite Talk to frame the Meeting instead of in the second day.

We should encourage participants / cluster coordinators to link up more throughout the year and just not at the annual Meeting, through the CoPs or other means, other meetings, learning, sharing. The Regional Forums can do this role, cluster to cluster, peer to peer learning at the regional level, etc. Some of this was discussed at the Shelter Coordination Workshop.

The minutes includes some feedback and analysis coming out of the GSC Meeting. The draft minutes will be shared before the SAG retreat.

| Action Point | Who | Deadline |
| --- | --- | --- |
| Minutes of the GSC Meeting to be shared with SAG member before the SAG retreat in December | SAG Co-chairs | December |

- Progress on Strategy Implementation – Pilar 3 Advocacy

The SAG went through the progress made in implementation of pillar 3 through the online tool here. The priority activities pending are the following:

| Action Point/Decisions | Who |  | Deadline |
| --- | --- | --- | --- |
| Action points: 3.1.G.4. – Organize a mini SAG meeting to review existing tools and guidance and decide on way forward Those who want to be part of the mini-SAG to look at evidence gaps and research questions to send an email to SAG co-chairs. UNHCR is contracting a bit of time from Oxford Brookes to look at this. Liaise with Interaction on the Academics-Practitioners initiative. UNHCR to discuss bilaterally with Interaction. |  | CARE, IMPACT, NRC, Save the Children, IOM + other agencies | December |
| Action points: 3.1.G.4. – Consider / Reflect on developing guidance and tools for shelter baseline (park it until 3.1.G.4 above advances) |  | CARE, IMPACT, NRC, Save the Children, IOM + other agencies | Pending on the above |
| Action points: 3.1.G.4. – Develop guidance and tools for real time outcome monitoring (pending on the above) |  | Based on 2019 discussions | 2020 |
| Action points: 3.1.G.4. – Ensure linkages between the brainstorming efforts on outcome monitoring and the vulnerability classification WG |  | Vulnerability classification WG | Immediate |
| Action points: 3.1.G.8. – Download and use the application and provide feedbacks (to Neil and Hannoa) |  | SAG | Immediate |
| Action points: 3.1.G.8. – Communication regarding the app to ensure it is used |  | Support team | December |
| Action points: 3.1.G.9. – Establish linkages/synergies between the vulnerability classification WG and SPHERE / Disability WG / DTM Pass this point on to the Vulnerability Classification WG |  | Vulnerability classification WG | Immediate |
| Action points related with 3.2.G.2. – Evidence on multi sectoral importance of shelter – look at the work of Interaction and discuss pending issues at the SAG retreat in December. |  | SAG agencies | December SAG retreat |
| Action points: 3.3.G.5. – Website – SAG members to send feedback on website to support team |  | SAG | Ongoing |
| Action points: 3.3.G.8. – Communities of Practice – Liaise with RedR on knowledge point and monitor how it is used and it could replace our online tools |  | Support team | June |

Regarding 3.1.G.4, Interaction got one year funding under the Academic-Practitioners initiative to develop a research and learning agenda. This includes about 25 Universities interested in it. Happy to work with Oxford Brookes on this to streamline efforts. Link also with the work done by Aaron Opdyke and presented at the GSC Meeting last year or the year before.

Regarding 3.1.G.8, UNHCR has provided funds to develop further the existing application. Any feedback, please send to Neil and Hannoa.

Regarding all points related to 3.2.G.2, the work by Interaction and the link to 3.1.G.4 as well as possible theme for the SoHSS is making progress on prioritizing the multi-sectorial impact of shelter. We should look at them in light of the work of Interaction and look at what is pending at the SAG retreat.

Regarding 3.3.G.8. there are efforts in the website development to improve the CoPs.

Regarding 3.3.G.10, there were a number of launches and a feedback survey was circulated.

Additionally, IOM mentioned that they have received funding from USAID/OFDA to compile Information, Education, and Communication (IEC) materials that country-level clusters have been developing over the last years. They will be working closely with the WG on Promoting Safer Building.

- SAG Retreat

| Action Point | Who | Deadline |
| --- | --- | --- |
| Include a discussion on participation at the GSC Meeting in the session of the December SAG Retreat | SAG co-chairs | Dec SAG Retreat |
| Please share topics to discuss at the SAG retreat. | SAG members | November SAG Teleconference |

- WUF

IOM on behalf of the GSC drafted a request for a networking event which has been fairly general just as a placeholder for the time being. We need to think strategically how we use this space if approved as well as how we link up with other submissions from GSC agencies.

Other submissions include one by Interaction (with CARE International, Habitat for Humanity) on the wider impact of shelter.

| Action Point | Who | Deadline |
| --- | --- | --- |
| Send comments on the GSC submission for a networking event at the WUF | SAG agencies | 31st October |
| Discuss how we use the event strategically at the SAG retreat | SAG agencies | SAG retreat |

- AOB

- Regional consultations in BKK on 21st Nov. Urban Settlements WG (USWG) would like GSC to disseminate the event details soon. Specially reach out to non-shelter cluster colleagues via GCCG or cluster coordinators.

- USWG will also visit the Philippines/Tacloban (23-26 November) and would like to meet/discuss with current or former colleagues.

- InterAction will gather video of communities’ perspectives on S&S for the above research. Contacts with families/colleagues appreciated.

- Guatemala Shelter/DRR Event on 9th/10th December. Will include Spanish online S&S Training, PCI’s Neighbourhood guidance note consultations, and possibly IOM on migration issues. Others are welcome to participate/present.  Will share info.

- A lot of work was done last year with Grand Bargain workstream on defining outcome indicators for multi-purpose cash. There was a negotiation on how many indicators they would allow to have in. The work is done and for roll out they are relying on individual agencies and responses picking this up, which seems a bit ineffective. Perhaps the Shelter Cluster can take a bit of a lead on this roll-out, given we have historically raised concerns about multi-purpose cash and the monitoring that follows. This is perhaps an opportunity for us to try something instead of just complain. A bit of a discussion in the WG but there isn’t consensus, therefore why it is being raised with the SAG.

| Action Point | Who | Deadline |
| --- | --- | --- |
| Cash WG leads to discuss with CLAs regarding the opportunity to roll-out the outcome indicators for multi-purpose cash grants. | Cash WG leads and CLAs | By the SAG retreat |
| Next SAG Meeting to be moved one week before so it is not too close to the SAG retreat | SAG co-chairs | Immediate |

The next SAG meeting will be on 21st November

at 11am Geneva time, 6am Washington, 9pm Melbourne.