## Slide 1
Shelter Working Group Meeting
Thursday 6 July, 10AM
Consortium of Humanitarian Actors Office

## Slide 2: Agenda
Introductions
Information Management
District Focal Point Update
Protection & Shelter
NBRO Drone assessment
Strategy update
AOB and Next Meeting

## Slide 3: Overview of planned response (4 districts)
Item | Total # of HH
Household NFIs Kits/ Cash | 26635
Shelter Repair kits/Cash | 5700
Repairing | 58
Community Based Shelter Programme | 400
Permanent House | 290
Transitional Shelter | 540
Partially Damaged Houses | 20439
Fully Damaged Houses | 2967
Items | Total Response Needed | Response Plan | Gap
Cash/ Shelter Repair Kits | 20439 | 6158 | 14281
Cash/ Household NFI Kits | 23406 | 26635 | (3229)
Permanent House/Transitional Shelter | 2967 | 830 | 2137
Transitional Shelter | 90
Permanent House | 250
Unmarked District for the Response Plan

## Slide 4: New reports
- by District and DS Division
- by Agency, then District and DS Division
Please check your agency’s information and send us updates

## Slide 5: Gaps in planned coverage – by district
Chart: Objective 1 - Emergency shelter (Shelter repair kits/repairs vs partially damaged houses)
| Kandy | Matale | Nuwara Eliya | Ampara | Kegalle | Rathnapura | Colombo | Galle | Gampaha | Hambantota | Kalutara | Matara | Unassigned
Planned | 2460 | 3298
Gap | 123 | 26 | 51 | 43 | 155 | 5231 | 83 | 3374 | 96 | 600 | 3329 | 2747 | 0

## Slide 6: Gaps in planned coverage – by district
Chart: Objective 2 - Support to return (Household NFI vs fully or partially damaged houses)
| Kandy | Matale | Nuwara Eliya | Ampara | Kegalle | Rathnapura | Colombo | Galle | Gampaha | Hambantota | Kalutara | Matara | Unassigned
Planned | 253 | 6928 | 3658 | 8267 | 7782
Gap | 124 | 26 | 52 | 43 | -87 | 1612 | 93 | 174 | 98 | 734 | -4356 | -659 | 0

## Slide 7: Gaps in planned coverage – by district
Chart: Objective 3 - Transitional/core shelter (Transitional/core/permanent vs fully damaged houses)
| Kandy | Matale | Nuwara Eliya | Ampara | Kegalle | Rathnapura | Colombo | Galle | Gampaha | Hambantota | Kalutara | Matara | Unassigned
Planned | 150 | 20 | 280 | 40 | 340
Gap | 1 | 0 | 1 | 0 | 11 | 699 | 10 | 438 | 2 | 134 | 302 | 1038

## Slide 8: Progress to date
Chart: Number of Households
| Objective 1 - Emergency Shelter | Objective 2 - Support to return (NFI) | Objective 3 - Transitional/core shelter | Objective 4 - Technical support
Completed distributions | 8 | 3659
Ongoing distributions | 1880
In pipeline (procurement/onroute) | 2500
Planned (funded) | 5750 | 13849 | 180 | 600
Planned (subject to funding) | 5000 | 650

## Slide 9: Web Details
www.sheltercluster.org
https://www.sheltercluster.org/response/sri-lanka-floods-2017
https://www.sheltercluster.org/sri-lanka-floods-2017/documents/21062017-nbro-presentation
https://www.sheltercluster.org/response/sri-lanka-floods-2017/documents?sort=date&sort_direction=DESC

## Slide 10
Affected – 630,000 PP
(126,000 HH)
Damaged HH - 24,742
Partially - 21,616
Fully
3,126
May Displaced HH
~ 75,000

## Slide 11
Shelter Recovery
Self- Recovery
Assistance (need based)

## Slide 12
Goal
The goal of the Shelter Sector is to provide people affected by the floods with the means to live in a safe, dignified and appropriate shelter. The Sector will support owner-driven recovery, prioritise the most vulnerable people, families and communities, and invest in DRR.
Objectives
Objective 1: Emergency shelter
  Provision of emergency shelter items contributing to self-recovery such as shelter kits (including tools and CGI) or their cash equivalent, supported by appropriate training, community mobilisation and IEC material.
Objective 2: Support to return
  Support the most vulnerable households to return through the provision of NFI kits (including kitchen sets, solar lights), or their cash equivalent along with appropriate IEC material.
Objective 3: Transitional/Core
  Provision of transitional shelter options for vulnerable households with fully damaged houses, or in identified high risk zones where a longer term permanent housing solution will need to be found.
Objective 4: Technical support
  Provide education information and communication on safer construction principles, and community-based hazard awareness, preparedness and DRR, during all phases of the response.

## Slide 13
No Damage
Minor damage requires little or no assistance
Up to 30% damaged, can be repaired
Greater than 30% damaged, can be repaired
Destroyed or damaged beyond repair
Emergency Shelter
Displaced
Host Family / Rental
Non-Displaced
NFI (light daamge)
Non-Displaced
Repair Kit (Major damage)
Displaced
Collective Centres
Protection Support | Tents | Tool Kits | NFI | Technical support | Financial
X |  |  | X |  | X
X |  |  | X | X | X
X |  | X | X | X | X
X | X |  | X |  | X
Emergency shelter support options
Damage Category 1 - 4
Impact

## Slide 14
Emergency/Transitional Period
Safe Site ?
No
Yes
Relocate
Shelter
Repair Kit
Transitional /core shelter
Partially Damaged
Fully Damaged
Undamaged
To provide SPHERE minimum shelter and protection standards
  Access and Protection
  Safe
  Durable – Sufficient for the period until full recovery is achieved
  Dignified
  Sufficient to meet social / cultural / and livelihood needs
Transitional shelter options are required for households that do not have the resources, or where there are other constraints, that delay recovery. Ideally investment in transitional solutions should promote and contribute toward recovery, such as materials, tools, and technical training and information.
Transitional/core shelter
Technical support