## Slide 1: Shelter Cluster joint monitoring INITIAL FINDINGS
2 December 2009

## Slide 2: Where we are
Timeline – now in the final (4th) week of monitoring – final results and analysis next week
Database online – work in progress! – includes results (submitted) from first 2 weeks (44 households in 4 districts)
Agencies still participating: CRS, Care/P3SD, Save the Children, Oxfam/Walhi/Kabisat, PMI, Islamic Relief
Constraints – submission deadlines, complete form filling / complexity of form, language / communication

## Slide 3: Household survey
84% houses severely/moderately affected
58% living in original house
23% in below-standard transitional shelter
16% in acceptable transitional shelter
3% with host families
Apparently no significant increase in household numbers – couple of exceptions in Kota Padang
Have interviewed mainly male ‘owners’ (less females, few tenants)

## Slide 4: Self-recovery
27% of people are rebuilding their homes – what are the other 63% doing?
90% say they need building materials (bricks, wood, cement, sand) & cash
46% say they have insufficient labour to rebuild
No notable difference in responses between rural / urban population (but small sample!)

## Slide 5: Household items
Imperfect form – not getting clear answers on quality / use / gaps
Most commonly distributed items are blankets and buckets
Most items received / bought are being used, with a few exceptions in the case of mosquito nets and cooking pots
Vast majority of household items have been bought from shops

## Slide 6: Tools
Imperfect form – not getting clear answers on quality, use or gaps
Most commonly distributed / bought items are machetes and claw hammers
People want building materials and cash, not just tools, to rebuild

## Slide 7: WASH
Good, simple questions and clear results!
Before earthquake 58% people used latrines, after earthquake 44%
Majority of people use wells for water collection (74% before, 65% after)
Rain and river water are also commonly used, including in Kota Padang
Few people use water delivery or water pipes