# Detailed methodology

This section outlines the methodology used for the assessment.

## Selection of the target area

Given the size of the City of Padang, the number of damaged houses, and the relatively short period to carry out the assessment, an approach was adopted that targeted Community Neighbourhood Units (RT) in a random selection of Kelurahan within the 11 Kecamatan. The assessment looked at those residing in severely or moderately damaged houses; lightly damaged houses were omitted.

The Badan Pendukung Rehabilitasi dan Rekonstuksi (BPRR), responsible for coordinating the Rehabilitation and Reconstruction Recovery Process in West-Sumatra, identified 423 Community Neighbourhood Units (RTs) to be the most heavily damaged. These 423 RTs all had at least 50% severely and moderately damaged houses, corresponding to 15,679 houses. In order to attain a statistically relevant sample of these damaged RTs, the assessment had to assess at least 10% of the 423 RTs. At the request of the assessment team, the BPRR kindly produced a list of 50 RTs which would provide an accurate sample of The City of Padang. The BPRR team also provided a list of 25 other RTs in the event that some of the initial RTs selected did not meet the assessment criteria.

When selecting the number of RTs per Kecamatan to be assessed, the total number of RTs per Kecamatan was divided by the 423 RTs identified, and multiplied by the 75 RTs targeted, as per the formula below:

Figure 1: formula used for calculating number of RTs to be assessed

RT per Kecamatan/423RT    X  75 RT = Number of RT to assess per Kecamatan

## Target area and number of interview

The assessment was conducted in 52 RTs over 34 Kelurahan in 11 Kecamatan. 2,114 households were interviewed, encompassing a wide range of socio-economic factors.

Figure 2: number and distribution of 2,114 household interviews per Kecamatan

The number and percentage of interviews vary from one Kecamatan to another for the following reasons:

the total number of RT per Kecamatan are different, according to the formula in section 2.1;

the numbers of households in each RT were different, ranging between 25 and 163;

the number of families that had fled completely collapsed houses differ in each RT;

self-recovery efforts varied between areas; and

in semi-rural areas, especially in Kecamatan Koto Tangah, there were severely damaged houses that were vacant before the earthquake.

52 RT Leaders including their households were interviewed. An extra 25 RT Leaders were also interviewed in order to gather further general information at the RT Level. Interviews with 20 heads of Kelurahan were conducted to gather general information on standard procedures when an emergency strikes. The total for these assessments is shown in the following figure:

Figure 3: number of RT Leaders and Heads of Kelurahan interviewed

## Research instrument: questionnaires

Two questionnaires were used. The first, for the RT leader, was to ensure that the RTs selected contained households living in severely and moderately damaged houses. The second was used for the detailed household interview to collect information on the actual living situation of the affected households. The questionnaires were tested prior to the assessment beginning by the Coordination team with two RT leaders and 2 households. Both questionnaires can be found in the annexes.

The Questionnaire was comprised of closed questions, as they were appropriate to the objectives and are easier to process.  Open-ended questions were employed in a few instances, for example, when the answer was ‘other’. The average duration of the household interview was 40 minutes.

## Criteria for vulnerable households

Six criteria for vulnerable households were used and defined as follows:

Person with a Disability (PwD)

Large families with more than 4 children, 0 to 5 years old

Single parents living with dependent children

Elderly living alone

Pregnant women without insurance coverage (Jamkesmas)

Low income (0 to 1.5 million Rp per month)

  - Note: the team estimated the threshold for Low Income (LI) according to the monthly cost for a family of four as shown below:

    - Food for 2 adults:  				600,000.- IDR

    - Food for 2 child, 5 to 17 years old: 		400,000.- IDR

    - Nutrition milk for 1 child, 0 to 5 years old:	200,000.- IDR

    - Scholarship for 1 child, 5 to 17 years old:	300,000.- IDR

    - Transport:					200,000.- IDR

Total monthly needs:				1,500,000.- IDR

## Confidentiality and expectations management

An objective of the assessment was to collect statistical information about the general situation of the most vulnerable affected households. To avoid creating false expectations of support, the enumerators did not take names, except for the RT leaders. This was explained to each of the households.

## Comments on the questionnaire

Overall, the questions were well understood by both the assessors and households, however, some specific terms were not clear, such as ‘cash stimulus’ and ‘standard emergency procedures’.

## Training of the volunteers

The training of the volunteers took place over one day; the first group of 38 participants in the morning and the second group in the afternoon. The content of the training included a short presentation of the Shelter Cluster and its role, then went on to explain the objectives and method for conducting the assessment.

There was a follow-up training for the six volunteers acting as Focal Points. This included: reporting mechanisms for any issues and for the progress; and basic guidance on how to evaluate housing damage.

## Data collection, implementation, monitoring and reporting

Data collection was undertaken 78 volunteers; 36 from BPRR (Andalas University Engineering students), 40 from the Indonesian Red Cross (PMI) and two Indo-Chinese. The volunteers were split into 36 teams of two volunteers (mostly gender mixed, 29 females and 49 males). Six others volunteers (three PMI, three BPRR) participated as Focal Points (Field Assistant).

Volunteers received a per diem, one pre-paid mobile card for each team leader and focal point, and a daily allowance for motorbike use. All volunteers were provided with medical insurance for assessment period.

There were daily morning and evening meetings with the Focal Points to collect the questionnaires, address any problems encountered, and for the daily progress report (see attachment X.V). Following each debriefing, the Focal Points organized meetings with their teams to report the meeting outcomes and to select the areas for the next day.

By way of monitoring the assessment, the Coordination team independently assessed 3 RT Leaders, 2 households and 1 head of Kelurahan to cross-check the understanding of the questionnaire by the participants.

## Database, data entry and analysis

The Coordinator assistant and the Database officer prepared the Database according the questionnaire. The Database Officer and three volunteers entered approximately 100 questionnaires each every day for ten days. The data was constantly checked and double-checked.

## Assessment cost

The operational assessment costs were 140,155,000 Rupiah (approximately 15,000 USD) and were funded by Oxfam. Mercy Corps funded the salary of the Assessment Coordinator.

## Time line

The assessment period was 37 days and was allocated for the following activities:

Preparation				18 days		2 February to 21 February 2010

Training of volunteers			1 day		22 February 2010

Assessment				9 days		23 February to 6 March 2010

Debriefing				1 day		8 March 2010

Data cross check, analyse and report	8 days		9 March to 19 March 2010

## Human resources

Assessment Coordinator

Coordination Assistant (finance, administration and HR management)

Coordination Assistant (questionnaire finalisation, training of volunteers, etc.)

Database Officer (to prepare the database, data entry and analyse)

six focal points, 72 volunteers, and 3 data entry volunteers

## Activities

Collection and review of data from previous assessments undertaken in The City of Padang;

Design assessment format in coordination with interested parties;

Preliminary assessment review, coordination with local Government structures and selection of the target area having the most vulnerable affected households;

Preparation of assessment materials, training package, training of the volunteers, assessment, database, analyse of the results, mapping of the location, final report and recommendations; and

Preparation of the questionnaire and assessment of the affected households concerning their vulnerability, living situation and their incomes before and after the earthquake.

## Final comments on the assessment process and lessons learnt

It was quite challenging conducting an assessment four months after the earthquake in an area which received virtually no shelter assistance from responding agencies. Households had clearly grown tired of answering questions.

It was useful to meet the RT Leader before beginning the household assessment to verify that the RT still met the selection criteria, however it would have been better to have met the head of Kelurahan first to crosscheck the RT, and to change if needed.

Given the relatively short time available to conduct the assessment, it was difficult to ensure that the RTs selected corresponded to the selection criteria before beginning the assessment. Better results may have been achieved if the assessment teams had met the head of the Kelurahan to get their advice on the selected RTs, to ensure the targets included the poorest affected households. As it happened, there were instances where selected RTs had recovered when neighbouring RTs faced worse conditions.

Many of the volunteers had previous assessment experience, which was a great advantage. The mix of PMI volunteers and technical students was also an asset. The Andalas University students assisted the PMI volunteers on the evaluation of the damage, while the PMI volunteers shared their knowledge of working in a humanitarian context with their colleagues.

Further efforts should be made to ensure that terms used are understood in the local dialect.

The training could have benefited from there being one full day per group of participants. This would have allowed more time with the questionnaires. Also, the assessors and not only the focal point should have been trained on evaluating housing damage.

The Damage and Loss Assessment cited 49,493 damaged houses, with 26,179 being heavily and moderately damaged.

Lightly damaged houses were categorised as being ‘cosmetic damage’ by the damage assessors.

The lists also included the poorest Kelurahan, as recommended by the Department of Welfare

See Annex IV: tables of the selected areas and number of interviews

To learn how to use the Database, see Annex IX: Database Explanation.

The database was prepared in Microsoft Excel. There are two databases: the first is concerning the RT Leader questionnaire, called ‘Database Q.1-RTL’; the second concerning the Households questionnaire No 2 called ‘Database Q2-HH’

See ANNEX XI: Questions to review from our questionnaires