| - Shelter Cluster Operational Framework |  |
| --- | --- |
| Country | Philippines |
| Region | Region XI and Caraga Region |
| Response Name | Typhoon Pablo |
| Cluster Lead Agency | Dept Social Welfare and Development (DSWD) |
| Co Leads | IFRC and IOM |
| Contacts DSWD |  |
| Contacts IFRC |  |
| Contacts IOM |  |
| Strategic Advisory Group (SAG) - Agencies | DSWD, NHA, Handicap Int, IOM, UNDP, CRS, Habitat for Humanity, UNHab, UNHCR, Save, Plan, Lutheran World Relief, Helpage International/Cose, World Vision, Oxfam (PINGO), HRC. |
| Technical Working Groups (TWIG’s) - Agencies | Technical TWIG – lead agency IOM – Plan, Save the Children, CRS, DSWD, HI, World Vision |
|  | Integration/cross cutting issues TWIG – lead agency UNDP, Unicef, UNCHR, UNFPA, ILO, Plan, Save the Children, CRS, DSWD, HI, Oxfam/HRC |
|  | Housing land and settlements TWIG – lead agency NHA/Habitat for Humanity, Plan, Save the Children, CRS, HI, DSWD, MGB |

| B. Strategy Status | Endorsed by Cluster (SAG) | Effective Date 21th Dec 2012 | Deadline for Revision 10th Jan 2012 |
| --- | --- | --- | --- |

| C. Monitoring and Reporting |  |
| --- | --- |
| Agency Reporting Modalities | Agency reporting template. |
| Cluster Performance Monitoring | To be confirmed. |
| Operational Impact Monitoring | To be confirmed. |

| D. Coordinated Assessments |  |
| --- | --- |
| Policy | Accurate data and good analysis are key to identifying needs and gaps and to identify and locate groups and individuals with specific needs or those at heightened risk for priority assistance. Women, girls, boys and men have different needs, capabilities and constraints and disasters and emergencies tend to exacerbate existing vulnerabilities. It is therefore essential to consult with all affected groups to establish needs and define the most effective way to provide shelter assistance, through the distribution of shelter materials, allocation of NFIs, cash transfer programs, or other forms of shelter support that may be appropriate. Where possible participatory assessments should be encouraged and during the assessment enumerators should meet with men and women separately, in a setting that makes both men and women feel comfortable enough to express their concerns. |
| Current assessments | Assessment activities to date are : - The initial multi-sector rapid assessment was conducted by the Government with support provided by the UNDAC team, OCHA and agencies. This commenced on Thu 6th and reported back on Sun 9th. - As part of the Shelter Cluster response a specialist assessment and GIS team from REACH were deployed to conduct a household level assessment that includes secondary data review and key informant interviews. Field work commenced on Wed 12th and was complete by Wed 19th. Reporting will be complete and shared to inter cluster by Fri 28th Dec 2012 - Shelter cluster partners are also conducting local operational assessments. - As part of their CCCM cluster lead IOM have also rolled out their Displacement Tracking Matrix (DTM). The Shelter Cluster IM expects to build on and complement these assessments conducted by cluster partners. |
| Planned assessments | Cluster partner organizations are planning assessments in their areas of operation Recommended: - Cluster partners agree to use the same assessment form to ensure all data can be collated and cross-referenced. - Recommended assessment form is shared on the cluster website. - Database and reports are shared with partners. - Assessments are coordinated with other agencies working in the area. |

| E. Case loads |  |  |
| --- | --- | --- |
| Target groups |  | Case load Details held in Annex |
| Inside EC | Displaced HHs living in EC’s. e.g. schools. | To be determined based upon assessments. |
|  | Displaced - HHs living in makeshift and or tents which are recognised by DSWD and classified as ‘inside EC’ | To be determined based upon assessments. |
| Outside EC | Displaced - displaced HHs living in spontaneous settlements in makeshift shelters or tents. Not recognised by DSWD as being ‘in side EC’s’. | To be determined based upon assessments. |
|  | Displaced HHs living with host families, etc. | To be determined based upon assessments. |
|  | Non-displaced HHs living in partially damaged houses. | To be determined based upon assessments. |
|  | Non-displaced HHs living in significantly damaged housing. | To be determined based upon assessments. |
|  | Non-displaced HHs living in makeshift shelters (or tents) on the plots of their totally destroyed house. | To be determined based upon assessments. |
|  | Total (Based on DSWD published figures for totally destroyed and damaged houses in the Region XI and Caraga Region as of 21 Dec) | 128,591 |
| Case load, notes assumptions and sources of information |  |  |
|  | - DSWD are the source of all numerical information - Average size assumed to be 5 members - source xxx - It is important to have as much information as possible about the beneficiary communities to appropriately plan shelter and housing responses. Taking into account the different shelter design needs or constraints of women and men, and persons with specific needs – for example single or pregnant women, unaccompanied minors, older persons, persons with disabilities, sexual minorities - may limit risks faced by these stakeholders. |  |

| F. Shelter strategic options matrix |  |  |  |  |
| --- | --- | --- | --- | --- |
| Target groups |  | Objective of intervention | Emergency activities up 6wks | Recovery activities 2wk to 24mth |
| Inside Evacuation Centres (ECs) | Displaced HHs living in EC’s. e.g. schools. | - Support provided to HHs to return to their original repaired or reconstructed homes. - HHs relocated to transitional camps. - Permanent resettlement. | - Repair of EC’s |  |
|  | Displaced - HHs living in makeshift and or tents which are recognised by DSWD and classified as ‘inside EC’ |  | - Tents - T Shelters | - Full or partial shelter repair kit, or - Permanent house solutions, depending on extent of damage to original shelter |
| Outside EC | Displaced - displaced HHs living in spontaneous settlements in makeshift shelters or tents. Not recognised by DSWD as being ‘in side EC’s’. | - Support provided to HHs to return to their original repaired or reconstructed homes. - HHs relocated to transitional camps. - Permanent resettlement. | - Tents - T Shelters | - Full or partial shelter repair kit, 0r - Permanent house solutions, depending on extent of damage to original shelter |
|  | Displaced HHs living with host families, etc. | - Support provided to HHs to return to their original repaired or reconstructed homes. - HHs relocated to transitional camps. - Permanent resettlement. | - Host family support - Tents - T Shelters | - Full shelter repair kit, or - Permanent house solutions |
|  | Non-displaced HHs living in partially damaged houses. | - Support provided to HHs to repair their partially damaged houses. - Permanent resettlement. | - Emergency shelter kit | - Partial shelter repair kit |
|  | Non-displaced HHs living in significantly damaged housing. | - Support provided to HHs to repair or rebuild their significantly damaged houses. | - Emergency shelter kit - Tents | - Full shelter repair kit, or - Permanent house solutions |
|  | Non-displaced HHs living in makeshift shelters (or tents) on the plots of their totally destroyed house. | - Support provided to HHs to rebuild their destroyed houses. | - Emergency shelter kit - Tents | - Permanent house solutions |
| Other | Renters: HHs who were renting a property which was damaged or destroyed. | - Support provided to regain rental accommodation. | - Emergency shelter kit - Tents - T Shelters - Rental support | - Rental support |
| Notes: |  |  |  |  |
| - All displaced and non displaced categories are subject to permanent resettlement when the Government declares ‘no build zones’. - Where appropriate cash grants or vouchers can be considered as a method of implementation – in coordination with appropriate support and monitoring mechanisms. - All repairs and permanent structures must be provided in coordination with the appropriate level of technical training, monitoring and guidance. - All repairs and permanent structures must comply to the appropriate recognised national standards and with guidance from the National Housing Authority. - Maximum recommended time for tents and tarps as a place of main habitation is 3 months. |  |  |  |  |

| H. Vulnerability Criteria |  |
| --- | --- |
| Family profiles | Define |
| Disability | Define |
| Age | Define |
| Low income | Define |
| Land tenure | Define |
| Persons requiring special attention | - Person’s habitual residence/displaced location is in geo-hazard area - Person’s habitual residence/displaced location is covered by ancestral domain - Person’s habitual residence/displaced location is in remote communities with minimal public services - Person’s habitual residence/displaced location is in conflict-affected area - Person who has experienced single/multiple displacement(s) due to conflicts, tribal feuds and natural disasters - Person who has no (or lost) birth certificate and who has difficulty accessing social welfare services - Person who has not received family access cards - Minority indigenous groups: Dibabawon, Mandaya,Mangguangan, Mansaka, Manobo, Moro |
| Persons with specific needs | - Single elderly - Elderly headed household - Woman headed household - Pregnant woman - Lactating mother - Single women - Child/Adolescent headed household - Child mother - Unaccompanied minor - Separated child - Single person with disability - Person/child with disability |

| I. Policy and Guiding Principles |  |
| --- | --- |
| The provision of temporary housing is to be guided by relevant international standards particularly the UN Guiding Principles on Internal Displacement – see Annex X. These principles are integrated into this operational framework and are summarised below. It is the responsibility of the aid community to support Government in meeting its obligations to the affected population. Further information is available from the Shelter Cluster, including practical steps to assist with implementation. |  |
|  | Considerations |
| Guiding principals | Apply relevant international standards particularly the UN Guiding Principles on Internal Displacement. |
|  | The cluster defined emergency shelter response as tents, tarps, shelter repair kits and tool kits. Transitional shelters and bunkhouses will be used were appropriate. |
|  | Use locally available human and material resources in order to achieve maximum participation and empowerment of the local economy without compromising the principles of environmental sustainability |
|  | Shelter programmes seek to ensure equity across all vulnerable groups. Such assistance should be based on independent assessment of level of damage, vulnerability, community resilience, hazard risk, and number of households affected. |
|  | Standardize the relief items. Avoid situation where different agencies provide different packages. |
|  | The typhoon affected areas of CARAGA and Region XI are conflict-affected for the past few decades. An estimated 60 - 80% of the affected communities are indigenous to these lands, and live in particularly remote hard-to-get areas. Ensure that these communities are receiving adequate and timely support on an equitable basis, and that the specific needs of these communities are properly considered. |
|  | Disaster risk reduction and mitigation measures are integrated into emergency response |
|  | Support community and owner driven reconstruction to build back better. |
|  | The emergency shelter response should move quickly into longer term DURABLE solutions. |
|  | Avoid partial coverage of needs in a beneficiary community. |
|  | Ensure distributions are well coordinated and dignified to ensure equal access of men and women to shelter materials and NFIs. |
|  | Prioritize good coordination of HCT members with lead cluster partner DSWD. Engage with, and build capacities of local authorities and Government coordination bodies. |
|  | Ensure proper linkages with relevant Clusters as appropriate, especially Health, CCCM, Water-Sanitation, Protection, and Early Recovery |
|  | Ensure mainstreaming of cross-cutting issues, See below |
|  | Explore and encourage the use of alternative technology for providing construction materials. Such alternative technology should be environmentally friendly and easy to use. |
|  | Encourage and enable the participation of affected communities in assessments, planning, implementation, monitoring and evaluation of shelter programmes. |
|  | Ensure that site planning reduces the risk of exploitation and abuse of women, girls, boys and men through choice of location, lighting and provision of public spaces for the social, cultural and informational needs of women, girls, boys and men. |
|  | Consider the different design needs of women and men, and persons with specific needs as well as ensure that shelter design is appropriate for the climate, social and cultural context |
| Policy | Ensure relocations due to hazard mapping are fair and equitable. The community to be relocated and the planned host community should be consulted and fully involved in the decisions making process. |
|  | In the first phase there is an emphasis on tarpaulins for roofing, but it’s also recognized that quick support is needed to assist those tying to build makeshift emergency shelter or repair damaged houses – shelter materials, repair kits, tool kits, etc. |
|  | When markets allow cash or vouchers are considered an adequate methodology. But they must be supported with appropriate levels of training, technical support/guidance and monitoring. |
|  | Maximise use of salvaged building materials. |
|  | All fallen trees belong to the DSWD. These are to be collected and processed for the shelter emergency and recovery programmes. Close coordination with UNDP on early recovery opportunities should be considered, e.g. saw mills, labour, etc |
|  | On-site / owner-driven construction is the preferred methodology. This methodology should be supported by the appropriate level of technical training, guidance/supervisions and monitoring. |
|  | Opportunities should be sought to encourage integration with livelihoods, e.g. building material markets, skilled artisans and unskilled labour, transportation of materials, etc, . |
|  | Tents are the least appropriate form of emergency shelter, with planned settlements the sheltering option of last resort |
|  | No use of illegally-sourced timber |
|  | Cash-for-Work or Food-for-Work are adequate methodologies, these should be used in combination of a wider package of support. Use common standards as advised by the Govt. Men and women should receive equal pay. |
|  | Prioritize allocation of resources according to agreed vulnerability criteria, and according to capacities and presence of Cluster members |
|  | Prepare timely transfer of responsibilities to local institutions, including Information Management unit |
|  | Emergency responses focus on the effective and timely provision of emergency and transitional Shelter. The shelter response reflects the linkages between shelter risk reduction, preparedness, relief, recovery, and development, resulting in a seamless transition from emergency to recovery and reconstruction. |
|  | Where income-earning shelter programming is either not possible, shelter programmes could identify alternate means of participation, such as skills-training in basic construction, for groups in the community that have not traditionally been in charge of building. Participation in shelter construction can offer women and girls greater financial independence. |
| Strategy | Support market-led/owner-driven recovery initiatives through self-help support at community level |
|  | Work with Gov’t and local authorities to inform households consistently and coherently through mass media on policy directives as they emerge, including, for example: - Technical advice (e.g practical and affordable storm resistant construction techniques) - Mechanisms for (land tenure) dispute arbitration - Advocacy for relocations to be community driven and supported by appropriate level of development |
|  | Establish need for emergency and temporary shelter solutions based on level of damage, vulnerability, community resilience, hazard risk, and number of households affected |
|  | Assistance should be prioritized equitably according to vulnerability (e.g child and female-headed households, the elderly, and physically disadvantaged) |
|  | Support those living with host families, self-settling in urban and rural areas, and, should it prove necessary, developing appropriate infrastructure for unplanned or planned camps. |
| Aim | To complement Government and civil society efforts in providing all disaster-affected persons with safe, appropriate, and habitable shelter – at least one safe room per household – in dignity, to defined international standards. |
| Objective | See Annex X Specific, Measurable, Applicable, Relevant, Prioritized, and Time-bound using indicators of success which have been pre-agreed within and between Clusters against which to measure progress |
| Standards | Provision of emergency and transitional shelter assistance will strive to comply with minimum standards as outlined in the following documents: Technical Guidelines and Standards established by the shelter cluster in Davao The Sphere Project; Humanitarian Charter and Minimum Standards in Disaster Response, 2011; (www.sphereproject.org) Transitional Settlement of Displaced Populations; (www.shelterproject.org) Guide to the use and logistics of family tents in humanitarian relief (ochaonline.un.org/lsu) |
| IM | Maintain an integrated monitoring capacity using common methodologies, definitions, and indicators |
|  | Carry out trend analysis of planned vs actual and report/inform where targets are not achieved. |
|  | Geo-statistical mapping of variables |
|  | Reporting within the Cluster – all members must report information to the DSWD lead cluster |
| Phasing | Work with the Early Recovery Cluster on merger and hand-over planning for reconstruction from the outset using early recovery frameworks |
|  | A standing preparedness capacity for renewed responses and the coordination thereof should be maintained as long as funds and capacities allow. |
| Comms | Ensure timely public information to beneficiaries on policies and shelter assistance |
|  | Beneficiary communications: ensure that feedback and complaint mechanisms are established for beneficiary communities |

| J. Cross Cutting Issues |  |
| --- | --- |
| Gender | - Gender inequality remains a challenge that contributes to discrimination and exclusion from access to resources, public services, education, healthcare services and employment and to gender-based violence. This undermines the human rights, health, dignity and the inherent potential of every human being. - Gender inequality takes many forms and is rooted in differential power relationships. Gender interacts with other dimensions of diversity such as - but not limited to - age, class, ethnicity (including minority and migrant groups), sexual orientation, HIV or AIDS status, and disability. - These interrelationships can further exacerbate inequitable and discriminatory behaviour and practices. - By advancing gender equality and embracing diversity, the impact of many other humanitarian problems can be reduced including violence, inequitable access to services, and the negative consequences of disasters. - IASC, Emergency Shelter: Gender Mainstreaming Tip Sheet |
| Disability | See annex X supported by Handicap International |
| Age | See annex X supported by Help age |
| HIV/Aids | To be confirmed |
| Environment | Care taken with building rubble – monitor content for asbestos or contaminants. |
|  | Ensure best practice during reconstruction for disposal of building waste materials. |
| Land tenure | - Ensure awareness of the differences in statutory and customary laws - Both formal and informal types of tenure should be considered - Humanitarian shelter assistance shall be provided to all disaster affected families irrespective of their legal tenure status. |

| K. Intercluster Coordination Current cluster configurations are held in Annex X |  |
| --- | --- |
| Protection | Refer to checklists in the Annex x. |
|  | The typhoon affected areas of CARAGA and Region XI are also conflict-affected for the past few decades. An estimated 60 - 80% of the affected communities are indigenous to these lands, and live in particularly remote hard-to-get areas. Many, but not all are residing in protected lands for indigenous communities, much of which is poorly developed (infrastructure) and where many villages are in remote areas that are hard to reach, especially after the Typhoon. Ensure that these communities are receiving adequate and timely support on an equitable basis, and also to ensure that the specific needs of these communities are properly considered by the various clusters |
|  | Without construction assistance, women and girls may feel pressure to engage in transactional/survival sex for help collecting materials and building a shelter. |
|  | Note - UNFPA will be carrying out monitoring to report on compliance with Protection checklists held in this framework. |
| Early Recovery | The early recovery cluster will coordinate: - Debris removal – in public places and fallen trees and housing timber production; - Cash for work; Repairing community infrastructure; - Support to local govt on DRR; - Rule of law; - Restoration of life lines (comms, electricity, services) |
|  | Recognise that many may rebuild without financial support. We should advocate for technical guidelines and monitoring to help them build back better rather than rebuild the same vulnerabilities they originally had. |
|  | Support to recovery starts now. We need to support those who have no shelter and people getting back into their houses and enabling them to stay in their own properties urgently, with emergency shelter and repair kits. |
| Education | Support to evacuation centres and shelter support that will allow returns will vacate school |
|  | We must advocate that public buildings which could act as evacuation centres in the future are built back better to ensure they don’t collapse again in future probable events. As was the case in Cateel, Boston and Baganga. |
|  | Child and mother friendly spaces. |
| CCCM | Site planning - see guidelines for tents |
|  | Site planning - see guidelines for settlement planning |
|  | Guidelines for planning of bunk houses – include and prioritise WASH and Protection |
|  | Camps and tents are NOT an ideal option and should only be a last resort. Camps and bunkhouses must be adequately planned and supported with services. |
| Health | Health issues which arise from living within makeshift shelters with tapeline/plastic sheeting and tests and evacuation centres. |
|  | Health issues arriving from living in camp environments for extended periods of time. |
| WASH | See Annex X for input from WASH cluster |
|  | Ensure WASH activities are included in the development of shelter interventions – including bunkhouses and relocation sites. |
|  | Ensure community participation in identifying water and sanitation practices and future needs. |
|  | Ensure appropriate levels of household sanitation are provided with all shelter solutions during the emergency and recovery phases. |
|  | Ensure appropriate levels of household water provision are provided with all shelter solutions during the emergency and recovery phases. |
|  | Ensure Hygiene Promotion forms part of any WASH related to the provision of shelter |
|  | Ensure community participation in identifying water and sanitation practices and future needs |

Annex X

UN Guiding Principles on Internal Displacement

The provision of temporary housing is to be guided by relevant international standards particularly the UN Guiding Principles on Internal Displacement.  These principles are integrated into these suggestions and are summarised below.  It is the responsibility of the aid community to support Government in meeting its obligations to the affected population.  Further information is available from the UN, including practical steps to assist with implementation.

1. Relocation should be voluntary: Displaced persons should not be coerced to move and force should never be used.  Every internally displaced person has the right to liberty and freedom to choose his or her place of residence.

2. Access to information and participation: Displaced persons must be provided with full, free and impartial information regarding all plans for relocation and resettlement.  Authorities should ensure the full participation of displaced persons in the planning and management of any return, resettlement or relocation process.

3. Access to humanitarian assistance and basic services: All displaced persons must have full, free and unimpeded access to humanitarian assistance.  This includes: essential food and drinking water; basic shelter and housing; appropriate clothing; and essential medical services and sanitation.  The relocation, resettlement or return of displaced persons should not interfere with their access to these basic rights.

4. Access to education: All displaced children should receive access to free education.  Education should respect their cultural identity, language and religion.  Education and training facilities should be made available to internally displaced persons, in particular adolescents and women, as soon as conditions permit.

5. Access to livelihoods: Internally displaced persons have the right to seek freely opportunities for employment and to participate in economic activities.

6. Family unity must be respected: The fundamental principle of family unity must be upheld at all times.  Every effort should be taken to ensure that families stay together during the relocation, resettlement or return of displaced persons. Special attention should be paid to care arrangements for unaccompanied or separated children to ensure that they are relocated with existing care givers in the community.

7. Protect women, children and groups with special needs: Special attention should be paid to the protection needs of unaccompanied and separated children, women-headed households, single parent households, the elderly and disabled during return, relocation or resettlement.

8. Right to documentation: The local authorities should ensure that displaced persons have access to all the necessary documentation for the full enjoyment of their legal rights, these include personal identification documents, birth certificates, marriage certificates, proof of land tenure and land and property ownership documentation.  The authorities should facilitate the issuance of new documents or the replacement of documents lost in the course of displacement.  Women and men should have equal rights to documentation and the right for documentation to be issued in their own names.

9. Protect the civilian character of all camps: The civilian, non-political, humanitarian nature of camps should be protected at all times.  Humanitarian assistance should be provided in accordance with the principles of humanity and impartiality and without discrimination on the grounds of race, religion, ethnicity, or political affiliation.  Humanitarian assistance to internally displaced persons should not be diverted, in particular for political or military reasons.

10. Avoid multiple relocations : Wherever possible the local authorities should avoid moving people multiple times.  Ideally, families should be moved only once to the same land where permanent shelters will be eventually be constructed, or to land in the same vicinity as future permanent settlements.

11. Respect cultural and conflict sensitivity: All relocation plans should be sensitive to the ethnic, religious, cultural and political composition of the displaced population.  Every effort should be taken to ensure that the needs of earthquake displaced populations and conflict displaced populations are dealt with in a fair and egalitarian way, without discrimination.

12. Provide assistance to host families: Humanitarian relief assistance should be provided to families hosting displaced people.

Annex X

| Typhoon Pablo Shelter Cluster LOGFRAME |  |  |  |
| --- | --- | --- | --- |
| OBJECTIVES | INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| Goal : To support the most vulnerable families affected by Typhoon Pablo to recover. | % of the population have recovered to an agreed standard. |  |  |
| Outcome 1 : The most vulnerable families affected by Typhoon Pablo have received adequate emergency shelter support. | % of the population have received emergency shelter to an agreed standard. |  |  |
| Output 1.1 : Support to evacuation centres |  |  |  |
| Output 1.2 Support to camps |  |  |  |
| Output 1.3 Emergency shelter |  |  |  |
| Output 1.4 Bunkhouses and transitional shelter |  |  |  |
| Activities Activities may often be included in separate document (activity schedule) for practical purposes | Inputs/resources | Costs & sources |  |
| Outcome 2 The most vulnerable families affected by Typhoon Pablo have recovered their homes. | % of the population have received repairs or permanent shelter to an agreed standard. |  |  |
| Output 2.1 Partial repair kits |  |  |  |
| Output 2.2 Significant repair kits |  |  |  |
| Output 2.3 Permanent housing on original land plot |  |  |  |
| Output 2.4 Permanent housing on relocation plot |  |  |  |
| Activities | Inputs/resources | Costs & sources |  |

Annex X

Inter cluster coordination

| Cluster structures, lead agencies and co-leads |  |  |
| --- | --- | --- |
| Cluster | Lead Agency | Co Lead |
| Food |  | WFP |
| Sub cluster NFI |  | IOM |
| Nutrition | DOH |  |
| Early Recovery |  | UNDP |
| Camp coordination/management | DSWD | IOM |
| Education |  | UNICEF |
| Shelter | DSWD | IFRC/IOM – emergency |
|  |  | Xxxx - recovery |
| WASH | DOH | UNICEF |
| Health | DOH | WHO |
| Logistics | OCD | WFP |
| Protection | DSWD | UNHCR/UNFPA |

| Shelter cluster configuration |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activities |  |  |  |  |
| Responsible | IFRC | IFRC | IOM |  |
| Location | National – Manila based | Regions XI and Caraga – Davao based | Hubs Trento Naburanturan, Cateel |  |
| Cluster coordination | All regions | XI and Caraga Regions | Hubs - |  |
|  | Manila based meetings | Davao based meetings | Hub based meetings |  |
|  | Manila based advocacy | Davao based advocacy | From Davao |  |
|  |  | Davao based IM | Hub based IM |  |
|  |  | Davao based Tech Coord | From Davao |  |

The following operational Agencies will take a lead in coordination at Municipality and Baganga level. Each Agency will take a lead for covering a series of Baganga’s in each Municipality. Each Agency will report to the Hub level cluster on assessments, gaps, ongoing/planned activities and constraints.

| Municipality Coordination |  |  |
| --- | --- | --- |
| Region | Municipality | Lead Agencies |
| Caraga Region | Agusan del Sur | - IOM (Hub level cluster coordinator) - Save the Children, - World Vision, |
| Region XI | Surigao del Sur | - IOM (Hub level cluster coordinator) |
|  | Compesella Valley | - IOM (Hub level cluster coordinator) - UNDP, - Plan International, - Catholic Relief Services, - Lutheran World Relief Services, - AADC w/ Care Int’ls, - Oxfam, - CCODP, - Save the Children |
|  | Davao Oriental | - IOM (Hub level cluster coordinator) - UNDP, - Plan International, - Catholic Relief Services - Lutheran World Relief Services, - ShelterBox |
| Others to be confirmed |  | HRC/Oxfam Habitat for Humanity |

Annex X

The commitments to WASH – source WASH Cluster

WATER, SANITATION AND HYGIENE (WASH) CLUSTER

Guidelines for selecting Evacuation Centers

16 Aug 2012

BACKGROUND

Water, sanitation and hygiene standards are key considerations for survival, health, dignity and well-being of Internally Displaced Persons (IDPs) in Evacuation Centers (ECs).

OBJECTIVE

The objective of this guideline is to ensure that evacuation sites are selected for IDPS (especially the needs of women, children and  disabilities) with due consideration for access to clean water, basic sanitation facilities, living in a hygienic environment and the ability to practice safe hygiene behavior.

WATER AND SANITATION PLANNING PERSONNEL

It is highly recommended that DOH sanitary inspectors and MMWS are involved in the process of selection of Evacuation Centers to ensure that water and sanitation inputs are included in the selection process, as per the guidelines below.

BASIC WASH GUIDELINES

The following basic guidelines are a checklist of for water, sanitation and hygiene requirements in site selection for evacuation centers:

Water

It is recommended that evacuation centers are selected that have:

- A safe, reliable and sufficient water supply for all water needs such as drinking, bathing, washing etc.  Ideally piped water supply or other protected source such as groundwater extraction using handpumps or protected wells (Min standard is 15 liters/per/day for all water needs, 5 liters/person/day for drinking).

- Been water quality tested with assistance of DOH/LGU sanitary inspectors or other qualified personnel and water treatment options and recommendations are considered based on the water quality analysis ( ie. Use of Jerry cans and the use of hyposol).

- Local of water facilities should be easy to access by the IDPs staying in the ECs

- Water source and facilities to be used at the ECs are safe/protected from possible contaminants and/or recommendation should be provided for protection of water sources/facilities

- Access to facilities by Person with Disabilities (PWD) and children should be considered

- If water supply quality cannot be guaranteed then other treatment options should be institutionalized in the camp.

Sanitation

It is recommended that evacuation centers are selected that have:

- Existing sanitation facilities, gender segregated, and hand washing facilities (Min standard is 50 IDPs per toilet).  Sufficient space needs to be dedicated for installation of toilets and hand-washing facilities to meet this ratio.  Sanitation sites should be selected by Government Sanitary Inspectors or dedicated NGO WASH engineers considering protection issues and ease of access.

- Sufficient space allotted for sanitation facilities in any planned temporary learning spaces and health facilities that may be planned for the site.

- Existing bathing facilities, preferably gender segregated.  Sufficient space needs to be dedicated for installation of gender segregated bathing facilities

- Existing solid waste bins and a temporary waste disposal collection area.  Sufficient space needs to be dedicated for installation of a temporary waste disposal collection area

- Access for liquid and solid waste collection, usually by heavy vehicles

- Assess to facilities by People With Disabilities (PWD) and children should be considered.

Drainage

It is recommended that evacuation centers are selected that:

- Drain well (eg not built in a depression) and do not have pooling water that will attract vectors such as mosquitoes.

- Are not prone to flooding and are not positioned on major drainage paths

Annex X

The commitments to older persons – source HelpAge

The UN Principles for Older Persons (UN General Assembly resolution 46/91) calls for ensuring the independence, participation, care, self-fulfilment and dignity of older people. It specifically states that older people should have access to basic services including shelter.

The background

Shelter is a basic human right for people of all ages, but for older people, the sense of security and comfort that a home provides is particularly important. Losing their home in a disaster or conflict therefore has a profound psychological impact, particularly on the “oldest old” (people above 80 years). Suitable housing for older people is crucial to ensure a dignified life. When managing a shelter programme, it is essential to identify and address the needs of vulnerable older people and

engage them in decision-making, in order for age-appropriate decisions to be taken.

Key action points to address

• Sensitise and provide training to your team on the importance of collecting data on older people, disaggregated by sex and age.

• Make your assessment tools age-friendly by including questions on the needs and capacities of older people.

• Conduct focus group discussions and individual interviews with both older men and women in various age groups.

• Ensure that your assessments include the most vulnerable older people – isolated older people, those with health problems, those aged 80 and above and skipped generation households

(where the middle generation is absent). See Action point 3.

• Identify what already works around accessibility, inclusion and participation of older people and what needs improving.

• Adapt your communication style to suit older people.

• Provide opportunities for older people to hold positions of responsibility and be represented on community-based committees.

• Increase opportunities for individual choice and problem solving by involving older people and their families and communities in issues such as land rights and construction.

• Ensure that older people are engaged in complaints mechanisms and project monitoring procedures.

• Target older people, especially the most vulnerable, in the process of selecting those to receive shelter assistance and in all stages of a humanitarian response.

• Ensure that isolated or housebound older people are aware of the selection process and are able to participate in it.

• Assess, through discussion with older people and their families and community, the support systems that are available to them and how these have been affected by the emergency.

• Take steps to ensure that the community acknowledges the risks and vulnerabilities of older members and that the community is supported to address these.

• Adhere to national and international standards for durable and accessible shelter construction.

• Ensure a culturally acceptable and age-friendly layout and design.

• Incorporate features that allow older people to enter and exit their shelters easily.

• Ensure that the shelter is not too far from water sources, healthcare centres, cyclone shelters or community centres and other facilities; that older people do not feel isolated or unsafe; and that they can evacuate their shelter easily.

• Ensure that non-slip floors and handrails are installed as appropriate; and that shelters are weather-proofed and winterisation kits distributed in good time.

• Recognise that people become less mobile with age: provide access to water sources and raised beds, adequate lighting and ventilation; and opportunities to adapt the shelter to meet future needs, including home-based livelihood activities.

• Ensure that older people’s issues and data are included on the agenda of shelter cluster meetings.

• Put in place a system of monitoring and evaluation among partners and local government, so that there is a continuous flow of feedback and direction on ageing issues, and disseminate good practice and lessons learned through relevant channels, including the shelter cluster.

• Coordinate and promote partnership with other clusters (Watsan, Health, Livelihood, Protection, Camp Coordination and Camp Management) to link older people to different services.

• Link your programmes to those addressing other vulnerable groups such as children, women and people with disabilities. There are overlaps between these groups – for example, many older people care for children or have disabilities.

Action point 1: Understand the needs and capacities of older people

Action point 2: Ensure that older people participate and are represented

Action point 3: Target vulnerable older people

Action point 4: Incorporate age-friendly features in both household and community shelters

Action point 5: Promote coordination, cooperation and sharing

Annex X

The commitments to Protection – source UNFPA

Annex X

The commitments to Disability – source Handicap International

Relevant documents listed below can be found on our website www.handicapinternational.ph

Disability

- Definitions of Persons with Specific Needs

- Disability Screening Tool

- Tips for Building Relationship with PWD

- Protection - Issues for People with Disabilities and Injuries

Disability and Emergency

- Tool for rapid handicap assessment

- Including Disability Issues in Disaster Management

- Disability Checklist for Emergency Response

- Post Disaster Disability Screening Form

- Guidelines for the Distribution of Specific Needs Items

- Guidelines for Accessibility in Emergencies

- Designing WASH to improve accessibility

- Water and Sanitation for Disabled People and other Vulnerable Groups

- Adapting Shelter Design for Improved Accessibility

- Guidelines for Creating Barrier-Free Emergency Shelters

- Including Children with Disabilities in Child-Friendly Spaces (Eng)

- Including Children with Disabilities in Child-Friendly Spaces (Tagalog)

- Livelihoods - Facilitating Early Recovery for Injured and Disabled People

- Disasters, disability and rehabilitation (WHO)