SHELTER CLUSTER MEETING

MONDAY 20 DECEMBER, 9:00 AM, 2012

DSWD FO XI SEMINAR HALL, DAVAO CITY, PHILIPPINES

MINUTES OF THE 4TH MEETING

Meeting Started:  9:05 AM

Meeting Ended:    11:25 AM

- Introductions

  - Chaired by DSWD:
Maria  Elena S. Labrador (maelenaslabrador@yahoo.com, 0927540983)

Co facilitated by IFRC and IOM:
Patrick Elliott (patrick.elliott@ifrc.org 09186879073)

List of Attendees:

| Name | Organization | Position/Function |
| --- | --- | --- |
| - Patrick Elliott | IFRC | ESC |
| - Ma. Elena S. Labrador | DSWD FO XI | Shelter Cluster Chair |
| - Neil Bauman | IFRC | IM |
| - Eva Maria C. Lausin | COSE | Proj Coord. |
| - Teerapong Laptwan | HELPAGE | RDO |
| - Marcus Soawyer | Access Aid Intl | Coordinator |
| - Rey Leones | Shelter Box | Coordinator |
| - Nick Ledonx | Samaritan’s Purse | Team Lead |
| - Kenneth james | Samaritan’s Purse | Programs |
| - Michael Gloekle | IFRC | Coord. |
| - John Vinson Gokeelao | IFRC | IM |
| - Seki Hirano | CRS | TA Shelter |
| - Wan Sophonpanich | Save the Children | Shelter Adviser |
| - Leny lakaria | ASEAN |  |
| - Brian Kelly | IOM | Regl Adviser |
| - Kasper Engborg | UNOCHA | H.O.S.O |
| - Joe Tabago | UNOCHA | Humanitarian Affairs Analysts |
| - Ma. Ena Olmedo | IOM | HSO-Cotabato |
| - Phyo Wai Kyaw | IFRC | Info Manager |
| - Eric Lazarte | Plan Intl | Program Advisor |
| - Sujata Tuladnar | UNFPA | Human Coordinator |
| - Jen Hiloma | ILO | NPO |
| - Catherine Goroo | Lutheran World Relief |  |
| - Moises F. Musia | ADRA-Phils | E.R Coord |
| - Gemma Asis | UNOCHA | IMA |
| - Lorelie T. Jayma | DSWD XI | DSWD-KC - Secretariat Shelter Cluster |
| - June Sanchez | DSWD XI | DSWD Secretariat – shelter cluster |

AGENDA

- Acceptance of last meeting minutes

- Message from Humanitarian Coordinator

- Review of latest data from DSWD and WWW

- Updates from agencies including plans, assessment, information

- Update on resource mobilization

- Coordination/hub structures

  - Cluster decentralization

  - Agency coordination at municipality and baganga level

- Strategic documents

  - Shelter cluster operational framework

  - Shelter cluster guidelines and standards

- Report back on:

  - TWIGs

  - SAG

- Any other business

INTRODUCTION OF NEW MEMBERS OF THE SHELTER CLUSTER

ACCEPTANCE OF THE PREVIOUS MINUTES

ADD IN THE AGENDA:

THIS SHELTER CLUSTER FOCUSES ON REGION XI ONLY PER ADVICE FROM ASEC CABRERA.

| AGENDA | DISCUSSIONS | CONCERNS RAISED |
| --- | --- | --- |
| Review of latest data from DSWD and WWW | - Using mainly DSWD data. It was observed that in Com Val there is minimal intervention since there are more houses damaged than in Davao Oriental. - UNOCHA said the agencies concern to scrutinize these data because the Numbers in the data sets are too simplistic - Neil Bauman presented a template for data reporting. Every member is encouraged to comply and submit to OCHA for unification - The template is just guideline. Whatever data sets each agency has, kindly submit the same to OCHA. It will be processed accordingly. - If we could fill up our data sheets to keep us abreast of our respective updates. - as to TARPS dispatched 20,000-DSWD 17,800-USAID 400+-IFRC - DSWD have records of receipts and dispatched items starting Dec. 4 only. | - Regarding the data distributed, need to know where these 55,503 houses damage in ComVal is concentrated to be able to address the need for temporary shelter. - Stocks from USAID, to know where they were distributed. - There might be a need for Shelter cluster operation is closer to the sites. - Deadline is on Friday 21 Dec, 2012 for the database. - It is also good to have coordination with the Wash cluster to match what we are having with the shelter cluster - OCHA for inter-cluster coordination as there are OCHA reps in all cluster, to situate the cluster as to what others have been doing. |
| Updates from agencies including plans, assessment, information | DSWD: - As to international donations, per advice of Sec. Soliman, these are exempted from tax. But need to consign goods to DSWD to name the same to Director Priscilla Razon then slash the donor’s name. Ex. Director Priscilla Razon/donor’s name or NGO’s name - DSWD allows the said NGOs to pack their items themselves but they should coordinate with the LGUs. - Is currently distributing 178,000 Noche Buena packs until Dec 24. - Currently setting up 83 bunkhouses. 23 in ComVal. 2 constructed by KC-DSWD in Compostela. 21 will be constructed by the Province, with whom the money was disbursed because they requested for it; to set up 20 bunkhouses each on Cateel, Boston & Baganga, totaling to 60 for Davao Oriental. First wave: 5 in Baganga; 8 in Cateel; 8 in Boston. - Construction under DSWD-Kalahi is under contract, but utilizing labour from the community. - DSWD contracted the bunkhouses due to the urgency. CRS: - Sense of recovery is very strong. If there is continued support, they can recover fast. - Presented a shelter & settlement response strategy. - Sent out tents 1882 units. It was handed to NDRRC. SHELTER BOX - Has distributed shelter kits. And was coursed thru the LGUs. I.L.O - They do cash for work... doing some shelter support also | - Need to maximize labour in the community - To plot for each municipality a template as presented by CRS and get a focal person to get this done in the local level. - To maximize labor in the community - The operational framework of Shelter Cluster can be discussed again together with the template designed by CRS. - CRS needs warehouse in Cateel. But prefers not to work with the military. |
| Coordination/hub structures - Cluster decentralization - Agency coordination at municipality and Baganga level | - 2 Logistics camps in Trento & Nabunturan are fully functional now. - For Coordination Hub in Nabunturan & Cateel are being put on hold at the moment due to another typhoon warning on the same path of that of Pablo |  |
| Update on resource mobilization | - Need to hear from Logistics Cluster which will meet this afternoon. |  |
| Strategic documents - Shelter cluster operational framework - Shelter cluster guidelines and standards | - Patrick Elliott posted draft documents at the www.sheltercluster.org. Everyone accepted without further discussion. | - Need to incorporate guidelines set by UNFPA used during Sendong. |
| Other Matters | - On Site identification DSWD will be the lead agency and to call Mines & Geo-science Bureau for the Hazard Map. |  |
|  | - On schedules during Christmas Season | - UNOCHA suggested next next 2 weeks meeting will be Mon & Thurs. Will resume to original scheds by January 2013. |
|  | - On Patrick & Neil leaving the Shelter Cluster | - They will be replaced byMichael Gloeckle |