# Meeting minutes

# Roxas – Panay - Shelter cluster meeting

Location: Roxas -Panay

Date: Wed 14th November 2013.

Chair: Roxas Province government office

Present:

- Philippines Red Cross / German red cross

- IOM

- Co-chair: Save The Children, Julien Mulliez, Save the Children

Shelter actors active in the area but not represented :

- World Vision

# Govt Updates - DSWD and Provincial

Updates:

Actions:

# Cluster agency assessment, response updates and challenges

Updates

- Trying to put a working group in place early on, before it gets hectic with loads of actors.

- Expecting many shelter actors to arrive in coming days so let’s get coordination right from the start. Agencies to inform group on their geographical targeting early on to avoid duplication.

- Agencies will try to follow Shelter cluster recommendation for kits specifications, including the principle of 1 tarp per household up to 5 people, 2 tarps above

- Recommended to coordinate with WASH kits to try to make sure each family gets a complete kit. ACF does WASH kits – could be nicely complementary

- IOM intending to focus on evacuation centers. Other actors encouraged to report to IOM information on location and numbers of people in evacuation centres they come across

- Suggestion from IOM for better integration into existing welfare system : ask Barangay chiefs if they have DSWD card system, if so we will record our distribution into the DSWD card.

Actions:

# Who, what, where and when

Updates:

Actions:

# Inter cluster updates – WASH, ER, CCCM

# Updates:

# Actions:

# Strategies – Emergency and Early Recovery .

# Updates:

# Actions:

# Technical standards

# Updates:

# Actions:

# TWIGS

# Updates:

# Actions:

# Any other business

Updates:

Actions:

Next meeting