# Meeting minutes

# Ormoc City – Leyte - Shelter cluster meeting

Location: Cebu City - Cebu

Date: Monday 18th November 2013.

Chair: CRS

Present:

| Care | IRD |
| --- | --- |
| Concern Worldwide (CW) | Islamic Relief (IR) |
| Cordaid | Medair |
| Dompet Dhufa Indonesia | Muslim Aid |
| DSWD | People in Need (PIN) |
| Habitat for Humanity | RAFI (Ramon Abolitz Foundation Inc |
| Handicap International | SDC (Swiss development cooperation) |
| Helpage International (HAI) | Shelterbox |
| IFRC – PNRC | Sign of Hope (SOH) |
| Intersos (IS) | Swiss Red Cross (SRC) |
|  | Worldvision Internatonal (WVI) |

Chair: Grace Q Subong: Shelter Cluster Coordinator

Stand in Co-chair: Jan-Willem Wegdam  Cordaid Shelter Adviser

# Govt Updates - DSWD and Provincial

- DSWD Shelter cluster coordinator thanked everyone for his or her presence and pointed out the importance of coordination. She explained that the government of Philippines leads the cluster coordination of the response.

- DSWD provides technical assistance to the provincial disaster management.

- On Tuesday 19th November there is a provincial shelter meeting. The shelter cluster coordinator will represent the organizations in the shelter cluster but this meeting is open for all agencies. Location = Provincial Capital, 14.00 pm Cebu.

- DSWD has collects damage and response data through their DROMIC (Disaster system. A network of DSWD staff on barangay level that collects systemized data and sends them to a Information Management unit in Manila that produces detailed reports. This is the link to Yolanda: http://disaster.dswd.gov.ph/reports-and-updates/typhoon_yolanda/ - wpfb-cat-18

- Coordination

- The meeting agreed with the proposal to continue organizing Shelter Cluster meetings in Cebu while this will become the hub in the affected area where many organizations will have their main office. Frequency of the meetings is initially 1x week, most like to be reduced to 1 x 2 weeks next month.

- Since the affected area’s is widespread there is a challenge for the coordination on barangay level. This is something the cluster can think of.

- The coordination of the activities on barangay level is also very pressing for the local government. The provincial government can consider providing additional resources for staffing.

# Cluster agency assessment, response updates and challenges

# The Cebu Cluster meeting will focus on the shelter / NFI response in Cebu island and surrounding (smaller) islands

# WVI mentioned that the mayor of DaanBantayan looks for an organization that can supporting him with the repair of a damaged roof of a warehouse: Mayor Augusto Corro can be reached on: 0917-8121090 or 0998-9792990

# There is a risk that there will be congestion between Bantayan island and the surrounding smaller islands because of the increased need for transportation and limited capacity of the relatively small boats.

# Discussion after the meeting revealed that there is a risk for inflation of materials in the affected area’s. This is already the case for fuel in Leyte. The government is invited to consider regulations.

# DSWD information of the 14 priority area’s, based on nr of displaced (transient) families

|  | # LGU | # Nr of displaced familes |  | # LGU | # Nr of displaced familes |
| --- | --- | --- | --- | --- | --- |
| # 1 | # Bantayan | # 17,329 | # 8 | # Borbon | # 5,158 |
| # 2 | # Daanbantayan | # 14,000 | # 9 | # Tabuelan | # 4,955 |
| # 3 | # Medellin | # 10,445 | # 10 | # Sogod | # 2,854 |
| # 4 | # Madridejos | # 9,545 | # 11 | # Pilar | # 2,580 |
| # 5 | # San Remegio | # 7,141 | # 12 | # Tabogon | # 2,078 |
| # 6 | # Santa Fe | # 6,226 | # 13 | # Poro | # 1,800 |
| # 7 | # San Francisco | # 5,494 | # 14 | # Tudela | # 1,771 |

# Who, what, where and when

- Due to the relative large number of participants only short introductions were given, the following table is an indicative summary (not complete!!) of the information shared

|  | Nr org’s assessment | Nr orgs planning / emergency shelter distributions | Remarks |
| --- | --- | --- | --- |
| North Cebu | 5 | 7 (PNRC, HfH, IR, IS, SDC, RAFI, WVI, SOH, | Chainsaw (HAI) Shelter repair kits with timber, CGI, nails (HfH) |
| Daanbantayan | 3 | 3 (PNRC, HfH, RAFI, |  |
| Bantayan | 5 | 7 (PNRC, HfH, SRC. PIN, RAFI, WVI | Chainsaw (HAI) |
| Batbatan | 2 | 2 PNRC, HfH |  |
| San Francisco island | 2 | 2 PNRC, HfH |  |
| Poro Island | 2 | 2 PNRC, HfH |  |
| Not specified or recorded |  |  | Cash for work (IRD) |

- PNRC and Habitat for Humanity assessed all affected area’s.

- RAFI has developed an excel database with a 3w of relief distributions in Cebu, containing data on barangay, organization, type of assistance, date, costs and contact person level. Mainly local organizations reported. Most registered distributions are related to Food. The information can be combined with the shelter cluster 3W. The information collections of RAFI and SC should be coordinated.

# Inter cluster updates – WASH, ER, CCCM

# Updates:

# Actions:

# Strategies – Emergency and Early Recovery .

# Updates:

# Actions:

# Technical standards

# Updates:

# Actions:

# TWIGS

# Updates: The agencies agreed to the idea to organize a TWIG to define the (early)recovery shelter strategy. This meeting will be organized and chaired by Red Cross Movement: The following agencies indicated to be present: CW, PIN, HfH, IR, Medair, RC, HI)

# Actions:  RC organize meeting

# Any other business

Updates:

Actions:

Next meeting

Monday, 9.00 AM

DSWD Office , MJ Cuenco Avenue corner Gen. Maxilom Ave., Cebu City