## Slide 1: Shelter Cluster Donors and Heads of Agencies Strategic Meeting 17:00, Nov 21st, 2013

## Slide 2: Outline of contents
Coordination arrangements for shelter
Introduce Shelter strategy
Funding levels low for the scale of emergency
-why?
-what capacity do we as a sector have to scale up?

## Slide 3: Current Appeal
46 million of which 14 million funded (30%)
Scale has increased to 1.1 million houses appeal figures will increase

## Slide 4: Shifting priorities
Time
Priority
Food and water
Shelter relief
Shelter recovery
4,200

## Slide 5: Impact on population
Houses destroyed about 520,000
Houses damaged about 500,000.
Displaced population - 4.4 million.
-
Evolving situation figures need to revised continuously

## Slide 6: Response Strategy and Progress
Emergency Distribution
4000 shelter kits delivered
300,000 in the pipeline – subject to funding
Emergency Self recovery Support
88,500 in the pipeline
Core, Transitional shelter and rental support
20,000 in the pipeline
Support to collective centres – no information
Support permanent Housing and tenure security

## Slide 8: Key factors to take into account
Prioritisation = Poverty index + number affected + severity of damage (typhoon or typhoon and surge wave)
Logistics
Capacity of markets to meet the demand
Capacity of local government and civil society
Land policy – relocations, tenure security

## Slide 9: Current strategic gap capacity analysis
Repair - reconstruction for 1.1 million houses
Shelter cluster capacity to address the shelter needs of 400,000 hhs
Civil society, self recovery
International community
Government
Scale of funding
Scale of implementation capacity

## Slide 10: Supply pipeline gap analysis
28,000 CGI sheets/week in affected area
National supply of CGI and other materials being investigated
We predict a massive shortfall particularly in roofing and framing materials

## Slide 11: Urgent Shelter Needs
Item | Urgent assistance requested from Donor
Roofing materials 26 gauge CGI sheets (10 sheets per hh) Local procurement international procurement | International procurement of CGI and fixings 3 million sheets
Framing materials Timber Coco lumber Steel | Local Salvage of Coco lumber – mobilising capacity for industrial scale processing TWIG on cocolumber

## Slide 12: Other supply chain considerations
Debris removal: Making available safe areas for reconstruction
Build back safer: Skilled, trained labour
Relocations: minimising multiple relocations, services and ensuring tenure security