Meeting Agenda

Western Visayas - Shelter cluster meeting

Location: Roxas - Panay

Date: Sunday 24 November 2013.

Chair: Capiz Regional DSWD

Co-chair: Shelter Cluster, Timothy Stats (IFRC)

Partners:

| Department of Social Welfare & Development | Ann Masculino |
| --- | --- |
| Department of Social Welfare & Development | Glenn Genovate |
| Department of Social Welfare & Development | Rose Senagustine |
| Department of Social Welfare & Development | Josie G Cambel |
| ADRA | Frank Brenda |
| ADRA Philippines | Moises Musico |
|  | Bhattimani Singh |
| Shelter Cluster | Timothy Stats |
| Shelter Cluster | Wan |
| HEKS | Khalid Grein |
| IFRC | Iranteu Serra |
| WeltHungerHilfe (WHH) | Markus Fiesiger |
| World Vision |  |
| Cluster Partners not present: |  |
| Philippines Rural Reconstruction Movement |  |
| Canadian Forces DART Engineer |  |
| Philippines Red Cross - Capiz Chapter |  |
| Solidar Suisse |  |
| PRRH-WHH |  |
| Emergency Architects |  |
| GOAL |  |
| Handicap International |  |
| ACTED |  |
| DORCAS |  |
| DFAID (ex-CIDA) |  |
| Humanity First Canada |  |
| PRRM-WHH |  |
| IRC |  |

## Joint Chamber of Commerce (Capiz)

- Introduction to cluster, offering assistance where possible.

- Will share consolidate list of suppliers to local markets via email.

Shelter Cluster: collect and share date provided to all.

## DSWD ASSESSMENT UPDATES:

- Have prioritised 50 municipalities for a second round of assistance (first round: family pack, second round: family pack)

- Criteria is weighted equally, 50% on poverty level, 50% on number of partially and totally destroyed houses. Some re-validation is required.

- Will include an additional column for provinces

- Poverty information can be found on

DSWD: To provide updated digital copy to Tim for circulation

## CCCM UPDATES - DSWD (Judith) / IOM LEAD:

- Oil spill update: 218 HH evacuated in Nipse, 38 in tents, 180 in school buildings and as of tonight, 95 HH still without shelter.

- MSF said they had 500 tents coming in starting today, however, these have not arrived so far.

- Some people have returned to the island and follow up for shelter needs will have to be carried out. These families were previously in EC.

- DART team had carried out an assessment for potential of setting up more tents there (to be verified)

- WASH is a key concern – lacking latrines – UNICEF to install,

- Pits dug by Canadian Forces – being rejected by principles?

- Electricity – from mayor? Wiring put into place yesterday, but still not working. More generators needed?

- Tomorrow meeting with LGU – Estancia, 9am.

## PARTNER ASSESSMENTS:

- Members can share assessments carried out

- ADRA: went to Calais – announced commitment for shelter kit and assess potential for further procurement. Shortage of standard CGI sheet in Roxas, but other materials are still avail.

- Chainsaw – 6 coming from DfID, ADRA taking 2, 4 available to be requested through the cluster

- WV carrying out market assessment in Panay and will share to cluster once completed.

- GAA: wholesaler for shelter goods in Iloilo.

- REACH assessment: introduction of, questionnaire feedback in next 24hr.

PARTNERS: provide feedback on Reach questionnaire over next 24 hrs.

## PLANNED RESPONSE, Need and Gaps:

- 3W updated, will send out again

- ACTED(?): Municipality prioritised in Aklan can potentially be assessed and covered by them.

- Need: call out for more tents

- OCHA: asks for different location in Panay – can agencies respond?

- OCHA has asked for some quick impact projects, generators, fuel, fix roof at hospital and fix a back hoe

- GAP: uneven spread of partners. No one in Antique or Negros Occidental

PARTNERS: Confirm details when possible, either email or pen updates/corrections directly onto hardcopy 3W hanging at the stage

## RESOURCE MOBILISATION

- Canadian Armed Forces may be able to fly stocks directly from Manila or Cebu or British Navy offers to ship stocks from Cebu to Roxas.

- DFID aircraft flying from Jakarta to Cebu -  which if booked, will have up to 40 Metric Tonnes spare capacity, willing to transport goods on behalf of NGO’s.

- New Zealand Air Force (C130) can support with transport of cargo from Cebu and MNL.

PARTNERS: Requests for access to come through the shelter cluster

## COORDINATION WITH other clusters:

- School repair: agencies interested in working with to inform SC, meeting to be set up with Ed Cluster and DepED.

## Inter cluster

- Next intra-cluster meeting tomorrow.

- CASH working group? Many agencies looking at it. ILO in Roxas now, will work in the area for few years

## SELCTION CRITERIA - Should agencies look at LGU’s level AOR, or municipality?

- Reporting at barangay level – at least 1 agency/barangay

- Governor says pick poorest of the poor.

- Protection cluster: vulnerability criteria – Many agencies looking at remittance information? Poverty incidents?  (on top of general vulnerable criteria).

PARTNERS: to share different selection criteria, Shelter Cluster will gather and make available.

Cluster meeting moving to Mon – Wed – Fri after general coordination meeting. Next meeting Wednesday 27th Nov.