Status

| Strategy Status | Version | Status | Effective date | Next revision |
| --- | --- | --- | --- | --- |
|  | 2.2 | DRAFT Under review | 15 December | <date> |

Shelter Cluster Structure

| Response name | Typhoon Yolanda, 2013 |
| --- | --- |
| Cluster Lead Agency | DSWD |
| Government Lead agency and contact | Agency: Department of Social Welfare and Development (DSWD) Name: Assistant secretary Camilo G. Gudmalin Email: cgudmalin@dswd.gov.ph, Mobile: 09209485383 |
| Cluster Coordinator Contact | Name: Victoria Stodart Agency: International Federation of the Red Cross and Red Crescent Societies (IFRC) Email: coord.phil@sheltercluster.org, Mobile: 09084011218 |
| Global Focal Point Contact | Name: Anna Pont Agency: International Federation of the Red Cross and Red Crescent Societies (IFRC) Email: anna.pont@ifrc.org, Mobile: +41793039919 |
| Hubs/Sub-hubs | Hubs: Tacloban (IFRC), Roxas (IFRC), Cebu (IFRC) Sub-hubs: Ormoc (IOM), Guiuan (IOM) |
| Strategic Advisory Group (SAG) Members | Chair DSWD Assistant Secretary Gudmalin, NHA, IFRC, IOM, CRS, HFHI, UN-HABITAT, Housing and Urban Development Coordinating Council (HUDCC), Dept of Interior and Local government (DILG) Gawad Kalinga (GK) |
| Endorsing Cluster partner Members | Active agencies in the cluster. |
| Relevant Technical Working Groups (TWiGs) |  |
|  | 1. Housing, Land and Property: co-chaired with the protection cluster. No build zones, bunkhouses, relocations, informal settlements 2. Reconstruction and Recovery: chairs UN-HABITAT and DSWD Ass Sec Gudmalin: How to operationalize reconstruction process, housing/shelter policy, salvaging, material supply, guidance, training on DRR 3. Technical: Standards, Specification and Guidance – including supporting self-recovery and transitional shelter |

Situation Analysis

| Situation | On the morning of 8 November, category 5 Typhoon Haiyan (locally known as Yolanda) made landfall in the Philippines, a densely populated country of 92 million people, devastating areas in 36 provinces. Haiyan is possibly the most powerful storm ever recorded. The typhoon first made landfall at Guiuan, Eastern Samar province, with wind speeds of 235 km/h and gusts of 275 km/h. Rain fell at rates of up to 30 mm per hour and massive storm surges up to six metres high hit Leyte and Samar islands. Many cities and towns experienced widespread destruction, with as much as 90 per cent of housing destroyed in some areas. Roads were blocked, and airports and seaports impaired. Water supply and power are cut; much of the food stocks and other goods and many health facilities were destroyed. Affected area: Regions VIII (Eastern Visayas), VI (Western Visayas) and VII (Central Visayas) were hardest hit. Regions IV-A (CALABARZON), IV-B (MIMAROPA), V(Bicol), X (Northern Mindanao), XI (Davao) and XIII (Caraga) were also affected. Tacloban City, Leyte province, with a population of over 200,000 people, was devastated, with most houses destroyed. An aerial survey revealed almost total destruction in the coastal areas of Leyte province. Affected population: An estimated 11.3 million people in nine regions—over 10 per cent of the country’s population—are affected. Over 4 million people were displaced by the typhoon with some taking refuge in evacuation centres, the rest in host communities or makeshift shelters. Thousands of people were been killed or are still missing. Housing damage: The Typhoon destroyed 520,000 houses and damaged an additional 500,000 houses. In some communities, the destruction to housing is 100%. |
| --- | --- |
| Assessment Findings | MIRA: The shelter cluster REACH team participated in the MIRA. Key findings for the shelter sector below. Most vulnerable populations: Families who have lost legal documentation of land and property title, those who have migrated, elderly, disabled, female headed households, poor families without self-coping resources. Emergency/Life saving Needs • Support to ECs, host families • Basic materials for makeshift shelter • Debris clearance and salvaged materials • Household Recovery Needs • Support for self recovery • Access to rebuilding and repair materials; tools, CGI, timber/structure • Training for safer construction • Debris clearance and salvaged materials, waste management • Transitional, core and incremental housing solutions are necessary • Government coordination structures will need support REACH : The Assessment is a household level assessment with 16 municipalities randomly sampled across 4 distance classes weighted in favour of coastal and high poverty areas, but with others represented. Assessment hubs are established in Tacloban and Roxas City. Data collection began out of Tacloban hub of 29 November and Roxas City on 3 December 2013. Preliminary data will be available on 27th December with a Final report by 31st December 2013. |
| Key Issues | - Informal settlers: what type of assistance, where will they be resettled? - No Build Zones and relocations - Shortages of recovery materials |

Shelter Operational Response Plan

| Country Strategic Response Plan (SRP) Objectives | STRATEGIC OBJECTIVE 2: Households with destroyed or damaged houses, including displaced populations, attain protective and sustainable shelter solutions; STRATEGIC OBJECTIVE 3: People whose livelihoods or employment have been lost or severely impaired regain self-sufficiency, primarily with the restoration of local economies, agriculture, and fisheries |
| --- | --- |
| Government Response | (Unconfirmed – in discussion, under review by cabinet) Government response planning is evolving and being coordinated through the various departments involved (DWSD, DPWH, and NHA). Guidance to the humanitarian response community so far is the following: CATEGORY; AFFECTED FAMILIES SITUATION; ASSISTANCE PACKAGE. I; Affected Family with own house/lot; PARTIAL DAMAGE: materials to the value of 10,000PHP TOTAL DAMAGE: materials to the value of 30,000PHP. Affected family to rebuild on site but outside of NO BUILD ZONE. II; Affected Families owning house/lot in NO BUILD ZONE; Resettlement lot with permanent row house 120,000PHP. III; Informal Settler Families with totally damaged house with no where to go; To resettlement sites with the following options: - Temporary Bunkhouse 32,000PHP - Permanent Row House - Displacement compensation (BALIK PROBINSYA) 10,000PHP. Other affected families staying in NO BUILD ZONES. * as presented by DSWD on 10th December 2013 in Tacloban |
| Cluster Objectives | Cluster objective 1: Shelter Cluster partners will provide immediate life-saving emergency shelter such as tarpaulin and tents with supporting NFI solutions for the most vulnerable typhoon affected households. Outcome-level indicators and targets - Number of households that sustained house damage from the typhoon that are currently living in safe, habitable emergency shelter (300,000 households) - % of households that are satisfied with the emergency shelter support and assistance that they received from humanitarian agencies (80%) Operational Activities: - Distribution of tarpaulins or plastic sheeting to provide roof coverage for households with damaged houses - Distribution of emergency tent solutions for households in most affected areas that have damaged houses - Training and assistance in the appropriate use of tarpaulins Coordination Activities: - Information, education, and communication (IEC) materials on appropriate, safe, building standards are provided to affected populations and implementing agencies - Monitoring to track outcomes of shelter programming including household and gender/vulnerability disaggregated satisfaction, restoration of livelihoods, access to schools, water/sanitation, family health, etc. Timeframe: November 2013 to March 2014 Key Target Vulnerable Groups: (see Key Vulnerable Groups) - Higher priority for Households with totally destroyed houses Cluster objective 2: Shelter Cluster partners will provide support for household self-recovery through incremental housing solutions using consultative, participatory processes. Outcome-level indicators and targets 2.1. Number of households that sustained house damage from the typhoon that are currently living in safe, habitable dwellings resulting from assistance from humanitarian partners (500,000 Households) 2.2. % of households that are satisfied with the recovery solutions and assistance that they received from humanitarian agencies (80%) Operational Activities: - Households are provided durable construction materials and tools to contribute to rebuilding or repair to damaged houses - Cash distributions (with monitoring) that are intended to enable households to purchase construction materials or labour that will contribute to progressive sheltering, monitoring disaggregated by usage type - Technical assistance on safer building practice delivered at community level - Supporting government with technical assistance on housing, planning and policy on better/safer building approaches. Coordination Activities: - Information, education, and communication (IEC) materials on appropriate, safe, building standards are provided to affected populations and implementing agencies - Monitoring to track outcomes of shelter programming including household and gender/vulnerability disaggregated satisfaction, restoration of livelihoods, access to schools, water/sanitation, family health, etc. Timeframe: November 2013 to December 2014 Key Target Vulnerable Groups: (see Key Vulnerable Groups) Cluster objective 3: Shelter Cluster partners will provide support to build community-level capacity to rebuild or repair housing damaged by the typhoon including alternative supplies of materials, increasing labour supply, and ensuring appropriate access to building areas is available. Outcome-level indicator and target 3.1. Assist rapid economic recovery in Typhoon affected areas (coastal, inland) (coordinated with the Early Recovery/Livelihood Cluster). Operational Activities: - Cash for work programmes that support recovery of salvageable material and disposal of unusable debris, with a particular focus on young underemployed males - Training of local carpenters, labourers, plumbers, electricians to be used in repair and reconstruction efforts Timeframe: November 2013 to December 2014 Key Target Vulnerable Groups: (see Key Vulnerable Groups) - Young, undereducated, underemployed men and youths |
| Key Vulnerability Groups | Current most vulnerable groups are identified as - Households with totally destroyed, uninhabitable houses - Poor households with low self-recovery capacity - Households that have insecure tenure - Households that have migrated - Households that are displaced and settled informally - Households at risk of relocation due to no-build zones - Households in rural areas with low access to materials - Households with pre-existing vulnerabilities such as female/single/elderly headed households, with disabled family members, etc. |
| Monitoring and Evaluation | Cluster partners will report regularly to Shelter Cluster information management personnel for compilation of 3W information. These compilations and analyses will be shared with cluster partners. The Shelter Cluster will also initiate situational monitoring practices in order to track progress against outcomes and verification of output level information. |

Technical Standards and Intervention Types

| Objective | INT# | Description | Target #HH | Notes and specification or standards |
| --- | --- | --- | --- | --- |
| Emergency | 01 | Tarpaulins | 250,000 | 1 per household of up to 5 people, 2 per household of 6 or more people - to be distributed with fixings and rope. Or cash grants of up to 3,000PHP |
|  | 02 | Tents | 50,000 | Family tent, minimum 16m2 of covered useable area |
|  | 03 | NFIs: Household Kits |  | Bedding and blankets, including solar lights, charger, radios, etc. |
|  | 04 | NFIs: kitchen sets |  | Cooking pots with lids, saucepan, serving spoon, table spoons, cups, plates, soup bowls. |
|  | 05 | Training: Emergency Shelter | 300,000 | Orientation for tarpualins fixings and/or setting up of tents, use of IEC material |
|  | 06 |  |  |  |
|  | 07 |  |  |  |
|  | 08 |  |  |  |
|  | 09 |  |  |  |
| Supporting Self Recovery | 10 | Construction Material | 500,000 | The material package must include sufficient material for durable roofing solution and/or cash of up to the same value. See the Shelter Cluster's technical guidelines for details |
|  | 11 | Tool Kit | 500,000 | Households have access to general repair and rebuilding: Timber saw (450mm), claw hammer, shovel, tin snip, pliers, etc. Can be distributed at household levels or community level for sharing between 5-10 households. |
|  | 12 | Clean-up Kit |  | Includes bucket, floor cloth, broom, mop, dustpan, scrub brush, sponge, detergent, gloves and chlorine. |
|  | 13 | Salvage, recycling and removal of debris |  | Support use of salvage material in repair and reconstruction. Includes community clean up and salvaging kit (wheelbarrow, crow bar, sledge hammer, shovel, hack saw, bolo (knife), barra, etc.) and cash for work. |
|  | 14 | Technical Assistance | 500,000 | Orientation and demonstration of simple key technical messages for safer building practices. May include construction/repair of model shelter. |
|  | 15 | Training of skilled labours |  | Training of carpenters and masons, plumbers, etc. in safer construction techniques. |
|  | 16 | Transitional shelter support |  | Include construction of transitional shelter, row houses, and core houses. Parameters to be specified in the Shelter Cluster’s Transitional Shelter guidelines. |
|  | 17 | Rental Support |  |  |
|  | 18 |  |  |  |

Intercluster issues

| Cluster | Lead-Agency | Comments |
| --- | --- | --- |
| Coordination | OCHA | Sitreps, shelter advocacy, FA, SRP, intercluster coordination, advocacy with Government |
| CCCM | IOM/UNHCR | NFI’s and shelter needs in collective centres, relocations from and to collective centres, Displaced Tracking Matrix, beneficiary lists and data on vulnerable groups |
| Early Recovery /Livelihoods | UNDP/FAO | Housing, building codes, debris removal, hazardous and no-build zones, coco lumber salvaging |
| Education | UNICEF/StC | Use of schools as collective centres, relocations from schools |
| Telecom | WFP | Facilitate beneficiary communications e.g. use of mobile networks, improved operational communication (good bandwidth, security comms) |
| Food security | WFP/FAO | Distribution points of food relevant for shelter NFIs. Information on beneficiary groups and vulnerabilities |
| Health | WHO | Incidence of disease that can be avoided by provision of appropriate shelter and NFI, HIV/AIDs and shelter guidance |
| Logistics | WFP | Transportation, storage, supply chain, customs clearance, security of movement and humanitarian access |
| Nutrition | UNICEF | Information on vulnerable groups through therapeutic feeding data |
| Protection | UNHCR | Loss of documentation, Housing, Land and Property issues, GBV, female and child headed households, elderly and disabled, vulnerability data, security |
| WASH | UNICEF | Ensure shelter sites have WASH facilities, support on identifying informal settlements |

Annex material:  (to be included in “Detailed Shelter Strategy”)

- Guiding Principles and Policies

- Gender, disability, age, GBV, HIV/AIDS Guidance

- Environment Guidance

- Landmines

- HLP checklist

- Annex 1: Detailed Shelter Indicators

|  |  | Indicator | Source/Informing datasets | Calculation/ Targets |
| --- | --- | --- | --- | --- |
| Needs | Overall Need for Shelter Assistance – These indicators will inform analysis on defining the overall caseload of households that will require some form of shelter assistance |  |  |  |
|  | N1 | Number/% of Houses damaged and destroyed as a result of the Typhoon | DSWD DROMIC housing damage (verified through REACH) |  |
|  | N2 | Number/% of HH that are currently displaced from their home plot as a result of the typhoon | DSWD DROMIC – Inside EC, Outside EC, CCCM Cluster DTM, REACH assessment |  |
|  | N3 | Number/% of HH that will require relocation due to no-build-zones | DSWD |  |
|  | N4 | Number/% of HH that are considered poverty vulnerable and have sustained damaged housing | National Poverty indicators, 4P registry, REACH |  |
|  | N5 | Number/% of HH that are settled informally and have sustained damage from the typhoon | DSWD DROMIC - outside ECs (minus home plot displaced?) |  |
|  | Strategic Target Objectives – Strategic targets as defined by DSWD and Shelter Cluster partners as being the humanitarian caseload that should be covered through non-governmental humanitarian agencies |  |  |  |
|  | OB1 | Obj 1 - Shelter Cluster partners will provide immediate life-saving emergency shelter such as tarpaulin and tents with supporting NFI solutions for the most vulnerable typhoon affected households. | DSWD-chaired Shelter Cluster Strategic Advisory Group decision | 300,000 HH |
|  | OB2 | Obj 2 - Shelter Cluster partners will provide support for household self-recovery through incremental housing solutions using consultative, participatory processes. | DSWD-chaired Shelter Cluster Strategic Advisory Group decision | 500,000 HH |
| Capacity | C1 | Number/% of HH that show evidence of self-recovery | REACH |  |
|  | C2 | Number/% of HH that are projected to be supported from government responses | DSWD |  |
|  | C3 | Number/% of HH that have been assisted through informal civil society interventions | REACH |  |
|  | C4 | Number/% of HH that are projected to be given emergency shelter support from humanitarian agencies | Shelter Cluster 3W Reporting |  |
|  | C5 | Number/% of HH that are projected to be given recovery shelter support from humanitarian agencies | Shelter Cluster 3W Reporting |  |
| Outputs | OP1 | # of Households that have been provided a minimum of 1 tarpaulin | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP2 | # of Households that have received a tent solution | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP3 | # of outreach methods used to convey good practice with tarpaulins | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP4 | # of different IEC materials distributed | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP5 | Number/% of HH that have been provided a durable roof solution | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP6 | Number of supplementary hardware interventions that contribute to durable housing, including tools, wall and structural materials | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP7 | # HH who have been provided a cash disbursement of 10,000 PHP or more | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP8 | # of awareness raising and outreach campaigns | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP9 | # of government departments/units supported | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP10 | # of service types provided to Government | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP11 | # of monitoring processes during the next year | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP12 | # of individuals employed for salvageable/debris material recovery | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP13 | % of employed individuals who are young males | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP14 | # of individuals trained | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP15 | # of trainings held | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
|  | OP16 | % of employed individuals who are young males | Shelter Cluster 3W Reporting Shelter Cluster Monitoring |  |
| Outcomes | OC1 | Number/% of households that sustained house damage from the Typhoon that are currently living in a habitable house/dwelling | Shelter Cluster Monitoring |  |
|  | OC2 | Number/% of households that sustained house damage that are satisfied with assistance - Built back safer - Willingness towards location - Access to schools - Health - WASH - Livelihoods | Shelter Cluster Monitoring |  |