## Sheet1
| Global Shelter Cluster | [5 empty] | 2014-06-09
ShelterCluster.org
Coordinating Humanitarian Shelter
Outreach & Capacity Working Group
Background (this section needs to outline clearly what the context/background of the issues are or the gaps/needs to which the activities listed below relate. Refer to 2014 Thematic Priorities document)
The GSC has identified that there is a need to promote better engagement with and participation of local and national actors as well as emerging humanitarian actors. Additionally, more could be done to better understand current existing shelter response capacities and partnerships to ensure complementarity of efforts, as well as explore synergies and opportunities for the provision of inter-agency trainings at the country and global levels in an effort to increase capacity and improve practice.
Objective
To expand the capacity of the GSC to support country-level shelter coordination and response by increasing the participation of cluster partners and other actors, and maximizing the human and material capacity of the cluster.
No. | Priority (High, Medium, Low) | Level of Difficulty/Effort (High, Medium, Low) | Activity | Output/Result | GSC Strategy Outcome/s (Refer to GSC strategy outcome numbers) | By who (Lead, participants) | For when (Date) | Status (Finished, on-going, to be defined)
Outcome 1: An inclusive broad based GSC, with increased participation of emerging humanitarian actors
1 | High | High | Map organisations that are attending shelter clusters at country level and at global level and identify organisations that participate in country-level clusters but not in the global cluster. | - A matrix capturing possible future partners and who will approach them - Increased participation in the GSC and in 2015 WGs | 2.01
2 | High | Low | Share some of the outputs in the GSC work plan with Shelter regional fora (see point 2.1.2) in order to divide up the work. | A matrix capturing outputs of the GSC workplan and the regional for a that will undertake them | 2.01
3 | Medium | Low | Map out the regional fora and regional events where the shelter cluster should be represented. | A matrix capturing regional events and who will be in charge of talking about the cluster there. | 2.01
4 | Medium | Medium | Develop outreach material in appropriate language to contact other organisations (leaflet, video, etc.) and agree process to approach agencies and for a | A toolkit to “sell” the Global Shelter Cluster. | 2.01
5 | Medium | ? | Open the participation in GSC Working Groups to non-GSC partners. |  | 2.1
6 | Medium | Medium | Identify and approach particular non GSC partners who could usefully contribute to specific WG activities |  | 2.1
Outcome 2: Increased engagement with local and national actors
7 | High | High | Mentorship, identification of local talents, including Gvmt, with capacity building (including internship opportunities) within GSC | 1. Agreed methodology for identification of local talents, mentorship and internship 2. Pilot it in 1-2 countries | 1.9, 1.8
8 | Medium | High | Develop a country-level shelter cluster awareness and training curriculum for cluster partners and local and national actors. | Curriculum developed and piloted | 1.9, 1.8
9 | Medium | Medium | Develop a training materials for governments including fundraising guidelines, leaflets, toolkits | Materials available | 1.9, 1.8
Outcome 3: Maximize the GSC human and material capacity: material stockpiles/ prepositioning aproaches, human resources, overall capacity
10 | Medium | Medium | Review/appraise the role of the GSC in promoting/advancing training and capacity building | - GSC Capacity Building Strategy including mentoring, distance learning, communities of practice, learning events | 1.1, 1.2, 2.7, 1.10, 2.6
11 | Medium | Low? | Map current capacities, partnerships, and identify gaps and opportunities for inter-agency capacity building and expansion of GSC partnerships. | - Map training initiatives - Map stockpiling / prepositioning approaches - Map HR approaches - Identify gaps
12 | High | High | Develop a self-learning online training in shelter coordination and response. |  | 1.7
13 | Medium | Low | Work towards defining common deployment methodologies including common ToR for members of the coordination team. | ToR for country-level shelter clusters shared | 1.8
14 | Medium | Medium | Develop a short training on common basic shelter concepts |  | 1.7
15 | Medium | ? | Cluster agencies to share information on partnerships/collaborations to determine extent of collaboration to date. | Summary of existing partnerships/collaborations | 2.9
16 | Medium |  | Increase knowledge about settlement approach among actors |  | 3.5
17 | Medium | Medium | Formalise a link with the Logistics Cluster | Improved availability and readiness of resources | 2.7
Current Members of the Working Group
Org | Name |  | Email address | Role
Shelter Box | Nicky Richardson |  | nickyrichardson@shelterbox.org | Member
Shelter Centre | Tom Corsellis |  | tom@sheltercentre.org | Peer reviewer
ACTED | Luca Pupulin |  | luca.pupulin@acted.org | Peer reviewer
CRS | Seki Hirano |  | seki.hirano@crs.org | Peer reviewer
UAH | Verónica Sánchez Carrera |  | vsc.arq@gmail.com | Peer reviewer
Habitat for Humanity International | Kip A. Scheidler |  | kscheidler@habitat.org | Member
IOM | joseph ashmore |  | jashmore@iom.int | Peer reviewer
Interaction | Hilmi Mohammed |  | MHilmi@INTERACTION.ORG | Member
IFRC/CanRC | Neil Bauman |  | neil.bauman@sheltercluster.org | Chair
UNHCR | Miguel Urquia |  | urquia@unhcr.org | Chair