## Slide 1: National Shelter Cluster Meeting
Kathmandu – DUDBC
20th May 11am
To be added to the contact list please email
coord3.nepal@sheltercluster.org

## Slide 2: Updates
Government update:
  Tarp Distribution: the Government has ordered 622,709 of which 230,569 have been distributed
  Humanitarian Partners – 192,094 distributed, with 509,547 in pipeline/to be distributed.
  Overall total – 528,400 distributed

## Slide 3: Updates
Flash Appeal – 26% funded at USD20,035,189
To be relaunched on Friday 29th May
To be extended from 3 months to 5 months
Currently no plan to increase amount overall
But needs to include response for second earthquake and contingency planning
Process and documentation to be provided by OCHA COB today.
If 100% funded then we would be able to support 350,000HHs with emergency shelter and approx. 150,000HHs with support to self recovery

## Slide 4: Strategic Goal
To deliver a shelter response that supports appropriate, flexible, progressive solutions to affected, vulnerable populations that contributes to their own self recovery to provide a safer, more resilient and durable shelter.
With the following options based on addressing humanitarian needs:
Shelter interventions which support short and long term self-recovery approaches
Capacity building through different means of trainings appropriate to the recipient
Key messaging promoting more resilient shelter

## Slide 5: Short- term objective
Short-term objective: 350,000 affected and most vulnerable households, are reached with a life saving shelter solution; prioritizing at risk groups (in hard to reach areas) by the end of July.
Outcome Indicator:
% of households whose homes have been destroyed or damaged that attain a basic, lifesaving shelter solution.

## Slide 6: Long-Term Objective
Long-term objective: XXX,XXX affected and most vulnerable households receive shelter solutions that progressively contribute and promote appropriate long-term self recovery. This should build upon the short term objective caseload
Outcome Indicators:
% of households whose homes have been destroyed or damaged that have a rigid roof
% of households that will keep more than 50% of their dwelling structure over the next two years

## Slide 7: Technical Guidelines
The Shelter technical and Implementation guidance in consultation with the six technical working groups identified by Shelter Cluster Partners
The Technical and Implementation Guidance Document will seek to outline for each response option:
    Intervention Purpose
    Outline the recommended Package as best practice
    Recommend Minimum Materials Specifications
    Implementation Modalities for Shelter
    Implementation Support
      Technical Training
      Capacity Building
      Ensuring Accountability to Beneficiaries

## Slide 8: Technical Guidelines
PART 1 Strategic Objective 1- SHORT TERM SOLUTIONS - Emergency/Relief Sheltering
Timeframe UP TO 3 MONTHS - Two potential ‘crises points’ (Monsoon/Winter)
  Targeting Households
  Specific Objective
  Key Principles: Best Practice
  Strengths and Challenges of the intervention

## Slide 9: Technical Guidelines
PART 1 - SHORT TERM SOLUTIONS - Emergency/Relief Sheltering
  Household kit Package ($100 – 10,000 NRup)

## Slide 10: Technical Guidelines
PART 1 - SHORT TERM SOLUTIONS - Emergency/Relief Sheltering
  Household kit Package ($100 – 10,000 NRup)
    Tarpaulin Specifications
    Tents Specifications
    Rope Specifications
    Blanket/ Mat Specifications
    Tools Specifications

## Slide 11: Technical Guidelines
PART 1 - SHORT TERM SOLUTIONS - Emergency/Relief Sheltering
  Implementation Support
    Emergency Shelter Kit Training
    Support Capacity Building and Training
    Emergency Information, Education and Communications (on shelter cluster website)
  Emergency Shelter Accountability Recommendations
    Shelter Post Distribution Monitoring and Assessment (for support to self-recovery)

## Slide 12: Technical Guidelines
PART 2 - Strategic Objective 2 – LONG TERM- SUPPORTING SELF RECOVERY Timeframe
Timeframe From 2 MONTHS onwards, Self- Recovery building to permanent reconstruction
    Earthquake Response Programming
      Intermediate/Temporary shelter provision for most vulnerable families
      Material inclusion in self-recovery and reconstruction plans
    Crises point 1:Monsoon Contingency (Intermediate solutions)
    Crises point 2: Winter Contingency

## Slide 13: Technical Guidelines
Support to Self- Recovery- Earthquake response Programming

## Slide 14: Technical Guidelines
Temporary Shelter Package
Repairs
    CGI Specifications
    Fixings Specifications
    Timber/ Bamboo –Other Materials
    Tools specifications
  Delivery Modality
    Materials Distribution
    CASH/Voucher Conditional/Unconditional

## Slide 15: Technical Working Groups
6 Technical Working Groups
  Capacity Building Training
  Key Messages
  Shelter Interventions
  Cash Modalities
  Contingency Planning (mosoon and winter)
  Accountability to Beneficiaries
Technical Advisory Group, 1 meeting per week

## Slide 17: Shelter Assessment
Shelter assessment – completed in Kathmandu, Bhaktapur, Lalitpur, Gorkha, currently underway in Dolahka
Govt agreed to assessment of 8 other priority districts: Sindhuli, Sindhupalchok, Rasuwa, Okhaldhunga, Dhading, Makawanpur, Kabre, Nuwakot, Ramechhap
Support to carry out the assessment – transport and enumerators – training etc will be provided

## Slide 18: Top Figures

## Slide 19
Chart: Gap per District – included planned
| Bhaktapur | Dhading | Dolakha | Gorkha | Kathmandu | Kabhrepalanchok | Lalitpur | Makawanpur | Nuwakot | Okhaldhunga | Ramechhap | Rasuwa | Sindhuli | Sindhupalchok
Emergency Shelter (Tarpaulins and/or tents) | 4152.7301 | -4703.9472 | 1821.7799 | 30773.0319 | 30335.8072 | 82524.8953 | -4306.4723 | 22072.7868 | 82221.9637 | 6206.6169 | 58822.1534 | 695.2913 | 17063.8988 | -16890.2359
Household kits (excluding tarpaulins) | 7727.3651 | -2095.4736 | 35416.89 | 40274.0159 | 20542.9036 | 50031.4476 | 4194.2638 | 13217.8934 | 40286.9819 | 5727.3085 | 31370.0767 | 645.1457 | 1296.9494 | 46489.382
Tool kits and fixings | 9227.3651 | 44576.5264 | 43934.89 | 39837.0159 | 25808.9036 | 49566.4476 | 4564.2638 | 13217.8934 | 51100.9819 | 6043.3085 | 31370.0767 | 4818.1457 | 15989.9494 | 48081.382

## Slide 20
Chart: Distributed today vs Needs
| Bhaktapur | Dhading | Dolakha | Gorkha | Kathmandu | Kabhrepalanchok | Lalitpur | Makawanpur | Nuwakot | Okhaldhunga | Ramechhap | Rasuwa | Sindhuli | Sindhupalchok
NEED (Number of HHs) | 11227.3651 | 47576.5264 | 48434.89 | 45157.0159 | 28808.9036 | 54034.4476 | 6564.2638 | 15217.8934 | 55100.9819 | 7843.3085 | 32870.0767 | 8618.1457 | 17789.9494 | 59014.382
HH with Emergency Shelter (Tarps or Tents) | 3224.5 | 8278 | 5501 | 17691.5 | 5959.5 | 4071 | 3259 | 1681.5 | 3811 | 1440 | 946.5 | 1022 | 1160 | 32567
Household kits (excluding tarpaulins) | 1500 | 6777 | 1718 | 783 | 5097 | 3 | 370 | 0 | 6293 | 316 | 0 | 3085 | 500 | 929
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60

## Slide 21: East Hub

## Slide 22
Chart: Dolkha Distributed
| Jhyaku | Sunakhani | Bigu | Dandakharka | Babare | Bhedapu | Bulung | Jiri | Melung | Pawati | Lamabagar | Orang | TBD | Gairimudi | Katakuti | Laduk | Alampu | Bhirkot | Hawa | Jhule | Khare | Lapilang | Suri | Namdu | Kalingchok | SusmaChhemawati | Fasku | Chilankha | Kabhre | Khopachagu | LakuriDada | Sahare | Sailungeswor | Bhimeswor N.P. | Bhusaphedi | Bocha | Chankhu | Chhetrapa | Chyama | Dudhpokhari | GauriSankar | GhangSukathokar | Japhe | Jugu | Lamidada | MagaPauwa | Mali | Malu | Marbu | Mirge | Sundrawati | Syama | Thulopatal
Tarpaulin | 570 | 300 | 155 | 108 | 100 | 100 | 100 | 100 | 100 | 100 | 99 | 80 | 65 | 35 | 32 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 12 | 9 | 7 | 6 | 5 | 5 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 23
Chart: Kavre Distributed

## Slide 24
Chart: Okhalhunga Distributed
| TBD | Khijifalate | Baruneshwor | Balakhu | Tarkerabari | Bhussinga | Ragani | Rawadolu | KhijiChandeshwori. | Kaptigaun(Khigikati) | Andheri(Narayansthan) | Baksa | Barnalu | Betini | Bhadaure | Bigutar | Bilandu | Chyanam | Diyale | Fediguth | Fulbari | Gamnangtar | Harkapur | Jantarkhani | Jyamire | Kalikadevi | Katunje | Ketuke | Kuibhir | Kuntadevi | Madhavpur | Mamkha | Manebhanjyang | Moli | Mulkharka | Narmedeshwor | Okhaldhunga | Palapu | Palte | Pokali | Pokhare | Prapcha | Ragadeep | Raniban | Ratmata | Rumjatar | Salleri | Serna | Shreechaur | Singhadevi | Sisneri | Taluwa | Thakle | Thoksel | Thulachhap | Ubu | Yasam
Tarpaulin | 624 | 257 | 200 | 150 | 150 | 135 | 133 | 116 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 107 | 0 | 0 | 0 | 35 | 133 | 16 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 25
Chart: Ramechap Distributed
| Manthali | Ramechhap | TBD | Gumdel | Bhadaure | BamtiBhandar | Betali | Bethan | Bhatauli | Bhirpani | Bhujee | Bijulikot | Chanakhu | Chisapani | Chuchure | Dadhuwa | Deurali | Dimipokhari | Doramba | Duragau | Farpu | Gelu | Goswara | Gothgau | GunsiBhadaure | Guptesor | Hiledevi | Himganga | Kathjor | Khadadevi | Khaniyapani | Khimti | Kubukasthali | Lakhanpur | Majuwa | Makadum | Maluwajor | NagaDaha | Namadi | Okhreni | Pakarbas | Phulasi | Pinkhuri | Pritee | Puranagau | Rakathum | Rampur | Rasanalu | Saipu | Salupati | Sanghutar | Sukajor | Sunarpani | Those | Tilpung | Tokarpur
Tarpaulin | 1675 | 800 | 169 | 50 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 26
Chart: Sinshuli Distributed
| TBD | Baseshwor | JhangajholiRalmata | Kamalamai N.P. | Kapilakot | PuranoJhangajholi | Sitalpati | KusesworDumja | Majhuwa | Bhadrakali | Bhimeshwor | BhuwaneshoriGwaltar | HariharpurGadhi | Mahendrajhayadi | Pipalmadi | Dudbhanjyang | KhangSang | Kholagaun | Solpathana | SunamPokhari | Amale | Arunthakur | Bahuntilpung | Balajor | Bastipur | Belghari | Bhimsthan | BitijorBagaiya | Dadiguranshe | Dudhouli | Harsahi | Hatpate | Jalkanya | Jarayotar | Jinakhu | KakurThakur | Kalpabrishykha | Kyaneshwor | Ladabhir(Mahendra) | Lampantar | Mahadevdada | Mahadevsthan | Netrakali | Nipane | Ranibas | Ranichuri | Ratanchura | Ratnawati | Santeswori(Rampur) | Sirthouli | Tamajor | Tandi | Tinkanya | Tosramkhola | TribhuvanAmbote
Tarpaulin | 616 | 350 | 300 | 300 | 300 | 300 | 280 | 275 | 275 | 175 | 175 | 150 | 100 | 100 | 100 | 25 | 25 | 25 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 27
Chart: Sindhupalchowk distributed

## Slide 28: West Hub

## Slide 29
Chart: Dhading Distributed
| TBD | Lapa | Bhumesthan | Baireni | Jogimara | Nilkantha | Salyantar | ReeGaun | Goganpani | Sertung | Khalte | Jeewanpur | Tipling | Thakre | Aginchok | Benighat | Gajuri | Kewalpur | Budhathum | Dhussa | Dhola | Darkha | Jyamrung | Kiranchok | Baseri | Chainpur | ChhatreDyaurali | Dhuwakot | Gumdi | Jharlang | Kalleri | Katunje | Khari | Kumpur | Mahadevsthan | Maidi | Marpak | Mulpani | Muralibhanjyang | Nalang | Naubise | Phulkhark | Pida | Salang | Salyankot | Sangkosh | Satyadevi | Semjong | Sunaulabazar | Tasarpu | Tripureswor
Tarpaulin | 7996 | 1529 | 30 | 0 | 350 | 311 | 340 | 210 | 580 | 591 | 157 | 2123 | 120 | 52 | 0 | 161 | 100 | 100 | 954 | 54 | 92 | 50 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0
Tents | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 4560 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 77 | 1985 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 30
Chart: Gorkha Distributed

## Slide 31
Chart: Gorkha Distributed

## Slide 32
Chart: Nuwakot Distributed

## Slide 33: Central Hub

## Slide 34
Chart: Baktapur distributed
| Bhaktapur N.P. | Madhyapur Thimi N.P. | Nagarkot | Changunarayan | Sudal | Jhaukhel | Bageswori | Balkot | Chhaling | Chitapol | Dadhikot | Duwakot | Gundu | Kautunje | Nankhel | Sipadol | Sirutar | Tathali | TBD
Tarpaulin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 35
Chart: Kathmandu Distributed
| Kathmandu M.N.P. | Lapsephedi | Kabhresthali | Bhimdhunga | Ramkot | Sangla | JhorMahankal | Kirtipur N.P. | Chalnakhel | Talkududechour | Futung | Jorpati | Sitapaila | Aalapot | BaadBhanjyang | Bajrayogini(Sankhu) | Balambu | Baluwa | Bhadrabas | Budanilkantha | ChapaliBhadrakali | Chhaimale | ChouketarDahachok | Chunikhel | Daanchhi | Daxinkali | Dhapasi | Dharmasthali | Gagalphedi | Gokarneswor | Goldhunga | Gonggabu | Gothatar | IchangNarayan | Indrayani | Jitpurphedi | Kapan | KhadkaBhadrakali | Machhegaun | Mahadevathan | Mahankal | Manmaiju | Matatirtha | Mulpani | Naglebhare | NaikapNayaBhanjyang | NaikapPuranoBhanjyang | Nayapati | Pukhulachhi | Satikhel | Satungal | Seuchatar | Sheshnarayan | Sundarijal | Suntol | Thankot | Tinthana | TokhaChandeswori | TokhaSarswoti | TBD
Tarpaulin | 9236 | 2000 | 1848 | 1250 | 1122 | 650 | 445 | 249 | 100 | 100 | 46 | 40 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 0 | 0 | 1250 | 1122 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 36
Chart: Lalitpur Distributed
| Bhattedanda | Lele | Jharuwarasi | Thaiba | Chhampi | Nallu | Siddhipur | Bhardev | Choughare | Dalchoki | Devichour | Thecho | Lubhu | Dhapakhel | Ashrang | Badikhel | Bisankhunarayan | Bukhel | Bungamati | Chandanpur | Chapagaun | Dhusel | Dukuchhap | Gimdi | Godamchaur | Godawari | Gotikhel | Harisiddhi | Ikudol | Imadol | Kaleswor | Khokana | Lalitpur U.M.N.P. | Lamatar | Malta | Manikhel | Pyutar | Sainbu | Sankhu | Sunakothi | Thuladurlung | Tikathali | TBD
Tarpaulin | 595 | 220 | 139 | 131 | 101 | 100 | 53 | 50 | 50 | 50 | 50 | 45 | 41 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 0 | 50 | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 50 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 37
Chart: Rasuwa Distributed
| Bhorle | Gatlang | TBD | Syafru | Thuman | Goljung | Bridhim | Chilime | Dandagoun | Dhunche | Haku | Jibjibe(Nilkantha) | Laharepouwa | Langtang | Ramche | Saramthali | Thulogoun | Timure | Yarsa
Tarpaulin | 422 | 400 | 240 | 140 | 135 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Household kits (excluding tarpaulins) | 100 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool kits and fixings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 38: Any other business
      Move meeting to once a week? On a Sunday?
      Next meeting – Sunday 11am DUDBC

## Slide 39: Thank you very much
First Name | Last Name | Role | email address | Mobile
Victoria | Stodart | Lead Coordinator | coord1.nepal@sheltercluster.org | 9810120909
Saanjeev | Hada | Operations Coordinator | Sanjeev.hada@ifrc.org | 9851027783
Seki | Hirano | Field Coordinator | coord2.nepal@sheltercluster.org | 9813149666
Lise Anne | Pierce | Assistant Coordinator | coord3.nepal@sheltercluster.org | 9810120923
Raul | Ecay | Information Manager | IM2.nepal@sheltercluster.org | 9810152591
Alisha | Ghimire | Information Manager | IM4.nepal@sheltercluster.org | 9851216004
Eve | Leonard | Technical Coordinator | tech1.nepal@sheltercluster.org | 9808429143
Siobhan | Kennedy | Technical Coordinator | tech2.nepal@sheltercluster.org | 9818414269
Robert | Trigwell | Assessment Coordinator | robert.trigwell@reach-initiative.org | 9813031024