Participants: MEDAIR, IOM, IFRC, Handicap International, OFDA, DFID, OCHA, UNOSAT, UN-CMCoord

| Action point | Responsible | Date |
| --- | --- | --- |
| Cluster to highlight lack of implementing partners during Global Shelter Cluster meeting next week in Geneva | Cluster | Next week |
| Cluster and partners to finalise standard interventions | Cluster/partners | COB 28/9 |

- Partner capacity updates

  - IFRC has a plane from Afaland coming in with NFIs, kit compositions not defined yet. IFRC is requesting health care, logistics and water/sanitation ERUs.

  - OFDA’s online commodities warehouse can be used to request items.

  - Logistics Cluster needs to be involved with incoming shipments to avoid customs issues.

- Standard interventions

  - No comments have been received on the proposed standard interventions.

  - Infrastructure upgrades will be included in our interventions in camps or camp like settings.

  - Tents may not be needed since there are 5,500 tents available in empty camps, they are UNHCR/IFRC spec.

  - There is a need for advocacy with the government to make sure that interventions are not limited to camps.

  - Repairs to schools will fall under the Shelter Cluster as Education has not been activated yet.

  - A TWIG will be set up to work out standard interventions, MEDIAR, Handicap, IFRC and IOM will participate.

- Assessment update

  - Today 5 new sites will be assessed: Kjorestad, Penne, Einarsneset, Kaneheia and Presteneset.

  - DTM released figures of the sites yesterday, 4,925 IDPs were verified in 5 sites.

  - UNOSAT risk mapping shows that Siggersvall and Lista Stadium are in high risk flood zones, the government should be made aware of this.

  - It is not clear yet when the floods will subside, damage assessments are needed in areas most affected (high wind speed zones).

- Funding update

  - OFDA funding proposal includes shelter, focuses on out of camp solutions, durable solutions at household level are preferred.

  - MEDIAR and IOM are working on a joint proposal for ECHO funding.

  - DFID call for proposals closes this morning.

  - CERF request will be launched, so partners can request funds for short-term life-saving projects.

- AOB

  - Military asset request form is available on the website.

  - Mosquito nets from IOM will be given to MEDAIR, soap goes to Health.

Next meeting: 28 September 17:00-18:00