ES/NFI Sector Monthly Coordination Meeting

Minutes

Date:	22 November 2017, 11.00 – 12.30 AM

Location: Blue Nile Conference Room, UNHCR

Action points:

- IOM and UMCOR to share pictures of the newly constructed shelters in West and East Darfur respectively.

- Reactivating the TWGs which have not met since early this year.

- Activation of East Darfur Coordination meeting. Sector coordinator to send out a request seeking monthly chairs on a rotational basis.

- UMCOR to share their fire prevention training material to ESNFI team for circulation sector.

- Partners to share any interesting stories or updates that they would like to publish in the quarterly sector update.

| Agenda Item | Discussion/action points |
| --- | --- |
| Introduction |  |
| Previous action points | IOM to share their PDM mission report. - Pending |
| Partner updates | IOM: In South Darfur, two needs assessments for the protracted caseloads are completed now; 800 improved shelters in Kass , complemented with ES/NFIs from the Common pipeline, to be distributed early December. In North Darfur 1,878 NFI kits will be distributed next week, including items from the common pipeline. In West Darfur construction of T-Shelter is still on-going. In west Kordofan: A needs assessment was completed with the registration of mixed load of refugees and IDPs. 50,000 individuals in Diling , Dalami , and Goosh . UMCOR: In East Darfur, 300 emergency shelters currently under construction in Adila , Abu karinka and El Deaen . Training on fire prevention and shelter care was conducted for 1000 households through the community extension workers. SRCS: In South Darfur 50 NFI kits were distributed from the NFI common pipeline in Bilail to newly displaced IDPs Also conducted a needs assessment in Kafia Kanji, South Darfur that identified 90 refugee households from CAR and 500 households from South Sudan. ES/NFI distribution planned. In South and West Kordofan, 323 South Sudanese refugees were assisted with ES/NFIs from the refugee stock. In WNS camp management is now done by COR. AOSCD: In south Darfur distributed ES/NFIs to 266 households in Belail IDP camp Interagency assessment with IOM ongoing in Kass and Gerida, targeting 1500 protracted IDP households. TGH : TGH NFI project under RRF fund ended in September and TGH currently has one project running in the ES/NFI sector under ECHO fund. TGH Distributed 100 NFI Kits and 50 shelters in Beida , West Darfur for Returnees from TGH buffer stock (pre-positioned through ECHO fund), and planning distribution of NFIS in Golo soon. |
| TGH Market Fares presentation | A presentation on TGH market fairs in two locations, was presented to the meeting on behalf of TGH. During the Q & A, meeting participants asked about the cost effectiveness of the process, the criteria of choosing the suppliers and the use of needs assessments of the needy population. TGH mentioned that one of the challenges was the volume of logistical arrangements to complete the fair, the unfamiliarity of suppliers with the process which is new to them, it took time to convince them to bring their commodities to the remote areas, and finally the security situation limiting the freedom of movement of the traders. |
| AOB | n/a |

**Next meeting Wednesday, 13th December2017

Participants List

| Name | Title/Organization | Email | Phone Number |
| --- | --- | --- | --- |
| Amin Al Fadil | UMCOR | aefadil@umcor-sudan.org | 0912339376 |
| Abdalmalik Abdalla Harun | AOSCD | Abdalmalikabdalla11@gmail.com | 0911150960 |
| Hatim Badien | OFDA/USAID | hbadien@usaid.gov | 0912160831 |
| Mayada Abdelrhman | Labena | Labena2014@hotmail.com | 0122257736 |
| Abdalla Suliman | SRCS | Abdalla.sulaiman@hotmail.com | 0912610520 |
| Lucie Meriam | TGH | Grantsmanager.soudan@triangleh.org | 0917460693 |
| Dooa Abdelrahman | UNHCR | abdelrdo@unhcr.org | 092240669 |
| Fatima Edris Khamis | Labena | Labena2014@hotmail.com | 017238483 |