| Cluster Coordination Performance Monitoring Report and Action Plan |  |  |  |
| --- | --- | --- | --- |
| Cluster: Emergency Shelter and NFI merged with CCCM Country: Yemen Level: National and Sub-National Survey completed on: 27th September 2017 CCPM meeting held on: TBD |  |  |  |
| Response rate amongst partners |  |  |  |
| Partner type | Numbers partners responding (national / sub-national level) | Total number of partners (based on last CDM) | Response rate (at national level) |
| International NGOs | 3 (3/0) |  |  |
| National NGOs | 57 (39/18) |  |  |
| UN organizations | 3 (1/2) |  |  |
| National authority | 2 (2/0) |  |  |
| Donors | 1 (1 / 0) |  |  |
| Others | 0 (0 / 0) |  |  |
| Total | 67 (46/21) |  |  |
| Comments on response rate |  |  |  |
| Other comments |  |  |  |

| Core cluster functions | Performance status at national level (Partners) | Difference with Coordinators (parnters-coordinators) | Constraints, unexpected circumstances, good practice | Follow-up action and support requirements | Deadline | Responsible for follow up |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Supporting service delivery | Satisfactory (72%) | 3% |  |  |  |  |
| 2. Informing strategic decisionmaking | Good (79%) | 16% |  |  |  |  |
| 3. Planning and implementing cluster strategies | Satisfactory (73%) | -2% |  |  |  |  |
| 4. Monitoring and evaluating performance | Satisfactory 74% | 11% |  |  |  |  |
| 5. Building nat’l capacity in prep. and cont. planning | Needs Improvement (56% ) | -19% |  |  |  |  |
| 6. Supporting robust advocacy | Satisfactory (73%) | 4% |  |  |  |  |
| 7. Promoting accountability to affected populations | Satisfactory (66%) | -3% |  |  |  |  |

| Core cluster functions | Performance status at sub-national level | Difference with Coordinators (parnters-coordinators) | Constraints, unexpected circumstances, good practice | Follow-up action and support requirements | Deadline | Responsible for follow up |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Supporting service delivery | Satisfactory 74% | -14 % |  |  |  |  |
| 2. Informing strategic decisionmaking | Satisfactory 71% | -4 % |  |  |  |  |
| 3. Planning and implementing cluster strategies | Satisfactory (74%) | -1 % |  |  |  |  |
| 4. Monitoring and evaluating performance | Satisfactory (75%) | 12 % |  |  |  |  |
| 5. Building nat’l capacity in prep. and cont. planning | Needs Improvement (66%) | 3 % |  |  |  |  |
| 6. Supporting robust advocacy | Needs Improvement (61%) | -27 % |  |  |  |  |
| 7. Promoting accountability to affected populations | Satisfactory (74%) | -1 % |  |  |  |  |

Additional comments or information on cluster performance from national partners

- 1/بناء قدرات المنظمات المحلية. 2/تمكين شركاء الكتلة الوطنية بالمتابعة والتقييم ورصد المخالفات للشركاء المنفذين في الكتل الفرعية.  3 / تأهيل وتدريب المنظمات المحلية والتي لم يتسنى لها تنفيذ مشاريعها ودراسة الأسباب . 4/إعادة النظر بشان النازحين والمتضررين في محافظة صعدة جراء القصف والمواجهات في المديريات الحدودية . 5/ التخاطب مع الكتل الفرعية بالتعاون والتنسيق والاهتمام بشركاء الكتلة الوطنية .. ودمتم  مؤسسة روافد اليمن التنموية الاجتماعية الخيرية.  محافظة صعدة

- As for the technical support, the cluster is playing its role effectively, just hope that the cluster is keen on two points we touched on the field. The first point is that the cluster is building the capacity of partners who have projects in the field. We have noticed from our work and field visits that many organizations in the field lack to the standards of humanitarian work besides the technical and administrative weakness in implementing some activities that have specific criteria that should not be compromised. The second point is that the cluster is developing new mechanisms to ensure that all the actors in the shelter sector join the cluster, such as the cluster partners would report any new actors they found in the field or assigning an organization voluntarily to monitor and register all the new actors in the field as we have seen some local agencies were working in the same target areas.   Best Regards.

- Cluster need to assess well the capacities of the local NGOs and try to organize specialized shelter, NFIs and CCCM trainings in light of the identified needs

- I think the Shelter\NFI\CCCM in the best Cluster in Yemen, because it regularly update reports and provide information to the partners.

- I would like to point on the cluster performance in meetings, I find out there is no any support and benefit. We mostly work on indicators, surveys and other documents whereas the most important thing is service provision and implementation where we see no any progress.

- I would like to point out on the Cluster performance in meetings. I find out nothing has progressed in implementation and service provision. The progress is only on the surveys, indicators, reports and other documents where implementation in the field and provision access for NGOs should be one of the clusters main consideration.

- i would like to take this as an opportunity to express our organization appreciation of the shelter/NFI/CCCM cluster's efforts and their organized and updated work.

- No

- No , thank you so much

- No comments, cluster's performance is pretty great

- No comments, the cluster's performance is pretty great

- Organizing workshops on community accountability, complaint mechanism and strategic planning As well as monitoring the performance of civil society organizations during implementation and after implementation,

- Really , we would to Thanks shelter cluster team

- Thank you for your efforts and further excellence

- thank you very much

- thanks

- the important to make capacity building for cluster partner

- The way of Coordinator of National Cluster in treatment local partners in the main cluster meeting is tough and he always has harsh words when talking with them,he does not accept other view points and work with volunteers in different TWG as employees under his department.

- To develope the cluster performance according to the filed need

- الاستعداد للازمات من وقت مبكر بتوفير وتجهيز متطلبات الاستجابة الانسانية مع اشراك المنظمات العاملة بالميدان

- الكتلة تحتاج لى تنمية قدرات الشركاء عشان الجميع يحصلو فرصهم في المجال الانساني

- تأهيل المؤسسات للتاهب لحالات الطوارئ  - تعزيز المسؤلية تجاه السكان النازحين والمتظررين خصوصا في محافظة صعدة فإن فيها حالات متظرره من الحرب ولم يتم النظر لهم وهم على النحو التالي :1/ سكان تحت الخطر لم يتمكنوا من النزوح والخوف من أمامهم ومن خلفهم 2/نازحين لهم أكثر من 9 أشهر إلى مناطق متفرقة  لم يتم استهدافهم حتى الان .  نأمل إعادة النظر والمسوح الميدانية للمتظررين فعلا وتحديث قاعدة البيانات كل شهر .. وكما يجب أن يتم تكليف شركاء الكتله الوطنية بعملية التحقق والمسح والتقييم ومتابعة المنظمات المنقذه للخروج بعمل إنساني شامل ونزيه . ولكم خالص تحياتنا مؤسسة روافد اليمن التنموية صعدة

- هناك العديد من الملاحضات (1-المهمة الاساسية رقم 3 (تخخطيط استراتيجيات الكتلة وتنفيذها:هنك ملاحضة بخصوص التنفيذ حيث لا يسير حسب ماهو مخطط له من حيث الزمان )(2-المهمة الاساسية رقم 5 بنا القدرات (هذه المهمة لاتزال قيد الدراسة والتخطيط

- هناك العديد من الملاحضات : 1- المهمة الاساسية رقم (3)تخطيط استراتيجيات الكتلة وتنفيذها (هناك ملاحضة بخصوص التنفيذ حيث لايسير حسب ماهو مخطط له من حيث الزمان ) 2-المهمة الاساسية رقم(5) بناء القدرات (هذه المهمة لاتزال قيد الدراسة والتخطيط

Additional comments or information on cluster performance from sub-national partners

- I would encourage more field missions from National Cluster leadership. I would also recommend to have more linkage between National Cluster lead with Sub-National Cluster partners. I would further encourage to have a workshop bringing all sub-national cluster leads with National cluster lead to work on SWOT analysis.

- No

- No thank you

- No.

- Shelter/NFIs/CCCM cluster it's the most activate cluster in Yemen, as a national NGO we received many supports from them but they need to improve some points in their performance as I selected above.

- The activities are great, no comments

- The way to work is a lot of professionalism and we wish the team success to reach the best always with our wish to support the emerging local organizations by enabling them to participate within the blocks to gain skill and benefit from the experience

- التحقت مؤخرا بالكتلة، ولا اعرف الكثير عن ادائها.

- الكتلة تحتاج الى مزيد من التطوير واشراك كثير من منظمات المجتمع المحلية وبناء القدرات ...الخ

- عند اختيار الشركاء في تنفيذ المشاريع لايتم اختيار شركاء كانو عامليين معهم بشكل طوعي ونفذو لهم الكثير من الاعمال الخاصه بالدعم النازحين حيث نلاحظ ان هناك تهميش للمؤسسات المحليه الشريكة في الكتله عند اختيار الشركاء كما نريد ان لماذا لايعتمد مخصصات ماليه للمؤسسات المحليه العامله في الميدان والتي ترفع تقارير وبيانات اول باول الى الكتله

- لا

Comments from Cluster Coordinators

- Clusters should practically be responsible for funding projects in order to make partners more considerable towards clusters recommendations and activities.

- I think the Cluster is trying to put beats and pieces together in a progressive manner. Change is a process and not an event. I wouldn't be the best person to evaluate the cluster at this time given that I am still new and trying to catch up. I am happy to do so in future.

- No