## Sheet1
| Global Shelter Cluster | [5 empty] | 16th May 2013 (this document should be updated for every meeting so please date)
ShelterCluster.org
Coordinating Humanitarian Shelter
Working Group on … SHELTER RECOVERY & RECONSTRUCTION
Background (this section needs to outline clearly what the context/background of the issues are or the gaps/needs to which the activities listed below relate. Refer to 2013 Thematic Priorities document)
The objective of this priority area is to improve the way the shelter cluster engages in longer-term sheltering and reconstruction activities. The GSC acknowledges the need to better understand reconstruction processes, stakeholders and technical issues in the early stages of a response to allow for comprehensive and relevant strategy development, planning and implementation of sheltering options. In the last years, the Early Recovery Cluster has decided that all recovery and reconstruction activities should be streamlined through technical clusters. The Early Recovery Cluster will therefore not be activated at a country level as such. Instead, a gap-filling cluster, named after the gap it aims to cover, for instance Capacity Building Cluster or Rule of Law Cluster, might be activated depending on needs and context. As a result, GSC partners feel a working group should be put in place to focus on recovery and reconstruction issues and specifically how they are linked to immediate relief interventions.
Objective
The objective of the working group is to address the key challenges of interconnectedness through different phases of the disaster management cycle. By drawing on past experiences, where early activities of coordination, policy development, technical guidance and support for interventions has led to promote successful shelter recovery and reconstruction, the working group will produce practical / user friendly resources for use by shelter cluster coordination teams and partners. This working group directly contributes to the Global Shelter Cluster Strategy (2013-2017), specifically goal 1.8 - Increased capacity to engage in shelter early recovery activities and a consistent approach to cluster handover and exit strategies.
No. | Priority (High, Medium, Low) | Activity | Output/Result | GSC Strategy Outcome/s (Refer to GSC strategy outcome numbers) | By who (Lead, participants) | For when (Date) | Status (Finished, on-going, to be defined)
1 | High | Define ‘Shelter Recovery and Reconstruction’ to provide scope and clarity to the working group. Including examples of initial activities that support/facilitate recovery and reconstruction efforts. | Endorsed language of the shelter cluster | 3.1 / 3.8 | Esteban, Mike | 2013-06-01 | on-going
2 | Medium | Literature review and case studies of shelter recovery to map out existing resources/guidelines/policy documents – based on the above definition and scope. This mapping will lead to key resources being shared with cluster partners as common tools and examples for predictable, consistent and coherent shelter recovery responses and build foundations for reconstruction processes. | Compilation of: • Key recovery framework • Key guidance and resources • X case studies highlighting successful integration of shelter recovery in emergency programming All documents to be posted on sheltercluster.org resource page. | 1.7 / 3.8 | Mike, Esteban | 2013-07-01 | on-going
3 | High | A policy note will be developed to provide guidance to shelter actors on effective shelter programming (including list of relevant country stakeholders) that addresses and support reconstruction needs and efforts; including the convening of appropriate stakeholders and the specific activities and approaches that can be incorporated into the initial stages of the response. | Draft policy note for feedback | 1.9 / 2.4 | WG | 2013-08-01 | on-going
4 | High | TOR will be developed for transferring the leadership of the cluster beyond emergency. The TOR will at minimum include the two most frequent scenarios: a handover between humanitarian organizations and a handover to national governments. Both situations will address the importance of providing adequate support to national governments to enable a proper transition. Other ‘transfer scenarios’ will also be explored. | TOR with two handover scenarios | 1.8 | Esteban, Mike | 2013-09-01 | on-going
5 | Medium | Review Shelter Recovery Advisors role description and develop a checklist of sheltering and shelter advocacy activities for this position at different stages in a response | Reviewed Shelter Recovery Advisor role description & Checklist; One-page ‘cheat-sheet’, summarizing and highlighting key issues around shelter in recovery and reconstruction (Modeled from the Coherent WG) | 1.1 | Esteban, Mike | 2013-09-01 | on-going
6 | High | A register of agencies supporting with shelter recovery coordinators will be established and joint deployment mechanisms will be strengthened in order to ensure that these coordinators can be deployed early on as part of shelter cluster coordination teams | 3W of agency capacity available at country, regional and global level | 1.2 | Mike, Esteban | 2013-10-01 | on-going
7 | Medium | Advocacy paper on longer term funding needs that allow for better programing and implementing of shelter recovery, released in time to support early recovery and reconstruction activities | Advocacy Paper | 3.2 / 3.3 / 3.8 | Mike, Esteban | 2013-10-01 | on-going
Current Members of the Working Group
| Mike Meaney (HFHI) | mmeaney@habitat.org
| Esteban Leon (UN-Habitat) | leon.unhabitat@unog.ch
| Andy Edwards (ASF) | a.edwards@asf-uk.org
| Anita Vanbreda (WWF) | anita.vanbreda@wwfus.org
| Anna Pont (IFRC) | anna.pont@ifrc.org
| Bill Flinn (CARE) | Flinn@careinternational.org
| Charles Kelly (ProAct Network) | disasterkelly@yahoo.com
| Gabriel Fernandez Del Pino (CARE) | fernandezdelpino@careinternational.org
| Mohamed Hilmi (InterAction) | MHilmi@INTERACTION.ORG
| Sandra D'Urzo (IFRC) | sandra.durzo@ifrc.org
| Theo Schilderman (BSHF) | Theo.Schilderman@bshf.org
| Tom Corsellis (Shelter Centre) | tom@sheltercentre.org
World Bank GFDRR
Hilmi (Inter Action)