Typhoon Haiyan

Shelter and CCCM Combined Cluster Meeting Minutes

Tacloban Co-ordination Hub

22nd Nov

Hub: Tacloban - Overall focus of the meeting was on shelter in region 8, and CCCM in Tacloban city.

Chaired: DSWD/Shelter Cluster Co-ordination (IFRC) / CCCM Coordination (IOM)

Hub: Tacloban - Overall focus of the meeting was on shelter in district 8.

Chaired: DSWD/Shelter Cluster/CCCM Cluster

Attended:  UNDAC, OCHA, Save the Children, Goal, UNHCR, Plan International, Unicef, People in Need, Acted, Oxfam, Samaritan Purse, Medair, WFP, Eastern Visayas Network, IOM, Intersos, World Vision, USAID

## GAPS and OVERLAP

For Tarpauline only

- Coverage (considering completed and planned by all actors) reletively good in Dulag, Mayorga, Tanauan Municipalities. Note this is only based on agencies actually undertaking what they have indicated as planned and at 1 tarp per household

- Significant gaps in all other muncipalites especially:

  - Marabut, Lawaan, Balangiga – but UNHCR and Acted now planning something here

  - Javier

  - Buruan – Samiritans Purse now planning for tarps here as a result of this meeting

  - Municpalities north of Tacloban

  - Giporios,

  - Salcedo

  - Julita - – Samiritans Purse now planning for tarps here as a result of this meeting

  - La Paz

  - Babatngnon – Samiritans Purse now aiming for tarps here.

For Household Repair Kits + conditional Cash – none started, but many actors are planning this for the next stage

For Assistance to Host familes – Only IOM working to assist. Only in Tacloban.

For Engagement with Private section especially Construction Contractors to assist with repair of Schools, and other significant structures such as municiple buildings – issued raised by Brett of WVI. David Dalgado to try to contact Tacloban chamber of commerce via mayors office.

## DSWD and OCHA update

- MIRA completed. Workshop for 3 members per cluster tomorrow 9am OSOC tent area

- DSWD has raised concern that people still require

## Shelter Cluster Detailed Assessment

- Working group to be formed around ACTED for detailed Shelter Cluster Assessment to start after MIRA completes. This group will meet at noon 23rd Nov 2013 (tomorrow).

## Bunkhouses and Temporary relocation sites around Tacloban:

- Agreed to have separate and smaller working group:

Key actions –

UNHCR to ask CHR to visit mayors office

Shelter Cluster Co-ord team to clarify with mayors office if Shelter Aid tents have ever been used before

IOM and Acted to work together to prioritise intention survey at evacuation centres

UNDP to be asked to assist with debris clearance related to these if required

## House repair kit (CGI + package) Working Group:

Save, Medair, Acted, Samiritans Purse, IFRC, Plan  (with some input from CRS via. Save, Goal via Shelter Cluster Co-ordination team) have met to look at house repair kit list, cost, spec.

Some talk about combined procurement, rough estimate that between 750,000 to 1.5 million CGI sheets will be needed by the agencies who are planning to distribute these items (in the Municpalities co-ordinated by the Tacloban hub).

Very draft summary list still to be discussed and confirmed:

|  | Description/Item | Unit | Unit Price [PHP] | Qty / family | Cost/Family [PHP] |  |
| --- | --- | --- | --- | --- | --- | --- |
| Packaging | Canvas Bag for Packing all but CGI sheets | Piece | 60 | 1 | 60 |  |
| Material | CGI Sheet, lenth to be confirmed, minimum 26 gage to international standards, galvanized, painted | Piece | 190 | 20 | 3800 |  |
| Material | Nail (Umbrella), for roof sheets, twisted galvanised, 75mm + watertight washer | Kg | 90 | 3 | 270 |  |
| Material | Nail, iron, for wood, 75mm | Kg | 65 | 1 | 65 |  |
| Material | Nail, iron, for wood, 40mm | Kg | 65 | 1 | 65 |  |
| Material | Tie wire, galvanised, diam. minimum 2.0 mm, roll of 25m | Roll | 120 | 1 | 120 |  |
| Material | Metal Strips, galvanized, 5cmX 30cm | piece | 20 | 10 | 200 |  |
| Material | Vulca seal or equivlent, can of 1 pint (min. 500ml) | piece |  | 10 | 0 |  |
|  |  |  |  | Totals | 4580 | 107.76 |
| Generally Agreed Spec. - For further discussion |  |  |  |  | PHP | USD |
| Optional Tools |  |  |  |  |  |  |
| For HH | 400 - 450 mm hand saw for timber |  |  | 1 |  |  |
|  | claw hammer |  |  | 1 |  |  |
|  | Tin snips |  |  | 1 |  |  |
| For Community | Some spades, hoes, picks, wheelbarrow, level |  |  |  |  |  |
| Optional Cash | up to 4000 PHP | for HH |  |  |  |  |
| per HH |  |  |  |  |  |  |

- Issue raised. Can beneficiaries actually hammer through 26 guage International Standard CGI rather than 26 guage international standard CGI. David Dalgado trying to confirm with IOM who have international standard 26 guage sheets in Tacloban.

- Can anything be procured locally or will all need to be procured internationally.

## Tents

Different people/agencies/government officals saying different things on whether tents are still required or not. Some concern that tents may not be appropriate except for specific interventions, however some agencies reporting requests for tents, some reporting no need.

## DTM

A DTM report has been produced (see attached) highlighting the large numbers of persons leaving typhoon affected areas through Tacloban airport and seaport, Baybay sea port and Ormoc. To better understand the relationship of this movement a short survey was carried out with 270 IDP households from the 3,199 identified by the DTM in various sites across Tacloban to map out separated families and intentions of migration and return. It revealed that only 18% are separated. Those that separated mentioned food security as trauma as the main reasons, and the relatives that left did so via the military flights.

Some figures reported: 18 IDP sites are located in schools, only 33% report having no form of management structure, 74% are located in publicly owned property, the majority of IPDs are living in rooms or classrooms, 31% in makeshift shelters and 2% in tents, the ratio of latrines is1 per 61 persons.

As identified in cluster meetings no issues flagged in the DTM have been addressed so far, the DTM has set up info boards at the entrance of the Sites to display the major gaps per sector on that site.

The DTM team will continue updating the DTM regularly until November 25th as the DSWD assumes its updating.

## Migration Outflow Desk

IOM and protection partners including UNHCR have set up since November 17 the Migration Outflow Desk (MOD) at Tacloban to screen for protection issues, trafficking in persons and other concerns. As of yesterday 1,051 persons were screened. 85% express the intention to live with family in final destination, 46% report no means of income at final destinations, 70% expressed the will to return to Leyte at some point in the future. Major destinations are Manil and the provinces of Cavite, Laguna, Bulacan and Rizal.

Plans underway to expand the MOD at the port of Tacloban were vessels also transport persons out of Tacloban and in Ormoc as well.

## Facilitation of Return Assessments

CCCM, Shelter and Early Recovery cluster partners are implementing a survey to map out households intentions of returning home, the level and type of assistance required. This will help design and provide assistance packages such as debris removal, cash for work, shelter repair kits, sheltering solutions among others, ultimately to determine the residual caseload that will require more targeted solutions.

## Relocation Sites

CCCM, Shelter and Early Recovery Clusters met the City Mayor and Municipal Housing Officer to present the clusters position on relocation and enquire on the relocation strategy of the Municipality.

The clusters perspective is basically to roll out other options of return and housing solutions prior to relocation to sites that are up to 18 km from the city centre. The Mayor expressed their priority being the informal settlers and specifically those located on the barangays along the shore. Their priority caseload is 7.600 households out of the over 36.000 affected families. They aim at starting relocation of idp families currently living along the rod to the airport on barangay 88 and move them into San Jose elementary school on that same Barangay. A field visit will be carried out tomorrow to assess on going debris removal carried out by the Early Cluster and identify solutions other than relocation.

## Useful definitions:

Evacuation Centres: Sites identified by DSWD to evacuate persons at risk that have become temporary sites as Internally Displaced Persons residing in them cannot for the being return home.

Spontaneous Sites:  infrastructure that resisted to the typhoon that people occupied after having lost their homes. Most are collective Centres meaning they are sheltered in existing infrastructure instead of makeshift shelters in vacant plots.

## Humanitarian response webpage:

https://philippines.humanitarianresponse.info/clusters/camp-coordination-management

Next Meeting

Daily CCCM and Shelter meetings will continue to take place jointly in Tacloban at the OSOCC (Grand Stand) next meeting 24th Nov 2pm. Agreed once every 2 days now with TWIGs between.

Early Recovery will follow Shelter & CCCM

Key documents:

Fixing tarps and emergency shelter:

https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/131116%20IEC%20-%20Tarpaulines.pdf

Guidance from Shelter, CCCM, WASH and Protection Clusters - Transitory Tent Sites Guidelines illustrated:

https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/131116%20IEC%20phillipines-Illustrated%20Tent%20Guidelines.pdf

Humanitarian response webpage:

https://philippines.humanitarianresponse.info/clusters/camp-coordination-management

Two IEC on site planning and best practices, build back safer, for reconstruction/repair of transitional or core houses:

https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/131116%20IEC%20-%20SIte%20Planning.pdf

https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/131116%20IEC%20-%20BB%20Safer.pdf

| David Dalgado Technical Coordinator Philippines Shelter Cluster Mob: +63 (0)9289 048 422 Email: tech.phil@sheltercluster.org Web: www.sheltercluster.org | Jean-Philippe Antolin Tacloban Cluster Coordinator Mob +63 0926724 5722 Email Jantolin@iom.int CCCM Tacloban email cccmtacloban@iom.int |
| --- | --- |