Typhoon Haiyan – Eastern Visayas region - Tacloban Co-ordination Hub

Shelter Cluster, CCCM, Early Recovery Cluster Meeting
 27 Nov 2013, 17:00-18.00

Summary Minutes

Agenda

- Introductions

- DSWD updates

- Coordination structure

- Other updates

- Shelter

- CCCM

- ER

- Meetings

- Introductions

- DSWD updates

- Undertaking resurvey of disaster affected. Work in progress but municipalities surveyed to date indicate that figures for houses destroyed and damaged are coming in at 5-8% less than existing DROMIC figures.

- Of municipalities re-surveyed (approx. half) there are as of 27th Nov 92 ECs with 4492 families in these. Please note this is partial picture as survey underway.

- Moves to progress closure of ECs underway. No more info to report at this stage

- Coordination role and structure

- Shelter cluster coordination structure and focal points updates – please see link

- https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/131123%20Shelter%20Cluster%20Philippines%20Hub%20Overview.pdf

- CCCM cluster coordination structure and strategy:

https://philippines.humanitarianresponse.info/clusters/camp-coordination-management

- Region V111, CCCM Lead: DSWD, Ms Pauline Liza C Nahua:

- Region V111, Shelter lead DSWD Lead Virginia Idano (under  review),

| Cluster | TWIG | Lead | Meetings |
| --- | --- | --- | --- |
| Shelter | House/household recovery package | DSWD David Dalgado, IFRC | Thursday and Mondays 5pm @ OSOOC and ODC |
| Shelter | Relief item distribution TBC | TBC | TBC |
| Shelter/ER/ CCCM/WASH | Tacloban recovery and reconstruction | Municipality/ UN Habitat - Irwin | Tbc but likely to start 1st week Dec |
| ER | Debris Recycling, coconut lumber, other material | UNDP | Tbc |
| ER/shelter | Cash for work | Tbc | Tbc |
| CCCM | DTM working group Looking at expanding the reach of DTM in Typhoon affected areas | Joana Dabao (cccmtacloban@iom.int) | Tbc |
| CCCM | Facilitation of Return Early Recovery, Shelter and CCCM cluster members working together to devise the approach. | tbc |  |
| CCCM | Site Management Capacity Building | Marc Maulit, IOM Cccmtacloban@iom.int | Tbc |

TWIGs agreed as above. Please note these are under continuing review

- Other updates

Shelter cluster

Assessment

- Please provide updated  info for3Ws this underpins our capacity assessment analysis

- The sheltercluster will not participate in MIRA 2 (SCT will review the form that the MIRA2 will use) so that shelter cluster can focus on REACH. REACH is starting their Shelter/WASH assessment from 28th Nov.

Ongoing

- We should not be advocating for any procurement or distribution of chainsaws. Due to strict logging laws and risk of illegal logging the government does not want ANY chainsaws being distributed. The salvage of coco lumber will be carried out most likely by FAO, UNDP and ILO.

- Lots of reports of ‘building back worse’ by self-build efforts and some agencies (tbc).

- Cluster advocating for support to recovery – the cluster has asked for 4 million CGI sheets in kind contribution and for hurricane straps – local markets cannot cope with the demand for materials. The cost of 2gga CGI is on average USD 7.

- Discussion in the ICCM of maximising public information, clusters need to maximise resources on this.

- Tents. There is no Govt directive or shelter cluster steer that tent distributions should stop. However tents are relatively expensive and not as versatile as tarps, nails and tools, though they may have a role to play in providing a temporary shelter where communities want to rebuild their houses on the same plot.

- Capacity constraints of skilled technicians/carpenters was highlighted as a concern. CSWD have some trained capacity through their programme. To be investigated more in TWIG meeting on housing recovery package on 28th Nov.

Strategy

- The revised appeal is underway to be launched in Manila and Geneva on 9th. Proposal needs to be sent to Manila or agencies can input directly to the OPS by COB today Wed 28th. Final vetting will take place over the weekend. There will be a HLP TWIG at national level: their first major task will be to investigate issues around no build zones, evictions, relocations, loss of documentation, and security of tenure…. The TWIG will present findings to the ICCM for discussion. Humanitarian agencies in the shelter cluster are highly likely to advocate for minimum number of relocations.

- Wed ICCM in Manila will have a meeting to decide on vulnerability criteria. Considering focus on informal settlements – we estimate the 89% of EC inhabitants are from informal settlements.

- Wed there will be a SAG meeting in Manila chaired by DSWD Assistant Secretary Gudmalin. SAG members are DSWD, NHA, IOM, IFRC; UN-HABITAT, CRS and HFH. We will share the draft strategy and technical guidance.

CCCM cluster

DTM

In coordination with DSWD and the CDD project it was agreed that IOM led DTM carried out at municipality level with MSWD and the Eastern Visayas Network of NGOs will feed the DSWD on going assessment.

By end of the week all municipalities in Leyte Island, Biliran Island and the southern part of Samar Island will be producing DTM to provide a cross sectorial baseline analysis on IDP sites. It targets the Evacuation Centres from the DROMIC reports and adds spontaneous sites that are discovered by the teams. Analysis of DTM will take place next week but information will be released on a daily basis and directly provided to DSWD to allow partners to plan and respond accordingly. Attached is the latest processed data of the municipalities of Tacloban, Palo, SantaFe and Alang Alang. Maps will be produced along with a kmz (google map) for ease of location.

Tomorrows DTM will include the new municipalities (Pastrana, Dagami, Tanauan, Tabon Tabon, Tolosa, Julita, Dulag, Burauen and Babatngon) and information on the DTM from Roxas and Guiuan. CCCM is looking for partners to expand the capacity and reach of DTM to all affected municipalities in the path of Yolanda.

A Technical working group on DTM to expand, analyse, verify and produce targeted reports could not be created as no partner for the exception of ACTED expressed interest. Interested partners are welcomed to approach the CCCM cluster co lead at the OSOOC tent to discuss and plan accordingly.

RAPID INTENTIONS AND NEEDS ASSESSMENT

In coordination with REACH, this survey which was distributed last night, highlights a clear intention of returning to homes via repairing and having access to basic repair kits, framing and economic support. Many IDP households could return and repair their homes if this assistance is made available along with guidance on building resilience, build back better. The Shelter cluster is developing working groups on these issues, and once assistance packages and strategies are devised the facilitation of return aimed at IDP sites can start with the priority ones such as schools.

A working group was proposed to work on facilitation of return to target priority sites under the framework of DSWD strategy to define the priorities, targeting, categorisation of beneficiaries for tailored assistance packages. Its aim is to reduce the number of IDP in sites and consolidate existing sites to improve standards and offer dignified living conditions. At this moment as partners are looking into targeting affected persons with relief items there was no quorum for this working group, IOM will address this issue directly with DSWD and intersted partners are welcome to join in.

BUILDING CAPACITIES FOR SITE MANAGEMENT

As the DTM reveals there are gaps in service provision, referral systems and management of sites. Most issues can be better identified, addressed and solved if proper management exists. Basic site management specifically in those sites were none exists could at least provide information on referral systems, basic monitoring, committee creation to self-manage a site. Partners are urgently sought to assist in capacity building of existing DSWD capacity and expansion to those sites that require it.

Strategy

Interested partners in submitting proposals for cccm activities have to prepare a proposal, the cluster can provide technical guidance and instructions on submission mechanism.

The strategy of the cccm cluster is available at the above mentioned webpage (Humanitarian response).

ER cluster

- On Tacloban recovery and Reconstruction TWIG, UNDP is currently discussing future articulation with UN Habitat and ways to support the municipality.

- Meetings  - going forward

- Next meeting 17.00-18.00hrs Friday 29th Nov in Govt ODC, near to OSOOC in stadium.

- From next week Joint ER/shelter/CCCM meetings will stop. These cluster meeting will then be held back to back as below.

17.00 – 17.30 CCCM

17.30 – 18.00 shelter

18.00 – 18.30 ER

There will be an option to have small breakout conversations post meetings as required in same vicinity.

This will be for first 2 weeks of Dec and reviewed in line with OCHA Inter cluster meetings.

| Richard Luff Co-ordinator – Eastern Visayas Region Philippines Shelter Cluster Mob: +63 (0) 905 440 0048 Email: coord3.phil@sheltercluster.org Web: www.sheltercluster.org | Jean-Philippe Antolin Tacloban CCCM Cluster Coordinator Mob +63 0926724 5722 Email Jantolin@iom.int CCCM Tacloban email cccmtacloban@iom.int |
| --- | --- |

Christophe Charbon

Early recovery Cluster Coordinator Cel + 63 0 905 3070 902

Email Christophe.charbon@undp.org