## Typhoon Haiyan – Eastern Visayas Region VIII

Humanitarian Shelter Working Group (HSWG) meeting

August 7th, 2014

Venue:  Granda Manor Shelter Coordination office, Tacloban City

Present

- HSWG coordination team

Arnaud de Coupigny – Regional coordinator

Farakh Saeed – Information manager

Pablo de Roulet – Information manager

Aradhna Duggal – Communication officer

Attendees:

NHA, DSWD.

ACTED, All Hands Volunteers, Communauteri, Concern inc./CECI, CRS, Food for the Hungry PH, Green Mindanao, Malteser International, Medair, Operation Blessing, Oxfam, Philippines Red Cross UNHCR, World Vision.

AGENDA:

- Shelter Focal Point network in RVIII

- NHA & DSWD

- Humanitarian Shelter Working Group meetings

- General, technical and Information Management updates

- Communication

- Any Other Business

- Shelter Focal Point network in RVIII

The transition period started with the announcement on 4th of July that the humanitarian clusters will be integrated within the Social Services Cluster under DSWD leadership. The Shelter Cluster renamed itself as the Humanitarian Shelter Working Group (HSWG) acting as a secretariat for coordinating the shelter agencies. HSWG will phase out in November and the question is how the shelter agencies will then address their concerns between themselves and to the authorities ? There is time to set up a light, flexible and sustainable shelter coordination mechanism dedicated to link agencies between themselves for exchanging information, raising issues, requesting meetings at the local and regional level with the authorities when necessary after November, but this means a reorganisation of the actual HSWG coordination structure. As the governmental framework and structure will be at the regional and municipal level, it is proposed that a network of Shelter Focal point is set up in Region VIII in order for shelter agencies to coordinate between themselves and link with the authorities at the municipal level.

PHASE 1 : Setting up a Shelter Focal Point network

A Shelter Focal Point is a volunteer taking responsibilities for facilitating information between shelter agencies at the local level. It can be done through: Emails, Informal/Formal – Regular/Ad hoc meetings depending of the needs and the situation of each municipality.

In Region VI, this network of Shelter Focal Points exist already and agencies and authorities know whom to contact in each municipality through a contact list.

The HWRG will send an Excel sheet to all partners in Region VIII in order for them to volunteer (or to refresh the actual list of focal points) for being Shelter Focal Point in their respective municipalities.

PHASE 2 : Shelter Focal Point at the Regional level.

Discussion is opened in order to find the better solution for setting up a representation of shelter agencies at the regional level after the phasing out of HRWG in November. There is two main possibilities :

- One agency act as Focal Point at the regional level.

- A group of agencies act as a secretariat

Options will be discussed during the next RWIII meeting. It should be understood that this is just the beginning of a process that will take weeks and we have the opportunity to set up a flexible and sustainable network.

- National Houses Authority and DSWD

Representatives of NHA presented the role of the Resettlement Cluster. Support will be given directly to the LGU’s and a communication network is already established. Three Yolanda Resettlement Forum are planned (To be confirmed) : in Biliran (26 of August) in Tacloban (28th of August) and in Borongan (2nd of September) with all the mayors and municipal engineers concerned. The HSWG will do a presentation on Build Back Safer in each forum.

NHA has the leadership on Permanent houses and the agencies willing to build permanent houses will have to submit their designs case by case to NHA.

It was asked to the agencies present how many of them are doing or planning to construct permanent houses. The answer is no one except one agency “thinking about it”. The HSWR coordinator raised the question of the necessity for the HSWG to participate to the Resettlement Cluster if no Shelter agencies, or very few, are involved in permanent housing. Shelter agencies, in order to have less confusion in the coordination framework, should follow the leadership of DSWD and contact NHA individually if concerned by NHA mandate, which should be done at the municipal level.

3.Humanitarian Shelter Working Group meetings

There is three meetings in Tacloban:

- Region VIII HSWG (be-weekly)

- Coastal Municipalities (be-weekly)

- Tacloban Shelter meeting (called by City Hall)

The previous day (6th of August) the HSWG had a meeting with the mayor of Tacloban, the summary of outcomes is:

- Shelter assistance can be provided in the now defunct ‘40m no build zone’ on a case by case basis.

- A matrix was agreed to ensure that adequate services will be provided in the transitional and permanent relocation sites. Agreed to have a committee to assess sites seven days prior to any movement of people.

- City Government team is to work directly with shelter agencies and contact details were provided accordingly.

- Regular meetings with the Mayor and his office to happen with shelter agencies who have matters to discuss.

Concerning the last point, the HSWG coordination team will liaise with the City administrator to agree on the next meeting date.

The Coastal municipalities meeting was held on the 8th of August and few agencies attended it. In line with the reorganization of the coordination structure, meetings will be held at the municipal level in the coastal municipalities through shelter focal points, and the former “Coastal Municipalities meeting” will join the HRWG Region VIII meeting held in Tacloban every two weeks.

4. General, technical and Information Management updates

Information Management update:

A presentation was done on mapping by HSWG Information manager. See annex for the maps.

- "DAFAC TAC DAMAGE" : This map shows where are the beneficiaries in Tacloban, the  damage and agency recovery activities (in green). 
- "Map SC meeting" : Number of agencies currently operating in all barangays of RVIII (includes both emergency and recovery)

- "TaclobanBarangays.kmz" : KMZ file of the barangays of the  municipality of Tacloban.(Including some damage data appended to it.) 
It works with Google Earth and will allow you to visualise basic information relating to Tacloban barangays and levels of damage. All data can be visualised by clicking on any polygon.
Note that the information on damage comes from the city of Tacloban and geographic information comes from an earlier digitisation of a paper map. Be aware that all information contained is only indicative and that polygons are likely not to fit exactly with reality (especially outside of city centre). It is just the best we have so far... If you are aware of errors in the file, please let us know. 

The fields "ID" and "PCODE" will not interest you, but categories that you may find useful are "Barangay" numbers "AlterName", recording commonly used other names of these areas, "AreaCity", a classification into larger zones by the municipality, Total and Partial damage numbers of houses, and "DamageSource", the source that provided damage information to the city. The last field "Contains NBZ" specifies whether there are restriction for construction in those areas.

5. Communication

There will be a radio show organized on 19 August to mark the World Humanitarian Day. There is a one hour slot (4 to 5 pm) dedicated to shelter to present who we are and what we do. Suggestion is that the Shelter Cluster coordinates the process and gets a group of a maximum of five to six Waray-Waray speakers. The group should be representative of the government (DSWD), cluster partners (local and international NGOs) and have voices from the community – a community member who has participated in a build back safer training, a carpenter who has received training on building back safer techniques.

Next meeting will be on Wednesday August 20st in HSWG Tacloban office (Granda manor) from 2 to 3:30 PM.