## Summary
HSWG Partner reporting - Recovery activities, Region VII (as of 06/10/14)
This file contains summary data from the latest agency reporting.
Full details of all activities can be found HERE
For explanation of intervention types, please see Recovery guidelines
Is your data missing or shown incorrectly? Please contact the IM team: reporting.phil@sheltercluster.org
1. ACTIVITIES BY LOCATION AND AGENCY
Click to view tables showing the number of households targeted, and reached to date by Intervention type, and by:
| By Municipality |  | By Municipality and then by Agency |  |  |  | By Municipality and Barangay
| By Agency |  | By Agency and then by Municipality |  |  |  | By Municiipality, Barangay and Agency
To view interactive charts showing municipality totals by intervention type (HH reached and HH targeted but not yet reached), click here
2. INTERVENTION SUB-CATEGORIES |  |  |  | This represents ALL targeted activities,not just those that have already been completed.
* SSRS shelter kits are material packages that followed the shelter cluster's initial strategy, valuing up to 10,000 PHP. Minor repairs = P10,000 to P20,000, Major repairs = P20,000 and above
3. SHELTER AND WASH
Partners were asked to indicate whether their programmes cover the provision of latrines, if required, at either the household or communal level, or to identify whether WASH partners were needed.
Most data has been reported without these details, therefore the second graph shows only those activities where a response was provided.
4. ACTIVITY STATUS
Activity status by intervention type. Repairs and retrofit sub-categories are also shown, as the majority of completed activities are within major repair and SSRS kit sub-catgories.
5. Training
Please note that only a limited number of agencies provided information on training during recent data gathering, therefore this is unlikely to represent all training provided
Types of training by agency
Number show the total trained in each category - please note some are individuals, others are households.
Profile of people trained
| Agency |  | Training Topic |  |  |  |  | Barangay Leaders & Comunities | Carpenters/Masons/Foreman | Govt. Technical Professionals | Households | Humanitarian Staff | Not specified | Grand Total
| World Vision |  | TESDA Carpentry training |  |  |  |  | No numbers provided
Grand Total
6. Public Outreach
Please note that only a limited number of agencies provided information on public outreach activities during recent data gathering, therefore this is unlikely to represent all outreach activities
Types of public outreach by agency
Number show the estimated audience/receipients of the activity
| Agency | Type |  |  |  | Estimated audience
| World Vision | IEC Material |  |  |  |  | 50
|  | Unspecified |  |  |  |  | 400
| World Vision Total | [5 empty] | 450
| Grand Total | [5 empty] | 450

## By Mun
Region VII - Recovery Shelter Activities by Municipality - reported by 06/10/14
Region | REGION VII (CENTRAL VISAYAS)
Column Labels
| 2. Temporary Shelter |  | 6. Repairs & Retrofit |  | 7. Core House |  | 8. Permanent House |  | 9. Settlement Planning |  | Total HH Targeted | Total HH Reached
Municipality | HH Targeted | HH Reached | HH Targeted | HH Reached | HH Targeted | HH Reached | HH Targeted | HH Reached | HH Targeted | HH Reached
CEBU | 1276 | 1161 | 21319 | 14551 | 5065 | 711 | 860 | 2 | 50 | 0 | 28570 | 16425
BANTAYAN | 839 | 839 | 3352 | 2622 | 813 | 115 | 90 |  |  |  | 5094 | 3576
CITY OF BOGO | 57 | 57 | 978 | 978 | [6 empty] | 1035 | 1035
DAANBANTAYAN | 50 | 16 | 7065 | 5219 | 292 | 0 | 74 | 2 | 50 | 0 | 7531 | 5237
MADRIDEJOS | 81 | 81 | 736 | 596 | 103 | 6 | 90 |  |  |  | 1010 | 683
MEDELLIN | 42 | 42 | 2383 | 1972 | 40 | 10 |  |  |  |  | 2465 | 2024
PILAR |  |  | 823 | 823 | [6 empty] | 823 | 823
PORO |  |  | 459 | 459 | [6 empty] | 459 | 459
SAN REMIGIO | 185 | 104 | 3304 | 1232 | 1704 | 479 | 300 |  |  |  | 5493 | 1815
SANTA FE | 22 | 22 | 1848 | 569 | 498 | 101 | 306 | 0 |  |  | 2674 | 692
TABOGON |  |  | 40 | [7 empty] | 40
TUDELA |  |  | 81 | 81 | [6 empty] | 81 | 81
(blank) |  |  | 250 |  | 1615 | [5 empty] | 1865
Not yet allocated geographically |  |  |  |  | 369 | [5 empty] | 369
(blank) |  |  |  |  | 369 | [5 empty] | 369
Grand Total | 1276 | 1161 | 21319 | 14551 | 5434 | 711 | 860 | 2 | 50 | 0 | 28939 | 16425

## By Agency
Region VII - Recovery Shelter Activities by Agency - reported by 06/10/14
Region | REGION VII (CENTRAL VISAYAS)
Column Labels
| 2. Temporary Shelter |  | 6. Repairs & Retrofit |  | 7. Core House |  | 8. Permanent House |  | 9. Settlement Planning |  | Total HH targeted | Total HH Reached
Agency | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached
AAR Japan |  |  | 1331 | 1331 | [6 empty] | 1331 | 1331
Citizens' Disaster Response Center |  |  | 250 | 0 | [6 empty] | 250 | 0
Enfants du Mekong |  |  | 363 | 363 | [6 empty] | 363 | 363
Habitat for Humanity |  |  | 5871 | 5871 |  |  | 290 | 2 |  |  | 6161 | 5873
HelpAge-COSE |  |  | 205 | 114 | [6 empty] | 205 | 114
Hilfswerk Austria International | [6 empty] | 300 |  |  |  | 300
IOM |  |  |  |  | 428 | 59 |  |  |  |  | 428 | 59
Islamic Relief Worldwide (IRW) |  |  |  |  | 270 |  | 270 |  |  |  | 540
Landsaid | 85 | 72 | 304 | 275 | [6 empty] | 389 | 347
Lutheran World Relief |  |  | 3151 | 1457 | [6 empty] | 3151 | 1457
Municipality |  |  | 1360 | 1360 | [6 empty] | 1360 | 1360
Muslim Aid |  |  |  |  | 150 | [5 empty] | 150
OM Philippines |  |  | 42 | 2 | 48 | 16 |  |  | 50 | 0 | 140 | 18
Order of Malta |  |  | 150 | 0 | 350 | 95 |  |  |  |  | 500 | 95
PDRRN |  |  | 300 | 300 | [6 empty] | 300 | 300
People in Need (PIN) |  |  | 1000 | [7 empty] | 1000
PFI |  |  | 120 | [7 empty] | 120
PRC - French Red Cross |  |  |  |  | 148 | 0 |  |  |  |  | 148 | 0
PRC - German Red Cross |  |  | 1000 | 445 | 2001 | 121 |  |  |  |  | 3001 | 566
PRC - IFRC |  |  | 3000 | 957 | 1379 | 154 |  |  |  |  | 4379 | 1111
PRC - Japanese Red Cross |  |  | 796 | 0 | 144 | 0 |  |  |  |  | 940 | 0
PRC - Taiwan Red Cross |  |  |  |  | 250 | [5 empty] | 250
RCAC-RRU | 150 | 48 | [8 empty] | 150 | 48
Sign of Hope |  |  |  |  | 266 | 266 |  |  |  |  | 266 | 266
World Vision | 99 | 99 | 1948 | 1948 | [6 empty] | 2047 | 2047
YPDR | 942 | 942 | 128 | 128 | [6 empty] | 1070 | 1070
Grand Total | 1276 | 1161 | 21319 | 14551 | 5434 | 711 | 860 | 2 | 50 | 0 | 28939 | 16425

## By Mun, Agency
Region VII - Recovery Shelter Activities by Municipality, Agency - reported by 06/10/14
Region | REGION VII (CENTRAL VISAYAS)
Column Labels
| 2. Temporary Shelter |  | 6. Repairs & Retrofit |  | 7. Core House |  | 8. Permanent House |  | 9. Settlement Planning |  | Total HH targeted | Total HH Reached
Municipality, Agency | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached
CEBU | 1276 | 1161 | 21319 | 14551 | 5065 | 711 | 860 | 2 | 50 | 0 | 28570 | 16425
BANTAYAN | 839 | 839 | 3352 | 2622 | 813 | 115 | 90 |  |  |  | 5094 | 3576
AAR Japan |  |  | 806 | 806 | [6 empty] | 806 | 806
Habitat for Humanity |  |  | 1258 | 1258 | [6 empty] | 1258 | 1258
HelpAge-COSE |  |  | 3 | 3 | [6 empty] | 3 | 3
Islamic Relief Worldwide (IRW) |  |  |  |  | 150 |  | 90 |  |  |  | 240
Lutheran World Relief |  |  | 565 | [7 empty] | 565
Muslim Aid |  |  |  |  | 130 | [5 empty] | 130
PRC - German Red Cross |  |  | 610 | 445 | 533 | 115 |  |  |  |  | 1143 | 560
YPDR | 839 | 839 | 110 | 110 | [6 empty] | 949 | 949
CITY OF BOGO | 57 | 57 | 978 | 978 | [6 empty] | 1035 | 1035
PDRRN |  |  | 127 | 127 | [6 empty] | 127 | 127
World Vision | 57 | 57 | 851 | 851 | [6 empty] | 908 | 908
DAANBANTAYAN | 50 | 16 | 7065 | 5219 | 292 | 0 | 74 | 2 | 50 | 0 | 7531 | 5237
AAR Japan |  |  | 274 | 274 | [6 empty] | 274 | 274
Habitat for Humanity |  |  | 3488 | 3488 |  |  | 74 | 2 |  |  | 3562 | 3490
Lutheran World Relief |  |  | 1457 | 1457 | [6 empty] | 1457 | 1457
OM Philippines | [8 empty] | 50 | 0 | 50 | 0
People in Need (PIN) |  |  | 1000 | [7 empty] | 1000
PFI |  |  | 50 | [7 empty] | 50
PRC - French Red Cross |  |  |  |  | 148 | 0 |  |  |  |  | 148 | 0
PRC - Japanese Red Cross |  |  | 796 | 0 | 144 | 0 |  |  |  |  | 940 | 0
RCAC-RRU | 50 | 16 | [8 empty] | 50 | 16
MADRIDEJOS | 81 | 81 | 736 | 596 | 103 | 6 | 90 |  |  |  | 1010 | 683
Enfants du Mekong |  |  | 150 | 150 | [6 empty] | 150 | 150
Habitat for Humanity |  |  | 431 | 431 | [6 empty] | 431 | 431
Islamic Relief Worldwide (IRW) | [6 empty] | 90 |  |  |  | 90
PRC - German Red Cross |  |  | 140 | 0 | 103 | 6 |  |  |  |  | 243 | 6
YPDR | 81 | 81 | 15 | 15 | [6 empty] | 96 | 96
MEDELLIN | 42 | 42 | 2383 | 1972 | 40 | 10 |  |  |  |  | 2465 | 2024
AAR Japan |  |  | 251 | 251 | [6 empty] | 251 | 251
Citizens' Disaster Response Center |  |  | 250 | 0 | [6 empty] | 250 | 0
Enfants du Mekong |  |  | 210 | 210 | [6 empty] | 210 | 210
Habitat for Humanity |  |  | 130 | 130 | [6 empty] | 130 | 130
HelpAge-COSE |  |  | 202 | 111 | [6 empty] | 202 | 111
OM Philippines |  |  | 40 | 0 | 40 | 10 |  |  |  |  | 80 | 10
PDRRN |  |  | 173 | 173 | [6 empty] | 173 | 173
PFI |  |  | 30 | [7 empty] | 30
World Vision | 42 | 42 | 1097 | 1097 | [6 empty] | 1139 | 1139
PILAR |  |  | 823 | 823 | [6 empty] | 823 | 823
Municipality |  |  | 823 | 823 | [6 empty] | 823 | 823
PORO |  |  | 459 | 459 | [6 empty] | 459 | 459
Enfants du Mekong |  |  | 3 | 3 | [6 empty] | 3 | 3
Municipality |  |  | 456 | 456 | [6 empty] | 456 | 456
SAN REMIGIO | 185 | 104 | 3304 | 1232 | 1704 | 479 | 300 |  |  |  | 5493 | 1815
Hilfswerk Austria International | [6 empty] | 300 |  |  |  | 300
IOM |  |  |  |  | 59 | 59 |  |  |  |  | 59 | 59
Landsaid | 85 | 72 | 304 | 275 | [6 empty] | 389 | 347
PRC - IFRC |  |  | 3000 | 957 | 1379 | 154 |  |  |  |  | 4379 | 1111
RCAC-RRU | 100 | 32 | [8 empty] | 100 | 32
Sign of Hope |  |  |  |  | 266 | 266 |  |  |  |  | 266 | 266
SANTA FE | 22 | 22 | 1848 | 569 | 498 | 101 | 306 | 0 |  |  | 2674 | 692
Habitat for Humanity |  |  | 564 | 564 |  |  | 216 | 0 |  |  | 780 | 564
Islamic Relief Worldwide (IRW) |  |  |  |  | 120 |  | 90 |  |  |  | 210
Lutheran World Relief |  |  | 1129 | [7 empty] | 1129
Muslim Aid |  |  |  |  | 20 | [5 empty] | 20
OM Philippines |  |  | 2 | 2 | 8 | 6 |  |  |  |  | 10 | 8
Order of Malta |  |  | 150 | 0 | 350 | 95 |  |  |  |  | 500 | 95
YPDR | 22 | 22 | 3 | 3 | [6 empty] | 25 | 25
TABOGON |  |  | 40 | [7 empty] | 40
PFI |  |  | 40 | [7 empty] | 40
TUDELA |  |  | 81 | 81 | [6 empty] | 81 | 81
Municipality |  |  | 81 | 81 | [6 empty] | 81 | 81
(blank) |  |  | 250 |  | 1615 | [5 empty] | 1865
PRC - German Red Cross |  |  | 250 |  | 1365 | [5 empty] | 1615
PRC - Taiwan Red Cross |  |  |  |  | 250 | [5 empty] | 250
(blank) |  |  |  |  | 369 | [5 empty] | 369
(blank) |  |  |  |  | 369 | [5 empty] | 369
IOM |  |  |  |  | 369 | [5 empty] | 369
Grand Total | 1276 | 1161 | 21319 | 14551 | 5434 | 711 | 860 | 2 | 50 | 0 | 28939 | 16425

## By Agency, Mun
Region VII - Recovery Shelter Activities by Agency, Municipality - reported by 27/09/14
Region | REGION VII (CENTRAL VISAYAS)
Column Labels
| 2. Temporary Shelter |  | 6. Repairs & Retrofit |  | 7. Core House |  | 8. Permanent House |  | 9. Settlement Planning |  | Total HH targeted | Total HH Reached
Agency, Municipality | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached
AAR Japan
BANTAYAN |  |  | 806 | 806 | [6 empty] | 806 | 806
DAANBANTAYAN |  |  | 274 | 274 | [6 empty] | 274 | 274
MEDELLIN |  |  | 251 | 251 | [6 empty] | 251 | 251
Citizens' Disaster Response Center
MEDELLIN |  |  | 250 | 0 | [6 empty] | 250 | 0
Enfants du Mekong
MADRIDEJOS |  |  | 150 | 150 | [6 empty] | 150 | 150
MEDELLIN |  |  | 210 | 210 | [6 empty] | 210 | 210
PORO |  |  | 3 | 3 | [6 empty] | 3 | 3
Habitat for Humanity
BANTAYAN |  |  | 1258 | 1258 | [6 empty] | 1258 | 1258
DAANBANTAYAN |  |  | 3488 | 3488 |  |  | 74 | 2 |  |  | 3562 | 3490
MADRIDEJOS |  |  | 431 | 431 | [6 empty] | 431 | 431
MEDELLIN |  |  | 130 | 130 | [6 empty] | 130 | 130
SANTA FE |  |  | 564 | 564 |  |  | 216 | 0 |  |  | 780 | 564
HelpAge-COSE
BANTAYAN |  |  | 3 | 3 | [6 empty] | 3 | 3
MEDELLIN |  |  | 202 | 111 | [6 empty] | 202 | 111
Hilfswerk Austria International
SAN REMIGIO | [6 empty] | 300 |  |  |  | 300
IOM
SAN REMIGIO |  |  |  |  | 59 | 59 |  |  |  |  | 59 | 59
(blank) |  |  |  |  | 369 | [5 empty] | 369
Islamic Relief Worldwide (IRW)
BANTAYAN |  |  |  |  | 150 |  | 90 |  |  |  | 240
MADRIDEJOS | [6 empty] | 90 |  |  |  | 90
SANTA FE |  |  |  |  | 120 |  | 90 |  |  |  | 210
Landsaid
SAN REMIGIO | 85 | 72 | 304 | 275 | [6 empty] | 389 | 347
Lutheran World Relief
BANTAYAN |  |  | 565 | [7 empty] | 565
DAANBANTAYAN |  |  | 1457 | 1457 | [6 empty] | 1457 | 1457
SANTA FE |  |  | 1129 | [7 empty] | 1129
Municipality
PILAR |  |  | 823 | 823 | [6 empty] | 823 | 823
PORO |  |  | 456 | 456 | [6 empty] | 456 | 456
TUDELA |  |  | 81 | 81 | [6 empty] | 81 | 81
Muslim Aid
BANTAYAN |  |  |  |  | 130 | [5 empty] | 130
SANTA FE |  |  |  |  | 20 | [5 empty] | 20
OM Philippines
DAANBANTAYAN | [8 empty] | 50 | 0 | 50 | 0
MEDELLIN |  |  | 40 | 0 | 40 | 10 |  |  |  |  | 80 | 10
SANTA FE |  |  | 2 | 2 | 8 | 6 |  |  |  |  | 10 | 8
Order of Malta
SANTA FE |  |  | 150 | 0 | 350 | 95 |  |  |  |  | 500 | 95
PDRRN
CITY OF BOGO |  |  | 127 | 127 | [6 empty] | 127 | 127
MEDELLIN |  |  | 173 | 173 | [6 empty] | 173 | 173
People in Need (PIN)
DAANBANTAYAN |  |  | 1000 | [7 empty] | 1000
PFI
DAANBANTAYAN |  |  | 50 | [7 empty] | 50
MEDELLIN |  |  | 30 | [7 empty] | 30
TABOGON |  |  | 40 | [7 empty] | 40
PRC - French Red Cross
DAANBANTAYAN |  |  |  |  | 148 | 0 |  |  |  |  | 148 | 0
PRC - German Red Cross
BANTAYAN |  |  | 610 | 445 | 533 | 115 |  |  |  |  | 1143 | 560
MADRIDEJOS |  |  | 140 | 0 | 103 | 6 |  |  |  |  | 243 | 6
(blank) |  |  | 250 |  | 1365 | [5 empty] | 1615
PRC - IFRC
SAN REMIGIO |  |  | 3000 | 957 | 1379 | 154 |  |  |  |  | 4379 | 1111
PRC - Japanese Red Cross
DAANBANTAYAN |  |  | 796 | 0 | 144 | 0 |  |  |  |  | 940 | 0
PRC - Taiwan Red Cross
(blank) |  |  |  |  | 250 | [5 empty] | 250
RCAC-RRU
DAANBANTAYAN | 50 | 16 | [8 empty] | 50 | 16
SAN REMIGIO | 100 | 32 | [8 empty] | 100 | 32
Sign of Hope
SAN REMIGIO |  |  |  |  | 266 | 266 |  |  |  |  | 266 | 266
World Vision
CITY OF BOGO | 57 | 57 | 851 | 851 | [6 empty] | 908 | 908
MEDELLIN | 42 | 42 | 1097 | 1097 | [6 empty] | 1139 | 1139
YPDR
BANTAYAN | 839 | 839 | 110 | 110 | [6 empty] | 949 | 949
MADRIDEJOS | 81 | 81 | 15 | 15 | [6 empty] | 96 | 96
SANTA FE | 22 | 22 | 3 | 3 | [6 empty] | 25 | 25
Grand Total | 1276 | 1161 | 21319 | 14551 | 5434 | 711 | 860 | 2 | 50 | 0 | 28939 | 16425

## By Mun, Bgy
Region VII - Recovery Shelter Activities by Municipality, Barangay - reported by 06/10/14
Region | REGION VII (CENTRAL VISAYAS)
Column Labels
| 2. Temporary Shelter |  | 6. Repairs & Retrofit |  | 7. Core House |  | 8. Permanent House |  | 9. Settlement Planning |  | Total HH targeted | Total HH Reached
Municipality, Barangay | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached
CEBU | 1276 | 1161 | 21319 | 14551 | 5065 | 711 | 860 | 2 | 50 | 0 | 28570 | 16425
BANTAYAN | 839 | 839 | 3352 | 2622 | 813 | 115 | 90 |  |  |  | 5094 | 3576
ATOP-ATOP |  |  | 184 | 184 | 168 | 34 |  |  |  |  | 352 | 218
BAIGAD | 123 | 123 | 49 | 49 | [6 empty] | 172 | 172
BANTIGUE (POB.) |  |  | 78 | 78 | [6 empty] | 78 | 78
BAOD |  |  | 160 | 100 | 101 | 22 |  |  |  |  | 261 | 122
BINAOBAO (POB.) |  |  | 48 | 48 | [6 empty] | 48 | 48
BOTIGUES |  |  | 42 | 42 | [6 empty] | 42 | 42
GUIWANON |  |  | 126 | 82 | 110 | 22 |  |  |  |  | 236 | 104
HILOTONGAN |  |  | 101 | 101 | [6 empty] | 101 | 101
KABAC |  |  | 23 | 23 | 30 | [5 empty] | 53 | 23
KABANGBANG | 158 | 158 | 15 | 15 | [6 empty] | 173 | 173
KAMPINGGANON |  |  | 6 | 6 | [6 empty] | 6 | 6
KANGKAIBE | 89 | 89 | 382 | 379 | 65 | 26 |  |  |  |  | 536 | 494
LIPAYRAN |  |  | 126 | 126 | [6 empty] | 126 | 126
MOJON |  |  | 295 | 237 | 88 | 10 |  |  |  |  | 383 | 247
OBO-OB |  |  | 829 | 264 | [6 empty] | 829 | 264
PATAO |  |  | 49 | 49 | 44 | [5 empty] | 93 | 49
PUTIAN |  |  | 11 | 11 | [6 empty] | 11 | 11
SILLON | 119 | 119 | 348 | 348 | 76 | [5 empty] | 543 | 467
SUBA (POB.) | 121 | 121 | 29 | 29 | [6 empty] | 150 | 150
SULANGAN |  |  | 60 | 60 | 130 | [5 empty] | 190 | 60
SUNGKO | 194 | 194 | 42 | 42 | [6 empty] | 236 | 236
TAMIAO |  |  | 259 | 259 | [6 empty] | 259 | 259
TICAD (POB.) |  |  | 90 | 90 | 1 | 1 |  |  |  |  | 91 | 91
(blank) | 35 | 35 |  |  |  |  | 90 |  |  |  | 125 | 35
CITY OF BOGO | 57 | 57 | 978 | 978 | [6 empty] | 1035 | 1035
ANONANG SUR | 10 | 10 | 267 | 267 | [6 empty] | 277 | 277
CAYANG | 14 | 14 | 307 | 307 | [6 empty] | 321 | 321
GUADALUPE | 19 | 19 | 260 | 260 | [6 empty] | 279 | 279
SIOCON | 14 | 14 | 144 | 144 | [6 empty] | 158 | 158
DAANBANTAYAN | 50 | 16 | 7065 | 5219 | 292 | 0 | 74 | 2 | 50 | 0 | 7531 | 5237
AGUHO | 50 | 16 | 18 | 8 |  |  | 74 | 2 |  |  | 142 | 26
BAKHAWAN |  |  | 10 | 10 | [6 empty] | 10 | 10
BATERIA |  |  | 150 | 15 | 27 | 0 |  |  |  |  | 177 | 15
BITOON |  |  | 159 | 30 | 29 | 0 |  |  |  |  | 188 | 30
CALAPE |  |  | 216 | 26 | 26 | 0 |  |  |  |  | 242 | 26
CARNAZA |  |  | 13 | 13 | [6 empty] | 13 | 13
LANAO |  |  | 577 | 305 | 51 | 0 |  |  |  |  | 628 | 305
LOGON |  |  | 21 | 21 | [6 empty] | 21 | 21
MALBAGO |  |  | 17 | 17 | [6 empty] | 17 | 17
MALINGIN |  |  | 85 | 5 | 11 | 0 |  |  |  |  | 96 | 5
MAYA |  |  | 2950 | 2940 |  |  |  |  | 50 | 0 | 3000 | 2940
PAYPAY |  |  | 33 | 23 | 148 | 0 |  |  |  |  | 181 | 23
TALISAY |  |  | 923 | 923 | [6 empty] | 923 | 923
TAPILON |  |  | 846 | 846 | [6 empty] | 846 | 846
TINUBDAN |  |  | 14 | 14 | [6 empty] | 14 | 14
TOMINJAO |  |  | 23 | 23 | [6 empty] | 23 | 23
(blank) |  |  | 1010 | [7 empty] | 1010
MADRIDEJOS | 81 | 81 | 736 | 596 | 103 | 6 | 90 |  |  |  | 1010 | 683
BUNAKAN | 81 | 81 | 15 | 15 | [6 empty] | 96 | 96
PILI |  |  | 431 | 431 | [6 empty] | 431 | 431
TALANGNAN |  |  | 150 | 150 | [6 empty] | 150 | 150
TARONG |  |  | 140 | 0 | 103 | 6 |  |  |  |  | 243 | 6
(blank) | [6 empty] | 90 |  |  |  | 90
MEDELLIN | 42 | 42 | 2383 | 1972 | 40 | 10 |  |  |  |  | 2465 | 2024
ANTIPOLO |  |  | 39 | 29 | [6 empty] | 39 | 29
CAPUTATAN NORTE | 13 | 13 | 442 | 442 | [6 empty] | 455 | 455
CAPUTATAN SUR | 6 | 6 | 188 | 188 | [6 empty] | 194 | 194
CURVA |  |  | 29 | 19 | [6 empty] | 29 | 19
DAANLUNGSOD |  |  | 281 | 230 | [6 empty] | 281 | 230
DALINGDING SUR | 4 | 4 | 289 | 289 | [6 empty] | 293 | 293
DAYHAGON |  |  | 21 | 21 | [6 empty] | 21 | 21
DON VIRGILIO GONZALES |  |  | 8 | 8 | [6 empty] | 8 | 8
GIBITNGIL | 13 | 13 | 353 | 190 | [6 empty] | 366 | 203
KAWIT |  |  | 157 | 70 | [6 empty] | 157 | 70
LAMINTAK NORTE |  |  | 9 | 9 | [6 empty] | 9 | 9
Lamintak Sur |  |  | 36 | 36 | [6 empty] | 36 | 36
Luy-a |  |  | 4 | 4 | [6 empty] | 4 | 4
MAHARUHAY |  |  | 90 | 40 | [6 empty] | 90 | 40
MAHAWAK |  |  | 22 | 22 | [6 empty] | 22 | 22
PANUGNAWAN | 6 | 6 | 223 | 223 | [6 empty] | 229 | 229
POBLACION |  |  | 33 | 13 | 20 | 0 |  |  |  |  | 53 | 13
TINDOG |  |  | 29 | 9 | 20 | 10 |  |  |  |  | 49 | 19
(blank) |  |  | 130 | 130 | [6 empty] | 130 | 130
PILAR |  |  | 823 | 823 | [6 empty] | 823 | 823
(blank) |  |  | 823 | 823 | [6 empty] | 823 | 823
PORO |  |  | 459 | 459 | [6 empty] | 459 | 459
(blank) |  |  | 459 | 459 | [6 empty] | 459 | 459
SAN REMIGIO | 185 | 104 | 3304 | 1232 | 1704 | 479 | 300 |  |  |  | 5493 | 1815
ANAPOG |  |  | 122 | 16 | 155 | 91 |  |  |  |  | 277 | 107
ARGAWANON |  |  | 250 | 240 | 137 | 0 |  |  |  |  | 387 | 240
BAGTIC |  |  | 98 | 17 | 21 | 0 |  |  |  |  | 119 | 17
BANCASAN |  |  | 87 | 16 | 55 | 0 |  |  |  |  | 142 | 16
BATAD |  |  | 114 | 16 | 63 | 0 |  |  |  |  | 177 | 16
BUSOGON |  |  | 69 | 18 | 103 | 32 |  |  |  |  | 172 | 50
CALAMBUA |  |  | 124 | 18 | 35 | 0 |  |  |  |  | 159 | 18
CANAGAHAN |  |  | 183 | 145 | 36 | 0 |  |  |  |  | 219 | 145
DAPDAP |  |  | 112 | 37 | 41 | 0 |  |  |  |  | 153 | 37
GAWAYGAWAY |  |  | 148 | 0 | 50 | 0 |  |  |  |  | 198 | 0
HAGNAYA | 50 | 16 | 82 | 16 | 60 | 0 |  |  |  |  | 192 | 32
KAYAM | 25 | 12 | 84 | 20 | 44 | 0 |  |  |  |  | 153 | 32
KINAWAHAN |  |  | 111 | 0 | 7 | 0 |  |  |  |  | 118 | 0
LAMBUSAN |  |  | 155 | 24 | 82 | 0 |  |  |  |  | 237 | 24
Lawis |  |  | 79 | 17 | 92 | 63 |  |  |  |  | 171 | 80
LIBAONG |  |  | 128 | 56 | 65 | 19 |  |  |  |  | 193 | 75
Looc |  |  | 77 | 17 | 66 | 62 |  |  |  |  | 143 | 79
LUYANG |  |  | 106 | 17 | 27 | 0 |  |  |  |  | 133 | 17
MANO | 60 | 60 | 334 | 287 | 28 | 0 | 300 |  |  |  | 722 | 347
POBLACION |  |  | 87 | 18 | 72 | 59 |  |  |  |  | 159 | 77
PUNTA |  |  | 73 | 73 | 54 | 29 |  |  |  |  | 127 | 102
SAB-A |  |  | 132 | 15 | 22 | 0 |  |  |  |  | 154 | 15
SAN MIGUEL |  |  | 180 | 13 | 47 | 0 |  |  |  |  | 227 | 13
TACUP | 50 | 16 | 75 | 17 | 84 | 0 |  |  |  |  | 209 | 33
TAMBONGON |  |  | 127 | 20 | 188 | 124 |  |  |  |  | 315 | 144
TO-ONG |  |  | 78 | 18 | 33 | 0 |  |  |  |  | 111 | 18
Victoria |  |  | 89 | 81 | 37 | 0 |  |  |  |  | 126 | 81
SANTA FE | 22 | 22 | 1848 | 569 | 498 | 101 | 306 | 0 |  |  | 2674 | 692
BALIDBID | 3 | 3 | 163 | 163 | [6 empty] | 166 | 166
KINATARKAN |  |  | 2 | 2 | 8 | 6 |  |  |  |  | 10 | 8
MARICABAN | 1 | 1 | 301 | 301 |  |  | 216 | 0 |  |  | 518 | 302
OKOY |  |  | 75 | 0 | 250 | 94 |  |  |  |  | 325 | 94
POBLACION | 4 | 4 | 100 | 100 | 17 | [5 empty] | 121 | 104
POOC | 9 | 9 | 1132 | 3 | 77 | [5 empty] | 1218 | 12
TALISAY | 5 | 5 | 75 | 0 | 146 | 1 |  |  |  |  | 226 | 6
(blank) | [6 empty] | 90 |  |  |  | 90
TABOGON |  |  | 40 | [7 empty] | 40
LIBJO |  |  | 10 | [7 empty] | 10
MUABOG |  |  | 10 | [7 empty] | 10
SALAG |  |  | 10 | [7 empty] | 10
SOMOSA |  |  | 10 | [7 empty] | 10
TUDELA |  |  | 81 | 81 | [6 empty] | 81 | 81
(blank) |  |  | 81 | 81 | [6 empty] | 81 | 81
(blank) |  |  | 250 |  | 1615 | [5 empty] | 1865
(blank) |  |  | 250 |  | 1615 | [5 empty] | 1865
(blank) |  |  |  |  | 369 | [5 empty] | 369
(blank) |  |  |  |  | 369 | [5 empty] | 369
(blank) |  |  |  |  | 369 | [5 empty] | 369
Grand Total | 1276 | 1161 | 21319 | 14551 | 5434 | 711 | 860 | 2 | 50 | 0 | 28939 | 16425

## By Mun, Bgy, Agency
Region VII - Recovery Shelter Activities by Municipality, Barangay, Agency - reported by 06/10/14
Region | REGION VII (CENTRAL VISAYAS)
Activity Type
| 2. Temporary Shelter |  | 6. Repairs & Retrofit |  | 7. Core House |  | 8. Permanent House |  | 9. Settlement Planning |  | Total HH targeted | Total HH Reached
Municipality, Barangay, Agency | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached | HH targeted | HH Reached
CEBU | 1276 | 1161 | 21319 | 14551 | 5065 | 711 | 860 | 2 | 50 | 0 | 28570 | 16425
BANTAYAN | 839 | 839 | 3352 | 2622 | 813 | 115 | 90 |  |  |  | 5094 | 3576
ATOP-ATOP |  |  | 184 | 184 | 168 | 34 |  |  |  |  | 352 | 218
AAR Japan |  |  | 27 | 27 | [6 empty] | 27 | 27
Habitat for Humanity |  |  | 18 | 18 | [6 empty] | 18 | 18
PRC - German Red Cross |  |  | 139 | 139 | 168 | 34 |  |  |  |  | 307 | 173
BAIGAD | 123 | 123 | 49 | 49 | [6 empty] | 172 | 172
YPDR | 123 | 123 | 49 | 49 | [6 empty] | 172 | 172
BANTIGUE (POB.) |  |  | 78 | 78 | [6 empty] | 78 | 78
AAR Japan |  |  | 78 | 78 | [6 empty] | 78 | 78
BAOD |  |  | 160 | 100 | 101 | 22 |  |  |  |  | 261 | 122
AAR Japan |  |  | 19 | 19 | [6 empty] | 19 | 19
PRC - German Red Cross |  |  | 141 | 81 | 101 | 22 |  |  |  |  | 242 | 103
BINAOBAO (POB.) |  |  | 48 | 48 | [6 empty] | 48 | 48
AAR Japan |  |  | 48 | 48 | [6 empty] | 48 | 48
BOTIGUES |  |  | 42 | 42 | [6 empty] | 42 | 42
AAR Japan |  |  | 42 | 42 | [6 empty] | 42 | 42
GUIWANON |  |  | 126 | 82 | 110 | 22 |  |  |  |  | 236 | 104
AAR Japan |  |  | 21 | 21 | [6 empty] | 21 | 21
PRC - German Red Cross |  |  | 105 | 61 | 110 | 22 |  |  |  |  | 215 | 83
HILOTONGAN |  |  | 101 | 101 | [6 empty] | 101 | 101
AAR Japan |  |  | 98 | 98 | [6 empty] | 98 | 98
HelpAge-COSE |  |  | 3 | 3 | [6 empty] | 3 | 3
KABAC |  |  | 23 | 23 | 30 | [5 empty] | 53 | 23
AAR Japan |  |  | 23 | 23 | [6 empty] | 23 | 23
Islamic Relief Worldwide (IRW) |  |  |  |  | 30 | [5 empty] | 30
KABANGBANG | 158 | 158 | 15 | 15 | [6 empty] | 173 | 173
AAR Japan |  |  | 15 | 15 | [6 empty] | 15 | 15
YPDR | 158 | 158 | [8 empty] | 158 | 158
KAMPINGGANON |  |  | 6 | 6 | [6 empty] | 6 | 6
AAR Japan |  |  | 6 | 6 | [6 empty] | 6 | 6
KANGKAIBE | 89 | 89 | 382 | 379 | 65 | 26 |  |  |  |  | 536 | 494
AAR Japan |  |  | 23 | 23 | [6 empty] | 23 | 23
Habitat for Humanity |  |  | 182 | 182 | [6 empty] | 182 | 182
YPDR | 89 | 89 | 10 | 10 | [6 empty] | 99 | 99
PRC - German Red Cross |  |  | 167 | 164 | 65 | 26 |  |  |  |  | 232 | 190
LIPAYRAN |  |  | 126 | 126 | [6 empty] | 126 | 126
AAR Japan |  |  | 126 | 126 | [6 empty] | 126 | 126
MOJON |  |  | 295 | 237 | 88 | 10 |  |  |  |  | 383 | 247
AAR Japan |  |  | 14 | 14 | [6 empty] | 14 | 14
Habitat for Humanity |  |  | 223 | 223 | [6 empty] | 223 | 223
PRC - German Red Cross |  |  | 58 | 0 | 88 | 10 |  |  |  |  | 146 | 10
OBO-OB |  |  | 829 | 264 | [6 empty] | 829 | 264
AAR Japan |  |  | 14 | 14 | [6 empty] | 14 | 14
Habitat for Humanity |  |  | 250 | 250 | [6 empty] | 250 | 250
Lutheran World Relief |  |  | 565 | [7 empty] | 565
PATAO |  |  | 49 | 49 | 44 | [5 empty] | 93 | 49
AAR Japan |  |  | 49 | 49 | [6 empty] | 49 | 49
Islamic Relief Worldwide (IRW) |  |  |  |  | 44 | [5 empty] | 44
PUTIAN |  |  | 11 | 11 | [6 empty] | 11 | 11
AAR Japan |  |  | 11 | 11 | [6 empty] | 11 | 11
SILLON | 119 | 119 | 348 | 348 | 76 | [5 empty] | 543 | 467
Habitat for Humanity |  |  | 326 | 326 | [6 empty] | 326 | 326
Islamic Relief Worldwide (IRW) |  |  |  |  | 76 | [5 empty] | 76
YPDR | 119 | 119 | 22 | 22 | [6 empty] | 141 | 141
SUBA (POB.) | 121 | 121 | 29 | 29 | [6 empty] | 150 | 150
AAR Japan |  |  | 29 | 29 | [6 empty] | 29 | 29
YPDR | 121 | 121 | [8 empty] | 121 | 121
SULANGAN |  |  | 60 | 60 | 130 | [5 empty] | 190 | 60
AAR Japan |  |  | 60 | 60 | [6 empty] | 60 | 60
Muslim Aid |  |  |  |  | 130 | [5 empty] | 130
SUNGKO | 194 | 194 | 42 | 42 | [6 empty] | 236 | 236
AAR Japan |  |  | 13 | 13 | [6 empty] | 13 | 13
YPDR | 194 | 194 | 29 | 29 | [6 empty] | 223 | 223
TAMIAO |  |  | 259 | 259 | [6 empty] | 259 | 259
Habitat for Humanity |  |  | 259 | 259 | [6 empty] | 259 | 259
TICAD (POB.) |  |  | 90 | 90 | 1 | 1 |  |  |  |  | 91 | 91
AAR Japan |  |  | 90 | 90 | [6 empty] | 90 | 90
PRC - German Red Cross |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1
(blank) | 35 | 35 |  |  |  |  | 90 |  |  |  | 125 | 35
Islamic Relief Worldwide (IRW) | [6 empty] | 90 |  |  |  | 90
YPDR | 35 | 35 | [8 empty] | 35 | 35
CITY OF BOGO | 57 | 57 | 978 | 978 | [6 empty] | 1035 | 1035
ANONANG SUR | 10 | 10 | 267 | 267 | [6 empty] | 277 | 277
PDRRN |  |  | 127 | 127 | [6 empty] | 127 | 127
World Vision | 10 | 10 | 140 | 140 | [6 empty] | 150 | 150
CAYANG | 14 | 14 | 307 | 307 | [6 empty] | 321 | 321
World Vision | 14 | 14 | 307 | 307 | [6 empty] | 321 | 321
GUADALUPE | 19 | 19 | 260 | 260 | [6 empty] | 279 | 279
World Vision | 19 | 19 | 260 | 260 | [6 empty] | 279 | 279
SIOCON | 14 | 14 | 144 | 144 | [6 empty] | 158 | 158
World Vision | 14 | 14 | 144 | 144 | [6 empty] | 158 | 158
DAANBANTAYAN | 50 | 16 | 7065 | 5219 | 292 | 0 | 74 | 2 | 50 | 0 | 7531 | 5237
AGUHO | 50 | 16 | 18 | 8 |  |  | 74 | 2 |  |  | 142 | 26
AAR Japan |  |  | 8 | 8 | [6 empty] | 8 | 8
Habitat for Humanity | [6 empty] | 74 | 2 |  |  | 74 | 2
PFI |  |  | 10 | [7 empty] | 10
RCAC-RRU | 50 | 16 | [8 empty] | 50 | 16
BAKHAWAN |  |  | 10 | 10 | [6 empty] | 10 | 10
AAR Japan |  |  | 10 | 10 | [6 empty] | 10 | 10
BATERIA |  |  | 150 | 15 | 27 | 0 |  |  |  |  | 177 | 15
AAR Japan |  |  | 15 | 15 | [6 empty] | 15 | 15
PRC - Japanese Red Cross |  |  | 135 | 0 | 27 | 0 |  |  |  |  | 162 | 0
BITOON |  |  | 159 | 30 | 29 | 0 |  |  |  |  | 188 | 30
AAR Japan |  |  | 30 | 30 | [6 empty] | 30 | 30
PFI |  |  | 10 | [7 empty] | 10
PRC - Japanese Red Cross |  |  | 119 | 0 | 29 | 0 |  |  |  |  | 148 | 0
CALAPE |  |  | 216 | 26 | 26 | 0 |  |  |  |  | 242 | 26
AAR Japan |  |  | 26 | 26 | [6 empty] | 26 | 26
PRC - Japanese Red Cross |  |  | 190 | 0 | 26 | 0 |  |  |  |  | 216 | 0
CARNAZA |  |  | 13 | 13 | [6 empty] | 13 | 13
AAR Japan |  |  | 13 | 13 | [6 empty] | 13 | 13
LANAO |  |  | 577 | 305 | 51 | 0 |  |  |  |  | 628 | 305
AAR Japan |  |  | 22 | 22 | [6 empty] | 22 | 22
Habitat for Humanity |  |  | 283 | 283 | [6 empty] | 283 | 283
PRC - Japanese Red Cross |  |  | 272 | 0 | 51 | 0 |  |  |  |  | 323 | 0
LOGON |  |  | 21 | 21 | [6 empty] | 21 | 21
AAR Japan |  |  | 21 | 21 | [6 empty] | 21 | 21
MALBAGO |  |  | 17 | 17 | [6 empty] | 17 | 17
AAR Japan |  |  | 17 | 17 | [6 empty] | 17 | 17
MALINGIN |  |  | 85 | 5 | 11 | 0 |  |  |  |  | 96 | 5
AAR Japan |  |  | 5 | 5 | [6 empty] | 5 | 5
PRC - Japanese Red Cross |  |  | 80 | 0 | 11 | 0 |  |  |  |  | 91 | 0
MAYA |  |  | 2950 | 2940 |  |  |  |  | 50 | 0 | 3000 | 2940
AAR Japan |  |  | 26 | 26 | [6 empty] | 26 | 26
Habitat for Humanity |  |  | 1457 | 1457 | [6 empty] | 1457 | 1457
Lutheran World Relief |  |  | 1457 | 1457 | [6 empty] | 1457 | 1457
OM Philippines | [8 empty] | 50 | 0 | 50 | 0
PFI |  |  | 10 | [7 empty] | 10
PAYPAY |  |  | 33 | 23 | 148 | 0 |  |  |  |  | 181 | 23
AAR Japan |  |  | 23 | 23 | [6 empty] | 23 | 23
PFI |  |  | 10 | [7 empty] | 10
PRC - French Red Cross |  |  |  |  | 148 | 0 |  |  |  |  | 148 | 0
TALISAY |  |  | 923 | 923 | [6 empty] | 923 | 923
AAR Japan |  |  | 21 | 21 | [6 empty] | 21 | 21
Habitat for Humanity |  |  | 902 | 902 | [6 empty] | 902 | 902
TAPILON |  |  | 846 | 846 | [6 empty] | 846 | 846
Habitat for Humanity |  |  | 846 | 846 | [6 empty] | 846 | 846
TINUBDAN |  |  | 14 | 14 | [6 empty] | 14 | 14
AAR Japan |  |  | 14 | 14 | [6 empty] | 14 | 14
TOMINJAO |  |  | 23 | 23 | [6 empty] | 23 | 23
AAR Japan |  |  | 23 | 23 | [6 empty] | 23 | 23
(blank) |  |  | 1010 | [7 empty] | 1010
People in Need (PIN) |  |  | 1000 | [7 empty] | 1000
PFI |  |  | 10 | [7 empty] | 10
MADRIDEJOS | 81 | 81 | 736 | 596 | 103 | 6 | 90 |  |  |  | 1010 | 683
BUNAKAN | 81 | 81 | 15 | 15 | [6 empty] | 96 | 96
YPDR | 81 | 81 | 15 | 15 | [6 empty] | 96 | 96
PILI |  |  | 431 | 431 | [6 empty] | 431 | 431
Habitat for Humanity |  |  | 431 | 431 | [6 empty] | 431 | 431
TALANGNAN |  |  | 150 | 150 | [6 empty] | 150 | 150
Enfants du Mekong |  |  | 150 | 150 | [6 empty] | 150 | 150
TARONG |  |  | 140 | 0 | 103 | 6 |  |  |  |  | 243 | 6
PRC - German Red Cross |  |  | 140 | 0 | 103 | 6 |  |  |  |  | 243 | 6
(blank) | [6 empty] | 90 |  |  |  | 90
Islamic Relief Worldwide (IRW) | [6 empty] | 90 |  |  |  | 90
MEDELLIN | 42 | 42 | 2383 | 1972 | 40 | 10 |  |  |  |  | 2465 | 2024
ANTIPOLO |  |  | 39 | 29 | [6 empty] | 39 | 29
AAR Japan |  |  | 18 | 18 | [6 empty] | 18 | 18
HelpAge-COSE |  |  | 11 | 11 | [6 empty] | 11 | 11
PFI |  |  | 10 | [7 empty] | 10
CAPUTATAN NORTE | 13 | 13 | 442 | 442 | [6 empty] | 455 | 455
AAR Japan |  |  | 21 | 21 | [6 empty] | 21 | 21
HelpAge-COSE |  |  | 4 | 4 | [6 empty] | 4 | 4
PDRRN |  |  | 55 | 55 | [6 empty] | 55 | 55
World Vision | 13 | 13 | 362 | 362 | [6 empty] | 375 | 375
CAPUTATAN SUR | 6 | 6 | 188 | 188 | [6 empty] | 194 | 194
HelpAge-COSE |  |  | 6 | 6 | [6 empty] | 6 | 6
World Vision | 6 | 6 | 182 | 182 | [6 empty] | 188 | 188
CURVA |  |  | 29 | 19 | [6 empty] | 29 | 19
AAR Japan |  |  | 17 | 17 | [6 empty] | 17 | 17
HelpAge-COSE |  |  | 2 | 2 | [6 empty] | 2 | 2
PFI |  |  | 10 | [7 empty] | 10
DAANLUNGSOD |  |  | 281 | 230 | [6 empty] | 281 | 230
AAR Japan |  |  | 18 | 18 | [6 empty] | 18 | 18
Citizens' Disaster Response Center |  |  | 51 | 0 | [6 empty] | 51 | 0
Enfants du Mekong |  |  | 210 | 210 | [6 empty] | 210 | 210
HelpAge-COSE |  |  | 2 | 2 | [6 empty] | 2 | 2
DALINGDING SUR | 4 | 4 | 289 | 289 | [6 empty] | 293 | 293
AAR Japan |  |  | 11 | 11 | [6 empty] | 11 | 11
HelpAge-COSE |  |  | 8 | 8 | [6 empty] | 8 | 8
PDRRN |  |  | 118 | 118 | [6 empty] | 118 | 118
World Vision | 4 | 4 | 152 | 152 | [6 empty] | 156 | 156
DAYHAGON |  |  | 21 | 21 | [6 empty] | 21 | 21
AAR Japan |  |  | 18 | 18 | [6 empty] | 18 | 18
HelpAge-COSE |  |  | 3 | 3 | [6 empty] | 3 | 3
DON VIRGILIO GONZALES |  |  | 8 | 8 | [6 empty] | 8 | 8
HelpAge-COSE |  |  | 8 | 8 | [6 empty] | 8 | 8
GIBITNGIL | 13 | 13 | 353 | 190 | [6 empty] | 366 | 203
AAR Japan |  |  | 11 | 11 | [6 empty] | 11 | 11
Citizens' Disaster Response Center |  |  | 72 | 0 | [6 empty] | 72 | 0
HelpAge-COSE |  |  | 91 | [7 empty] | 91
World Vision | 13 | 13 | 179 | 179 | [6 empty] | 192 | 192
KAWIT |  |  | 157 | 70 | [6 empty] | 157 | 70
AAR Japan |  |  | 55 | 55 | [6 empty] | 55 | 55
Citizens' Disaster Response Center |  |  | 77 | 0 | [6 empty] | 77 | 0
HelpAge-COSE |  |  | 15 | 15 | [6 empty] | 15 | 15
PFI |  |  | 10 | [7 empty] | 10
LAMINTAK NORTE |  |  | 9 | 9 | [6 empty] | 9 | 9
HelpAge-COSE |  |  | 9 | 9 | [6 empty] | 9 | 9
Lamintak Sur |  |  | 36 | 36 | [6 empty] | 36 | 36
AAR Japan |  |  | 32 | 32 | [6 empty] | 32 | 32
HelpAge-COSE |  |  | 4 | 4 | [6 empty] | 4 | 4
Luy-a |  |  | 4 | 4 | [6 empty] | 4 | 4
HelpAge-COSE |  |  | 4 | 4 | [6 empty] | 4 | 4
MAHARUHAY |  |  | 90 | 40 | [6 empty] | 90 | 40
AAR Japan |  |  | 31 | 31 | [6 empty] | 31 | 31
Citizens' Disaster Response Center |  |  | 50 | 0 | [6 empty] | 50 | 0
HelpAge-COSE |  |  | 9 | 9 | [6 empty] | 9 | 9
MAHAWAK |  |  | 22 | 22 | [6 empty] | 22 | 22
AAR Japan |  |  | 19 | 19 | [6 empty] | 19 | 19
HelpAge-COSE |  |  | 3 | 3 | [6 empty] | 3 | 3
PANUGNAWAN | 6 | 6 | 223 | 223 | [6 empty] | 229 | 229
HelpAge-COSE |  |  | 1 | 1 | [6 empty] | 1 | 1
World Vision | 6 | 6 | 222 | 222 | [6 empty] | 228 | 228
POBLACION |  |  | 33 | 13 | 20 | 0 |  |  |  |  | 53 | 13
HelpAge-COSE |  |  | 13 | 13 | [6 empty] | 13 | 13
OM Philippines |  |  | 20 | 0 | 20 | 0 |  |  |  |  | 40 | 0
TINDOG |  |  | 29 | 9 | 20 | 10 |  |  |  |  | 49 | 19
HelpAge-COSE |  |  | 9 | 9 | [6 empty] | 9 | 9
OM Philippines |  |  | 20 | 0 | 20 | 10 |  |  |  |  | 40 | 10
(blank) |  |  | 130 | 130 | [6 empty] | 130 | 130
Habitat for Humanity |  |  | 130 | 130 | [6 empty] | 130 | 130
PILAR |  |  | 823 | 823 | [6 empty] | 823 | 823
(blank) |  |  | 823 | 823 | [6 empty] | 823 | 823
Municipality |  |  | 823 | 823 | [6 empty] | 823 | 823
PORO |  |  | 459 | 459 | [6 empty] | 459 | 459
(blank) |  |  | 459 | 459 | [6 empty] | 459 | 459
Enfants du Mekong |  |  | 3 | 3 | [6 empty] | 3 | 3
Municipality |  |  | 456 | 456 | [6 empty] | 456 | 456
SAN REMIGIO | 185 | 104 | 3304 | 1232 | 1704 | 479 | 300 |  |  |  | 5493 | 1815
ANAPOG |  |  | 122 | 16 | 155 | 91 |  |  |  |  | 277 | 107
Sign of Hope |  |  |  |  | 91 | 91 |  |  |  |  | 91 | 91
PRC - IFRC |  |  | 122 | 16 | 64 | 0 |  |  |  |  | 186 | 16
ARGAWANON |  |  | 250 | 240 | 137 | 0 |  |  |  |  | 387 | 240
PRC - IFRC |  |  | 250 | 240 | 137 | 0 |  |  |  |  | 387 | 240
BAGTIC |  |  | 98 | 17 | 21 | 0 |  |  |  |  | 119 | 17
PRC - IFRC |  |  | 98 | 17 | 21 | 0 |  |  |  |  | 119 | 17
BANCASAN |  |  | 87 | 16 | 55 | 0 |  |  |  |  | 142 | 16
PRC - IFRC |  |  | 87 | 16 | 55 | 0 |  |  |  |  | 142 | 16
BATAD |  |  | 114 | 16 | 63 | 0 |  |  |  |  | 177 | 16
PRC - IFRC |  |  | 114 | 16 | 63 | 0 |  |  |  |  | 177 | 16
BUSOGON |  |  | 69 | 18 | 103 | 32 |  |  |  |  | 172 | 50
Sign of Hope |  |  |  |  | 32 | 32 |  |  |  |  | 32 | 32
PRC - IFRC |  |  | 69 | 18 | 71 | 0 |  |  |  |  | 140 | 18
CALAMBUA |  |  | 124 | 18 | 35 | 0 |  |  |  |  | 159 | 18
PRC - IFRC |  |  | 124 | 18 | 35 | 0 |  |  |  |  | 159 | 18
CANAGAHAN |  |  | 183 | 145 | 36 | 0 |  |  |  |  | 219 | 145
PRC - IFRC |  |  | 183 | 145 | 36 | 0 |  |  |  |  | 219 | 145
DAPDAP |  |  | 112 | 37 | 41 | 0 |  |  |  |  | 153 | 37
PRC - IFRC |  |  | 112 | 37 | 41 | 0 |  |  |  |  | 153 | 37
GAWAYGAWAY |  |  | 148 | 0 | 50 | 0 |  |  |  |  | 198 | 0
PRC - IFRC |  |  | 148 | 0 | 50 | 0 |  |  |  |  | 198 | 0
HAGNAYA | 50 | 16 | 82 | 16 | 60 | 0 |  |  |  |  | 192 | 32
PRC - IFRC |  |  | 82 | 16 | 60 | 0 |  |  |  |  | 142 | 16
RCAC-RRU | 50 | 16 | [8 empty] | 50 | 16
KAYAM | 25 | 12 | 84 | 20 | 44 | 0 |  |  |  |  | 153 | 32
Landsaid | 25 | 12 | 36 | 7 | [6 empty] | 61 | 19
PRC - IFRC |  |  | 48 | 13 | 44 | 0 |  |  |  |  | 92 | 13
KINAWAHAN |  |  | 111 | 0 | 7 | 0 |  |  |  |  | 118 | 0
PRC - IFRC |  |  | 111 | 0 | 7 | 0 |  |  |  |  | 118 | 0
LAMBUSAN |  |  | 155 | 24 | 82 | 0 |  |  |  |  | 237 | 24
PRC - IFRC |  |  | 155 | 24 | 82 | 0 |  |  |  |  | 237 | 24
Lawis |  |  | 79 | 17 | 92 | 63 |  |  |  |  | 171 | 80
IOM |  |  |  |  | 22 | 22 |  |  |  |  | 22 | 22
PRC - IFRC |  |  | 79 | 17 | 70 | 41 |  |  |  |  | 149 | 58
LIBAONG |  |  | 128 | 56 | 65 | 19 |  |  |  |  | 193 | 75
Sign of Hope |  |  |  |  | 19 | 19 |  |  |  |  | 19 | 19
PRC - IFRC |  |  | 128 | 56 | 46 | 0 |  |  |  |  | 174 | 56
Looc |  |  | 77 | 17 | 66 | 62 |  |  |  |  | 143 | 79
IOM |  |  |  |  | 37 | 37 |  |  |  |  | 37 | 37
PRC - IFRC |  |  | 77 | 17 | 29 | 25 |  |  |  |  | 106 | 42
LUYANG |  |  | 106 | 17 | 27 | 0 |  |  |  |  | 133 | 17
PRC - IFRC |  |  | 106 | 17 | 27 | 0 |  |  |  |  | 133 | 17
MANO | 60 | 60 | 334 | 287 | 28 | 0 | 300 |  |  |  | 722 | 347
Hilfswerk Austria International | [6 empty] | 300 |  |  |  | 300
Landsaid | 60 | 60 | 268 | 268 | [6 empty] | 328 | 328
PRC - IFRC |  |  | 66 | 19 | 28 | 0 |  |  |  |  | 94 | 19
POBLACION |  |  | 87 | 18 | 72 | 59 |  |  |  |  | 159 | 77
PRC - IFRC |  |  | 87 | 18 | 72 | 59 |  |  |  |  | 159 | 77
PUNTA |  |  | 73 | 73 | 54 | 29 |  |  |  |  | 127 | 102
PRC - IFRC |  |  | 73 | 73 | 54 | 29 |  |  |  |  | 127 | 102
SAB-A |  |  | 132 | 15 | 22 | 0 |  |  |  |  | 154 | 15
PRC - IFRC |  |  | 132 | 15 | 22 | 0 |  |  |  |  | 154 | 15
SAN MIGUEL |  |  | 180 | 13 | 47 | 0 |  |  |  |  | 227 | 13
PRC - IFRC |  |  | 180 | 13 | 47 | 0 |  |  |  |  | 227 | 13
TACUP | 50 | 16 | 75 | 17 | 84 | 0 |  |  |  |  | 209 | 33
PRC - IFRC |  |  | 75 | 17 | 84 | 0 |  |  |  |  | 159 | 17
RCAC-RRU | 50 | 16 | [8 empty] | 50 | 16
TAMBONGON |  |  | 127 | 20 | 188 | 124 |  |  |  |  | 315 | 144
Sign of Hope |  |  |  |  | 124 | 124 |  |  |  |  | 124 | 124
PRC - IFRC |  |  | 127 | 20 | 64 | 0 |  |  |  |  | 191 | 20
TO-ONG |  |  | 78 | 18 | 33 | 0 |  |  |  |  | 111 | 18
PRC - IFRC |  |  | 78 | 18 | 33 | 0 |  |  |  |  | 111 | 18
Victoria |  |  | 89 | 81 | 37 | 0 |  |  |  |  | 126 | 81
IOM
PRC - IFRC |  |  | 89 | 81 | 37 | 0 |  |  |  |  | 126 | 81
SANTA FE | 22 | 22 | 1848 | 569 | 498 | 101 | 306 | 0 |  |  | 2674 | 692
BALIDBID | 3 | 3 | 163 | 163 | [6 empty] | 166 | 166
Habitat for Humanity |  |  | 163 | 163 | [6 empty] | 163 | 163
YPDR | 3 | 3 | [8 empty] | 3 | 3
KINATARKAN |  |  | 2 | 2 | 8 | 6 |  |  |  |  | 10 | 8
OM Philippines |  |  | 2 | 2 | 8 | 6 |  |  |  |  | 10 | 8
MARICABAN | 1 | 1 | 301 | 301 |  |  | 216 | 0 |  |  | 518 | 302
Habitat for Humanity |  |  | 301 | 301 |  |  | 216 | 0 |  |  | 517 | 301
YPDR | 1 | 1 | [8 empty] | 1 | 1
OKOY |  |  | 75 | 0 | 250 | 94 |  |  |  |  | 325 | 94
Muslim Aid |  |  |  |  | 20 | [5 empty] | 20
Order of Malta |  |  | 75 | 0 | 230 | 94 |  |  |  |  | 305 | 94
POBLACION | 4 | 4 | 100 | 100 | 17 | [5 empty] | 121 | 104
Habitat for Humanity |  |  | 100 | 100 | [6 empty] | 100 | 100
Islamic Relief Worldwide (IRW) |  |  |  |  | 17 | [5 empty] | 17
YPDR | 4 | 4 | [8 empty] | 4 | 4
POOC | 9 | 9 | 1132 | 3 | 77 | [5 empty] | 1218 | 12
Islamic Relief Worldwide (IRW) |  |  |  |  | 77 | [5 empty] | 77
Lutheran World Relief |  |  | 1129 | [7 empty] | 1129
YPDR | 9 | 9 | 3 | 3 | [6 empty] | 12 | 12
TALISAY | 5 | 5 | 75 | 0 | 146 | 1 |  |  |  |  | 226 | 6
Islamic Relief Worldwide (IRW) |  |  |  |  | 26 | [5 empty] | 26
Order of Malta |  |  | 75 | 0 | 120 | 1 |  |  |  |  | 195 | 1
YPDR | 5 | 5 | [8 empty] | 5 | 5
(blank) | [6 empty] | 90 |  |  |  | 90
Islamic Relief Worldwide (IRW) | [6 empty] | 90 |  |  |  | 90
TABOGON |  |  | 40 | [7 empty] | 40
LIBJO |  |  | 10 | [7 empty] | 10
PFI |  |  | 10 | [7 empty] | 10
MUABOG |  |  | 10 | [7 empty] | 10
PFI |  |  | 10 | [7 empty] | 10
SALAG |  |  | 10 | [7 empty] | 10
PFI |  |  | 10 | [7 empty] | 10
SOMOSA |  |  | 10 | [7 empty] | 10
PFI |  |  | 10 | [7 empty] | 10
TUDELA |  |  | 81 | 81 | [6 empty] | 81 | 81
(blank) |  |  | 81 | 81 | [6 empty] | 81 | 81
Municipality |  |  | 81 | 81 | [6 empty] | 81 | 81
(blank) |  |  | 250 |  | 1615 | [5 empty] | 1865
(blank) |  |  | 250 |  | 1615 | [5 empty] | 1865
PRC - German Red Cross |  |  | 250 |  | 1365 | [5 empty] | 1615
PRC - Taiwan Red Cross |  |  |  |  | 250 | [5 empty] | 250
(blank) |  |  |  |  | 369 | [5 empty] | 369
(blank) |  |  |  |  | 369 | [5 empty] | 369
(blank) |  |  |  |  | 369 | [5 empty] | 369
IOM |  |  |  |  | 369 | [5 empty] | 369
Grand Total | 1276 | 1161 | 21319 | 14551 | 5434 | 711 | 860 | 2 | 50 | 0 | 28939 | 16425

## SummaryCalc (hidden)
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
Row Labels | 2. Temporary Shelter
On original site | 184
Not specified | 1092
Grand Total | 1276
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
Row Labels | 7. Core House
On original site | 3842
Not on original site (Resettlement project) | 128
Mixed | 350
Not specified | 1114
Grand Total | 5434
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
Row Labels | 8. Permanent House
Not on original site (Resettlement project) | 590
Not specified | 270
Grand Total | 860
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
Row Labels | 6. Repairs & Retrofit
Major repairs | 328
Minor repairs | 5064
SSRS Shelter kit | 15649
Not specified | 278
Grand Total | 21319
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
| HH level facilities available / provided | Not specified
Row Labels
2. Temporary Shelter | 184 | 1092
6. Repairs & Retrofit | 2254 | 19065
7. Core House | 644 | 4790
8. Permanent House | 290 | 570
9. Settlement Planning |  | 50
Grand Total | 3372 | 25567
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
HH level facilities available / provided
Row Labels
2. Temporary Shelter | 184
6. Repairs & Retrofit | 2254
7. Core House | 644
8. Permanent House | 290
Grand Total | 3372
Region | REGION VII (CENTRAL VISAYAS)
Sum of HH_target | Column Labels
| Completed distributions | Ongoing distributions | In pipeline (procurement/onroute) | Planned
Row Labels
2. Temporary Shelter | 1101 | 175
6. Repairs & Retrofit | 13354 | 3367 | 3087 | 1511
Major repairs | 2 | 286 | 20 | 20
Minor repairs | 480 | 3081 | 1253 | 250
SSRS Shelter kit | 12744 |  | 1814 | 1091
Not specified | 128 |  |  | 150
7. Core House | 333 | 1651 | 1318 | 2132
8. Permanent House |  | 290 | 570
9. Settlement Planning |  |  |  | 50
Grand Total | 14788 | 5483 | 4975 | 3693
Region | REGION VII (CENTRAL VISAYAS)
Count of Individuals | Column Labels
Row Labels | (blank) | Grand Total
World Vision
TESDA Carpentry training
Grand Total
Region | REGION VII (CENTRAL VISAYAS)
Row Labels | Sum of Recepients
World Vision | 450
IEC Material | 50
(blank) | 400
Grand Total | 450