## Sheet1
| Global Shelter Cluster |  |  | 2015-03-20
ShelterCluster.org
Coordinating Humanitarian Shelter
Shelter Cluster: Accountability Working Group
Background
From 2012 onwards, the GSC has advanced a number of initiatives that aimed at better articulating the impact of shelter cluster coordination and response activities. In doing so, members of the GSC Working Group (WG) on Assessing Impact identified the need to expand the scope of the group’s activities to encompass all elements of the humanitarian program cycle, from preparedness, to assessment and planning, to monitoring, reporting and evaluation. A number of guidelines have been developed and piloted at country level to this purpose, including assessment and indicator guidelines
Objective
The overall objective of the Working Group is increase the accountability of humanitarian shelter interventions towards affected populations and humanitarian stakeholders. This will be achieved throguh two specific objectives: 1. enhanced ability to monitor and evaluate responses, 2. enhacend ability to monitor and evaluate coordiantion management, 3 enhanced use of available tools and technmologies 4) improved understanding of accountability to affected populations among coordiantion team members
No. | Priority (High, Medium, Low) | Activity | Output/Result | Status (Finished, on-going, to be defined) | who
Outcome 1) enhanced Monitoring and Evaluation of overall response
1.1 | high | 1) Consolidate existing methods, tools and practices |  | under discussion with SAG | all
1.2 | high | 2) WG workshop in Geneva end may 2015 | Note (NB) - how we determine 1) awareness on the situation/needs, 2) monitoring of cluster partner activities (where, what, who), 3) the impact or outcomes of those activities |  | neil, megan
1.3 |  | 3) Revision of Shelter Cluster Indicators | reach consensus on how we, as a sector, monitor our response |  | all
1.4 |  | 4)Work on measuring the impacts of a cluster |  |  | all
1.5 | high | 5) IM toolkit | further develop IM toolkit | under discussion with SAG | WG co-leads
Outcome 2) Enhanced Monitoring and evaluation of coordination
2.1 | high | complete guidelines on evaluations and cluster evaluation strategy | How we determine the effectiveness of the shelter cluster coordination activities |  | UNHCR (tbc) plus support of co-leads
2.2 | high | Implementation of cluster performance monitoring |  |  | all
Outcome 3) Use most appropriate online tools
3.1 | medium | Monitor activity info and other developments, and review applicability to shelter cluster | practical tools, and methods of collecting and aggregating the data from the above section, including viability of a central data repository |  | all
3.2 | medium | Review usability of sheltercluster website |  |  | all
Outcome 4) enhanced Understanding amon clsuter tteams of accountabiltiy to affted populations
4.1 | low | Illustrated case studies | Examples are here: http://www.ecbproject.org/resource/18358 page 13 |  | iom ?
4.2 |  | promotion of exisitng documetnation | wokring group one pager and ECB materials. |  | all
| Org | contacts
co-chair | IOM | Joseph ashmore | jashmore@iom.org
co-chair | IMPACT | Megan Passey | megan.passey@impact-initiatives.org awg.global@sheltercluster.org
group mailing list |  | AWG global@sheltercluster.org