# Shelter/NFI Working Group Meeting, Bujumbura

#### Date: – 26 March 2015

#### Location : IOM Bujumbura

As lead for the Shelter/NFI sector, IOM called a meeting with its partners on 26 March 2015.

UNHCR, UNICEF, IRC and the Burundian Red Cross sent representatives.

Attendance:

Noelle Darbellay (IOM), Kristina Mejo (IOM), Joseph Ashmore (IOM), Geneva and Global Shelter Cluster support team, Matteo Frontini (UNICEF), Marc Niyibikora (IRC), Alix Mashaka (UNHCR), Aloys Nkeha (UNHCR Jean-Claude Niyongabo (CRB)

## 1. Introduction

The purpose of the meeting was to:

- identify various settlement options in the Burundian context

- review information management documents, tools  and overall strategy

- review ways of operating, hubs and mobile teams for the Burundian context

## 2. Response strategy

Output: Summary table of expected settlement options and shelter response options (informal material needs for prepositioning)

Agreement: to distribute household NFI and household wash items together wherever possible. This will require coordination with supplying agencies and implementing partners

#### 2.1 Increasing detail on Settlement options and responses

Various potential settlement options were presented to the participants who were then asked to identify the most likely ones in the Burundian context. These are summarized on the last page of tis document.

Note camps are not the preferred option, but may be required in exceptional circumstances.

On this basis, three (3) types of kits were identified.

In the case of large scale and sudden displacement, light-weight kits would be initially distributed to temporary sites. They would also be provided to those returning to damaged houses. In the second phase of a response to a crisis, transitional kits would be distributed.

It was agreed that for logistical reasons, it would be easier to distribute both NFI and WASH items at the same time rather than duplicate actions.

### 3.	Information management

#### 3.1 MIRA

Based on the MIRA questionnaire that was developed in the Central African Republic (CAR), the participants revised the basic MIRA to adapt it to the Burundian context (revised version attached).

#### Shelter Assessments and registration

Agreement: there should be single point agency of displacement figures.

It was proposed that IOM take a lead in registration, and centralize figures.

Action: Further discussions is required between agencies to resolve issues relating to registration processes and cards.

#### 3.3 Commodity tracking and forms

Agreement: use of a single standard form for tracking distributions

All participants agreed that for overall monitoring, reporting and transparency purposes, it would be better to use one single standardized commodity tracking form. However, agencies would still use their own systems for internal and donor requirements. IOM will be responsible to share a form used in another context with the participants and adapt it if necessary to the context.

This is particularly key as it will allow avoiding duplication and as UN Agencies and IOM often resorting to the same implementing partners, it would make their tasks easier when reporting if there is one standardized commodity tracking form.

- Coverage and mobile teams

Action: Agencies should to look into establishing MoUs in relation to distribution and data collection. Close coordination will required between shelter and wash leads to ensure effective common use of resources.

The use of mobile teams in the country would be something to be further explored by the working group.

In this context, UNICEF also explained that they are currently signing stand-by agreement with various partners to preposition items and ensure a quick response in case of a crisis.

This will also be further explored by other working group members.

# Sommaire des options pour les déplacées

Ce document a été élaboré afin d’identifier les endroits dans lesquels les personnes déplacées au Burundi pourraient fuir/chercher un abri en cas de crises (socio-politique, naturelle, médicale, etc.). Ce document ne vise en aucun cas à promouvoir la construction de camps qui ne sera considérée que comme solution de dernier recourt.

Plan d'intervention

| Groupes cibles |  | Nombre total de cas estimé(s) | Activités d'urgence (jusqu'à 6 semaines – le cas échéant) |  | Activités de relèvement précoces (jusqu'à 9 mois – le cas échéant) |  | Cibles / Hypothèses/Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Cible #HH | Interventions et normes approuvées | Cible #HH | Interventions et normes approuvées |  |
| Personnes déplacées | Centres collectifs (école, église, marché, chef-lieu de commune, bâtiment privé, centre de santé, hangar) | <#> | <#> | INT1 – Kit Non Vivres | <#> | INT 8 - réhabilitation |  |
|  |  |  | <#> | INT4 – Amélioration du site | <#> |  |  |
|  |  |  | <#> | INT6 – Cuisines communales | <#> |  |  |
|  | Site spontanées dispersés (stade) | <#> |  | INT3 – Abri collectifs |  | INT 7 – Kit abri transitionnel ? |  |
|  |  |  |  | INT2 - Kits Abri D’urgence |  |  |  |
|  |  |  | <#> | INT1 – Kit Non Vivres | <#> |  |  |
|  |  |  | <#> | INT5 – Amélioration du site | <#> |  |  |
|  |  |  | <#> | INT6 – Cuisines communales | <#> |  |  |
|  | Familles d’accueil | <#> | <#> | INT1 – Kit Non Vivres | <#> |  |  |
| Personnes non déplacées | Familles d'accueil ayant besoin d'aide | <#> | <#> | INT1 – Kit Non Vivres | <#> |  |  |
|  | logement détruit | <#> | <#> | INT1 – Kit Non Vivres | <#> |  |  |
|  |  |  | <#> | INT 2 – Kit abri d’urgence | <#> | INT 7 – Kit abri transitionnel |  |
|  | logement décoiffé | <#> | <#> | INT1 – Kit Non Vivres – au besoin | <#> |  |  |
|  |  |  | <#> | INT 2 – Kit abri urgence | <#> | INT 7 – Kit abri transitionnel |  |
|  | logement légèrement endommagé | <#> | <#> | INT1 – Kit Non Vivres – au besoin | <#> |  |  |
|  |  |  | <#> | INT 2 – Kit abri urgence– au besoin | <#> | INT 7 – Kit abri transitionnel |  |
| NOMBRE TOTAL DE CAS |  | <#> |  |  |  |  |  |

INT 1 – kit non vivres

INT 2 – Kit abri urgence

INT 3 – construction d’abris collectifs

INT 4 – Amélioration des centres collectifs

INT 5 – Amélioration des sites (drainage et infrastructure)

INT 6 – Cuisines communales

INT 7 – Kit abris transitionnels

INT 8 - réhabilitation

This list might be reviewed when IRC will share standard kit list for Burundi