Shelter Cluster

Meeting Minutes

March 27, 2015

Agenda:

- Assessment

- 3Ws and distribution

- Gaps

- DFAT pipeline and good coming out of Brisbane

- Urban/peri-urban areas in Efate

- Focal Points

- SAG updates

- Health/education coordination

- AOB

- Next meetings

Attendance: IFRC, HFH, French RC, CARE, Caritas, Save the Children, Salvation Army, Butterfly Trust, DFAT, NDMO, WVI.

- Assessment

- 2 related assessments are currently being planned which will inform recovery process/strategy:

  - NDMO-led multi-sector assessment with participation by each cluster;

  - Shelter Cluster-led shelter specific vulnerability and recovery assessment.

The key differences/complementarities are that the multi-sector assessment will focus of key informant interviews (community chiefs in particular) while the shelter specific assessment is a random sample at household level.  The shelter sector assessment will be supported by REACH (assessment specialists) and based on information needs and assessment design specifications from shelter cluster members. Collaboration will also be sought with NDMO and WASH cluster.

- Shelter assessment working group meeting Saturday 28/3, 4pm

- 3Ws and distribution

- Ongoing work to update 3Ws and agency distribution information.

- Please send updates to: im.vanuatu@sheltercluster.org

- Initial review of data provided suggests that there is a total of 26,000 tarps in-country and pipeline. If correct, this suggests a total surplus of 4,000 tarps (initial assessments suggested a need for 22,000 tarps).

- CARE/Samaritan’s Purse could distribute additional tarps.

- South Malekula is a potential gap in shelter coverage.

- An estimated 8,000 tarps have been distributed by all agencies. This means about 50% of families have received them. The total target is 15,000 affected families.

- Gaps

- South Malakulou and South Pentecost are possible gaps. Red Cross, WVI, and Save the Children have indicated that assessment/distribution teams are heading to these islands.

- Following distribution authorization from NDMO, agencies have matched areas of need in urban/peri-urban Port Vila with aid agencies. All areas now have designed agencies with assessment/distribution ongoing.

- Red Cross has shared assessment/distribution methodology to ensure common approach that is coordinated with local authorities.

- DFAT & Brisbane pipeline

- ADF flight arriving Saturday with shelter supplies prioritized. Items include shelter relief items for DFAT Humanitarian Partnership Agencies as well as DFAT relief stock.  Distribution will be coordinated through the shelter cluster.

- Focal Points

- Agency cluster contacts have been agreed to for some of the main islands who will support the PDCs.

  - TAFEA:

  - Tanna – Red Cross.

  - Erromango – CARE

  - SHEFA:

  - Efate (Port Vila and Rural Efate)– SWG.

  - Shepherd Islands – Save the Children and RC (Save the Children: Tongoa and Epi; RC: remaining islands)

  - MALAMPA:

  - Ambrym –ADRA

  - Paama – RC

  - Malekula – ADRA

  - PENAMA:

  - Pentecost – WV

  - Maewo –WV

- Strategy Working Group

- Initial discussion on shelter strategy is underway as the emergency period begins to phase out.  Broadly, the strategy aims to:

  - Ensure a coordinated approach to safe sheltering;

  - Identify gaps, different settlement types/needs, and a possible range of approaches for urban, rural, informal and peri-urban settlements, among others.

  - Develop common approaches to IEC materials and shelter/construction skills development in communities.

  - Appropriate links with other sectors, eg WASH.

- Strategy Working Group meeting: Tuesday 31 March, 4pm

- Health and education shelter requests

- Shelter cluster has received repeated requests for assistance with schools/health centres, especially for tarps.

- Infrastructure cluster is mapping and repairing damage to schools and health facilities with assistance from ADF and NZDF.

- Some Shelter Cluster agencies are also working in schools, especially Save the Children.

- Where possible, shelter cluster will link health/education with agencies that have available materials, but this may be difficult under current shelter resource constraints. The primary cluster aim is emergency shelter support to households.

AOB

- IEC materials translated into Bislama, WVI check on status/accuracy of translation.

NEXT MEETING:

Shelter Cluster: Monday, 30 March 4pm

Assessment Working Group: Saturday, 28 March, 4pm

Strategy Working Group: Tuesday, 31 March 4pm