Shelter Working Group

Meeting minutes

March 30, 2015

Agenda

- Introductions

- 3Ws &Gaps

- Assessment

- Market mapping

- IEC materials

- Debris/trees

- Tafea Province – CARE update

- Minimum agreed shelter standards

- Tarps & tents/shelter & education

Key Shelter Cluster contacts:

- Cluster Coordinator:

  - Tom Bamforth: coord.vanuatu@sheltercluster.org

  - Ph. 7753937

- Information Manager:

  - Neil Bauman: im.vanuatu@sheltercluster.org

  - Ph. 5473799

2. 3Ws &Gaps

- Please send updated 3W information to im.vanuatu@sheltercluster.org

- Principally tracking tarps, tool kits, kitchen sets and blankets

- Need is difficult to calculate but ongoing work to refine/wash the data with new information from cluster partners and government assessment data.

- 23 islands identified, with a need of 12,600 households, (rough estimate) that have totally destroyed, or partially damaged house. Population figures are unstable, and this initial estimate is likely to rise.

- Total number of HH assisted is c. 9500.

- Number of tarps distributed, in-country and in pipe: 31,500 tarps.

- 3W information in cluster database will be sent to individual agencies for verification to ensure that everything is captured.

- Concerns around quantities of food in pipeline  - may slow down shelter items coming in.

3. Assessments

- Multi-sector, key informant assessment starts Wednesday for Tafea and Shefa.

- Shelter key informant assessment has been finalized, assessors identified (courtesy of gender and protection cluster), and trained in how to use the form.

- Phase II: Penama and Malampa starts after Easter.

- Separate (but complementary) shelter & settlements vulnerability assessment planning is underway in collaboration with REACH.

- Going to go down to household level, representative sample at island level, define estimated caseloads, confirm gaps, and future for monitoring for emergency and early recovery. Looking at starting after Easter break

  - Will start in Port Vila, and then later go out to the other islands

  - REACH staff will travel to the islands, will assess 23 islands

  - Looking at maximum of 30 – 68 HH per island assessed

  - Will try to harmonize the REACH assessment with multi-sector assessment, to complement it.

4. Market mapping

- Adesh Tripathee (Habitat for Humanity) has had an initial look at market conditions in Port Vila.

- There is general availability of tools and shelter supplies and competitive prices. No evidence of shortage or inflation yet. There are tax exemptions for NGOs on VAT until 25 May.

5. IEC materials

- WVI is working on some draft pictorial IEC materials with Bislama translation and will share with cluster.

Other considerations:

- Literacy rates may be an issue.

- IEC can be placed on village noticeboards.

- Importance of context: strong indigenous building techniques that need to be understood.

- Traditional houses reported as the safest houses in the village. People are preferring the more modern houses, which are less safer.

- Keep messages simple: bracing and connections.

- Different messages for urban/rural.

6. Debris/trees

- NHO- some resources available, like fallen trees, local mills, saws to cut lumber can cut local trees fallen in community. Many local trees will go rotten in few months. People have the local knowledge. To do it faster, not about importing lumber, more about cutting the trees, and putting up sawmills.

  - Concerns:

    - Potential environmental damage of introducing sawmills.

    - Ownership of trees may need to be established.

7. Tafea situation – CARE update

- Importance of context: eg. Erromango is very different from Happyland.

- Communities are rebuilding very quickly. Emergency phase still important, they may rebuild their house, but kitchen needs work.

- Many communities still have access to tools – 100% distribution is not excessive. One toolkit per c. 5 families is more appropriate.

8. Technical Group: agreed emergency shelter approach

- For the emergency period, the Shelter Cluster agreed a statement on technical assistance.

- Appropriate emergency shelter support is highly context dependent. The agreed sheltering approach is:

  - Totally damaged HH: 2 Tarpaulins

  - Partially damaged HH: 1 Tarpaulin

  - HH should have access to a shelter kit (the quantity per HH will depend on the context and cluster agency assessment of what tools are already available. One toolkit per HH may be excessive).

  - Additional NFIs such as kitchen sets, blankets will also be agency and context specific and dependent on assessed need.

- Agency reporting needs to be on the basis of HH served.

9.Tarps and tens/shelter and education

- There are some tarps and tents in the VMF gym. A stocktake is currently taking place.

- Agencies wishing to access these resources should send an email with distribution plan to coord.vanuatu@sheltercluster.org

- Please note: requests for education/health shelter-related materials should go through the education/health clusters.

- Urban areas

- Concerns raised about emergency shelter coverage in urban areas.

- Possibly greater needs than initially thought and agencies report increasing numbers of people demanding shelter relief items at agency offices.

- Agencies may not have sufficient tarps to cover the entire area.

- SC will prioritise coordination of shelter in urban/peri-urban areas.

Next meeting:

Wednesday, 1 April 4pm Meteo office, NDMO.