| #### Cluster: |  |  | #### Shelter |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Date of Meeting: |  |  | #### April 14th, 2015 |  |  | #### Time: |  |  |  |  |  |
| #### Meeting Facilitator: |  |  | #### Tom Bamforth |  |  | #### Location: |  |  |  |  |  |
| #### Minutes Prepared By: |  |  | #### Ryan Smith |  |  | #### Location: |  |  | #### NDMO |  |  |
| ### 1. Meeting Objectives |  |  |  |  |  |  |  |  |  |  |  |
| - Introductions - 3W Report - Strategy – Urban & Rural - Stocks/Pipeline - Debris to Shelter - Communications - Focal Points - Natangora |  |  |  |  |  |  |  |  |  |  |  |
| ### 3. Agenda and Notes, Decisions, Issues |  |  |  |  |  |  |  |  |  |  |  |
| Topic |  |  |  |  |  |  |  | Owner |  |  | Time |
| - Introduction Nikita – starting protection group Julian – frc, filling in for Arturo |  |  |  |  |  |  |  | Tom |  |  |  |
| - 3W Update - Port Vila - Damage data is deflated and will go up soon as assessment data comes in - Although case load will go up, there are overstocks to partially absorb - Tanna - IOM reports about 32 makeshift evac centers still occupied in Tanna - WV just completed 1000+ tarp distributions in Tanna, increasing coverage - Overstocks are recorded but like Port Vila case numbers will go up as assessment data comes in. - Tarp Standards - Verifying SP tarp specs to match to minimum standards. - Minimum standards posted to Shelter Cluster Vanuatu site. - 3W - Agency ensure that you use new 3W reporting template |  |  |  |  |  |  |  | Ryan |  |  |  |
| - Strategy – Urban & Rural - Draft of shelter cluster strategy being revised - 5 key objectives included - Support to local disaster committee - Activities – inputs – DRR built in, linked to - Shelter ties in with wash - no roofs = no water catchment - Julian - Community based disaster working group exists |  |  |  |  |  |  |  | Tom |  |  |  |
| - Strategy – Urban & Rural - Draft of shelter cluster strategy being revised - 5 key objectives included - Support to local disaster committee - Activities – inputs – DRR built in, linked to - Shelter ties in with wash - no roofs = no water catchment - Julian - Community based disaster working group exists |  |  |  |  |  |  |  | Tom |  |  |  |
| - Stocks/Pipeline - Red cross has extra stocks of blankets, shelter kits. - Act for peace will have 400 tarps in the container - Save the Children has 350 shelter tool kits for purchase - If you have extra stocks, let tom know - Act for peace will have report on urban coverage, will send it in to tom, tom will pass around - Steve – where are we recording people’s concerns? - Can we compile and record concerns, see if there are hotspots? - Tom & Ryan make record database where agencies can report beneficiary feedback |  |  |  |  |  |  |  | Tom |  |  |  |
| - Port Vila Urban Areas - Long term dev groups coming into PV - Jennie – WV went in with dla. Interest from gov for turning response into urban development – urban vision recovery strategy. Gov doesn’t have apparatus in place to deal with urban issues. Gov wants policy that has approval of cluster. Has recovery and drr activites. Emphasizing short term and longer term. - Key Points - Accommodating emerging urban form - Generating new economic & livlihoods - Assuring food security - Rebuild and planning inrafstrucutuer - immigrants - Slum upgrading - Creating strong urban governace - Preserving & celebrating culture - City and municipal living doesn’t end at borders of jurisdication, challenge - Need to address urban needs - Julian – evacuation centers included in plan? - Meeting 11am tomorrow meeting to finalize this draft and feedback |  |  |  |  |  |  |  | Jennie |  |  |  |
| - Debris to Shelter - Fallen trees, logs can be milled. Support for timber milling of fallen trees. Looking for saw mills and chinsaws. Arrangement betweween cutters and landowners. Throughout province. Identified gatekeepers of province through dla. IOM in coordination with local authorities. - If anybody is interested in medium to long term collaboration on milling let shelter now |  |  |  |  |  |  |  |  |  |  |  |
| - Communications - Need to do more with communications, broadcast what the cluster is doing - Any agencies interested in comms strategy? - Any agencies have some comms people with them? - Meet tomorrow afternoon with agency’s comms specialist |  |  |  |  |  |  |  | Tom |  |  |  |
| - Focal Points - Looking for agency cluster focal points on each of the islands - Care – tanna, futuna, erromango - WV – shepherds? - STC – tongoa - Would agencies be interested? People we could call as eyes on the ground. Let cluster know. |  |  |  |  |  |  |  | Tom |  |  |  |
| - Natangora - Dave - Natangora sourced from XXXX near santo. 240 vatu a thatch. Very expensive. - We have contact of a man on mala |  |  |  |  |  |  |  | Tom |  |  |  |
| ### 4. Action Items |  |  |  |  |  |  |  |  |  |  |  |
| Action |  |  |  |  |  |  |  | Owner |  |  | Due Date |
| Assessments for PDNA has been finished, share with group for technical meeting 11am April 15th |  |  |  |  |  |  |  | Tom |  |  |  |
| Add columns to 3W for recovery activities |  |  |  |  |  |  |  | Ryan |  |  |  |
| Follow up with Brenda about affected community going to NDMO. Create database for agencies to report back on. |  |  |  |  |  |  |  |  |  |  |  |
| Josh look at technical guidelines – are we talking repairs? Transitional shelters? Every permanent and semi permanent house should have wash compenent, put it on WASH radar. |  |  |  |  |  |  |  | Josh |  |  |  |
| ### 5. Next Meeting (if applicable) |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  | April 17th, 2015 |  | Time: | 3pm |  | Location: |  |  |  |  |
| Objective: |  |  |  |  |  |  |  |  |  |  |  |