| #### Cluster: |  |  | #### Shelter |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Date of Meeting: |  |  | #### 04/24/2015 |  |  | #### Time: |  |  |  |  |  |
| #### Meeting Facilitator: |  |  | #### Tom Bamforth |  |  | #### Location: |  |  | #### NDMO |  |  |
| #### Minutes Prepared By: |  |  | #### Ryan Smith |  |  | #### Location: |  |  | #### NDMO |  |  |
| ### 3. Agenda and Notes, Decisions, Issues |  |  |  |  |  |  |  |  |  |  |  |
| Topic |  |  |  |  |  |  |  | Owner |  |  | Time |
| Updates - Hap – Finalized, presented to government. All shelter inputs in there, - OPS – All shelter programs in there, approved. $3.7 million for shelter programs for the next 6 months of recovery programs. - HAP & PDNA at same time – what does that mean to funding and donor process? Maybe start getting donors in to meetings to raise awareness of activities. Preserving well-being & dignity. - TWiG – Finalizing repair material, fixings kits, - Comms – Messages there in french, english, bislama but got bumped from program. Should go out soon though. |  |  |  |  |  |  |  |  |  |  |  |
| 3w’s - Updated 3W’s with OCHA, reaching about 18,000 to 19,000 households tarpaulins. - Caseload remains the same as more data comes in but still needs to be verifiied. - Feedback – compiled in report, about 2,900 cases requesting shelter assistance. - Most from Port Vila and surrounding areas. - Numbers are hard to reference because of issue of cross checking, double counting, tracking of assistance received after complaint, assessing individual hosueholds, etc. Also not accurately tracking outside islands. - Trends – overwhelmingly most compkaints come from resettled island communities, and/or from informal settlements. - Presentation of NDMO stocks of agency tarps – please update if figures are not correct. |  |  |  |  |  |  |  |  |  |  |  |
| Protection - Key people in protection - Lucy and Esra - Background – G&P cluster with 4 working groups that all report up. Protection is about improving safety and access. Preserving well-being & dignity.Key point is do no harm. Not discriminating or excluding. How to identify and access most vulnerable people. Establishing complaints mechanism, and ensuring people are involved in their own recovery. - Sometimes central distribution areas reduce access for vulnerable groups to food and goods. - Directly to household is best but logistical challenges make that difficult. But that also helps with verifying household numbers and damage. |  |  |  |  |  |  |  |  |  |  |  |
| Milling - Started in vila – debris clearance.Separting wood, but depends on quality and capcity to start milling - CARE looking to get chainsaw mills going, waiting on equipment. Question of training. Questions include who owns the logs/the land? Can people sell the timber? Who would get the timber mills after? Logs can rot after 3 months on the ground. - Watson from Forestry present. Mill trees on the ground ASAP. - Looking to allocate mills that have that largest areas of downed trees. |  |  |  |  |  |  |  |  |  |  |  |
| Gaps, and Port-Vila urban/peri-urban As gaps are identified through feedback and M & E we continue to coordinate relevant shelter agencies to address them. |  |  |  |  |  |  |  |  |  |  |  |
| Next Meeting - Possible we can arrange to have a shelter cluster meeting in Tanna for Friday in order to get in the field and reach agencies there. TBD. |  |  |  |  |  |  |  |  |  |  |  |
| ### 4. Action Items |  |  |  |  |  |  |  |  |  |  |  |
| Action |  |  |  |  |  |  |  | Owner |  |  | Due Date |
| Pass around soft copies of protection docs. Email feedback template to Lucy & Esra. |  |  |  |  |  |  |  | Ryan |  |  |  |
| Correct NDMO stocks if incorrect |  |  |  |  |  |  |  | Agencies |  |  |  |
| Meet Monday TWiG for Milling working group 10am. |  |  |  |  |  |  |  | Agencies involved and Forestry |  |  |  |
| Next cluster meeting next Wednesday 4pm. |  |  |  |  |  |  |  | Tom |  |  |  |
| ### 5. Next Meeting (if applicable) |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  | April 27th, 2015 April 28th, 2015 |  | Time: | 10am 4pm |  | Location: |  |  | NDMO NDMO |  |
| Objective: |  |  |  |  |  |  |  |  |  |  |  |