| #### Cluster: |  |  | #### Shelter |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Date of Meeting: |  |  | #### April 29th, 2015 |  |  | #### Time: |  |  |  |  |  |
| #### Meeting Facilitator: |  |  | #### Tom Bamforth |  |  | #### Location: |  |  | #### NDMO |  |  |
| #### Minutes Prepared By: |  |  | #### Ryan Smith |  |  | #### Location: |  |  | #### NDMO |  |  |
| ### 1. Meeting Objective |  |  |  |  |  |  |  |  |  |  |  |
| - Introductions - Updates: - Hap - Shelter vulnerability - Natangora - 3W’s - Meeting in Tanna |  |  |  |  |  |  |  |  |  |  |  |
| ### 3. Agenda and Notes, Decisions, Issues |  |  |  |  |  |  |  |  |  |  |  |
| Topic |  |  |  |  |  |  |  | Owner |  |  | Time |
| Introductions - Margaret (Vanwoods) - Org for women’s rights and opportunities - microfinance - Centers all around Vanuatu - Model – Women join as pod, meet every week, save and repay every week. Get trained and advice, have repayment scheme, no defaults. Haven’t used aid money, have no defaults. - Why in shelter cluster? – Vanwoods has linkages to affected islands – maybe some of the aid can be given and disbursed through vanwoods, microfinance. Wash, shelter interests. - It’s possible to use this to assist shelter rebuild amongst communities, although women aren’t builders. - Possibly have smaller working group meeting to discuss further Jessie Ray – Peace Corps - Went through islands with lots of natangora for the shepherds - Want to develop a plan to get this natangora down to the shepherds - Have been in touch with shipping companies that can accommodate some shipments - Will only come in leaves, which is good, because this will give women a chance to do something with them for shelter or for livlihoods. - Want to set this up for preparedness for future cyclones - Next step – find out from CDCs how much they need. Could find out from every CDC total amount. - Just rough idea for now, lots of leads, need to follow up and create plan |  |  |  |  |  |  |  |  |  |  |  |
| Vulnerability assessments - Nearly done with all assessments - Next steps: working on results. Draft to headquarters maybe by Wednesday, then cicrculate for comments, then maybe publish by Friday and can present results. - Self recovery – generally, affected communities have been organizing and going HH to HH assisting with repair and rebuilds, traditional structures rebuilding quicker than mixed or modern. |  |  |  |  |  |  |  |  |  |  |  |
| 3Ws Key Messages - Tarpaulin distributions will eventually reach over 20,000 HH. - Requests for shelter assistance are being recorded and analyzed for potential gaps in area coverage. - Maps have been created to help with assessment. More maps and infographics available upon request. - Shelter cluster website has been updated with more shelter resources, information and schedules. |  |  |  |  |  |  |  |  |  |  |  |
| WASH - How are we integrating WASH into shelter programs? - Some for water collection, infrastructure for community projects, like schools, centers, etc. Linked to pre existing WASH programs. - Others are doing latrine repair (shelter + wash compenents), water catchments. |  |  |  |  |  |  |  |  |  |  |  |
| Tanna - Trying to schedule meeting in Tanna next week, to be able to meet with Tanna govt and humanitarian partners. Details to come. |  |  |  |  |  |  |  |  |  |  |  |
| ### 5. Next Meeting (if applicable) |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  | Thursday, May 7th, 2015 |  | Time: | 4pm |  | Location: |  |  | NDMO |  |
| Objective: |  |  |  |  |  |  |  |  |  |  |  |