| #### Cluster: |  |  | #### Shelter |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Date of Meeting: |  |  | #### May 5, 2015 |  |  | #### Time: |  |  | #### 2pm Sharp |  |  |
| #### Meeting Facilitator: |  |  | #### Tom Bamforth |  |  | #### Location: |  |  | #### NDMO |  |  |
| #### Minutes Prepared By: |  |  | #### Ryan Smith |  |  | #### Location: |  |  | #### NDMO |  |  |
| ### 1. Meeting Objective |  |  |  |  |  |  |  |  |  |  |  |
| - Introductions - Schools - 3W’s - Gaps, disability list - Early recovery - PWD Home Design - Chainsaws |  |  |  |  |  |  |  |  |  |  |  |
| ### 3. Agenda and Notes, Decisions, Issues |  |  |  |  |  |  |  |  |  |  |  |
| Topic |  |  |  |  |  |  |  | Owner |  |  | Time |
| Introductions - Representatives of the groups VRCS, Education, Prov. Trainer, Finance Dept, Magistrate Courts, Assistant SG, Customs, Prov Gov, and others. |  |  |  |  |  |  |  |  |  |  |  |
| Schools - Damage assessments from secondary schools coming in. - 45 teacher’s accommodations damaged or destroyed. - School Tents have been blown away in the strong wind. - Teacher’s accommodations affected, forced now to stay and sleep in classrooms. - Shelter Cluster can collect assessment data and reports and coordinate with Education Cluster to address concerns. |  |  |  |  |  |  |  |  |  |  |  |
| 3W’s - Have reached about 4,800 HH, set to hit about 3,700 more HH, to about 8,500 HH total. - We have been collecting feedback from beneficiaries, observers, agencies etc. - We are seeing the beginning phases of monitoring, shelter repair training and shelter repair kit distribution activities. - We are available for Tanna specific information, coordination, communication, etc. Contact details provided. |  |  |  |  |  |  |  |  |  |  |  |
| Gaps - People in the village did not wait for distributions, people helped themselves to build. Tarpaulin yes for each shelter – but also shelter tool kits to enable people to build back again. - We should focus on getting tool kits out to communities, and to family groups - A lot of government agency workers don’t have the time to repair their own homes, busy working in the response. - Need to get tool kits out ASAP to build back, clear, cut trees, etc. - Could do training quicker and easier to get them tool kits faster. - Need tools to start cutting trees and possibly milling. Chainsaws are expensive. They are coming in, but need training and safety schemes to go with them. - People want CGI/hollow black for homes but also seeing more now sturdiness of traditional structures. - Data reliability is an issues - Some issues with standardized quantities and quality of shelter distributions. - Any monitoring happening? Hearing back from beneficiaries now but maybe more rigourous process needs to be implemented. |  |  |  |  |  |  |  |  |  |  |  |
| Chainsaws - There are some chainsaws here in Tanna - There are some plans to bring chainsaws in, but with it needs to come training and support. - Chainsaws and milling are being followed up in TWiGs in PV. |  |  |  |  |  |  |  |  |  |  |  |
| PWD Shelter Design - PWD delegate has design and concept to build cyclone resistant traditional home. Has contact helping with the design, wants to build in center of town for visibility and promotion - Another benefit is that its cheap - Delegate to send in designs and go from there. |  |  |  |  |  |  |  |  |  |  |  |
| Coordination - Need identified for more information to Tanna shelter actors, and need for more local cluster coordination - Shelter Cluster to follow up, and possible to have more Shelter Cluster meetings in Tanna in the future. |  |  |  |  |  |  |  |  |  |  |  |
| ### 4. Action Items |  |  |  |  |  |  |  |  |  |  |  |
| Action |  |  |  |  |  |  |  | Owner |  |  | Due Date |
| All delegates send in relevant data, reports and feedback to the shelter cluster |  |  |  |  |  |  |  | All |  |  |  |
| Shelter Cluster provide contact information and follow up on Tanna concerns. |  |  |  |  |  |  |  | Shelter Cluster |  |  |  |
| ### 5. Next Meeting (if applicable) |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  | TBD |  | Time: |  |  | Location: |  |  | Tanna |  |
| Objective: |  |  |  |  |  |  |  |  |  |  |  |