| #### Cluster: |  |  | #### Shelter |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Date of Meeting: |  |  | #### May 8th, 2015 |  |  | #### Time: |  |  |  |  |  |
| #### Meeting Facilitator: |  |  | #### Tom Bamforth |  |  | #### Location: |  |  | #### NDMO |  |  |
| #### Minutes Prepared By: |  |  | #### Ryan Smith |  |  | #### Location: |  |  | #### NDMO |  |  |
| ### 1. Meeting Objective |  |  |  |  |  |  |  |  |  |  |  |
| - Introductions - Updates - Shelter Vulnerability Assessment - Protection - Cluster Tanna Visit - 3Ws - Trainin and Tools - Matasso IDPs - Lessons Learned - AOB |  |  |  |  |  |  |  |  |  |  |  |
| ### 3. Agenda and Notes, Decisions, Issues |  |  |  |  |  |  |  |  |  |  |  |
| Topic |  |  |  |  |  |  |  | Owner |  |  | Time |
| Shelter Vulnerability Assessment - Writing report now, finalizing next week. 806 HHs reached, across 13 sample sites on 18 islands. - Preliminary results are showing there are still gaps, some significant - Preliminary needs include fixings, milled lumber, and tools, and there is a lack of availability of those things in many areas. - Report will come out for review and comments soon, please send in comments so report can be finalized next week. |  |  |  |  |  |  |  |  |  |  |  |
| Introductions - Xavier Genot, new cluster lead taking over tomorrow |  |  |  |  |  |  |  |  |  |  |  |
| Protection - Lucy – UNHCR, G&P Cluster - Gathering information, feedback, requests from Women’s Information Tents - Women are reporting basic shelter needs - Information collected awhile a go, hard to tell how relevant info still is - Vila – out of ~280 women, ~260 requesting tarps or tents. - Areas identified look similar to areas identified in NDMO feedback recorded - Many in Tanna, also requesting shelter items - Will forward information to shelter cluster to dissenimate and follow up on |  |  |  |  |  |  |  |  |  |  |  |
| Cluster Tanna Visit - Delayed return until yesterday, missed meeting - Heavy rain, transport difficult, bad roads - Visited North Tanna, Middlebush and West Tanna to see agency activities - Cluster meeting had mainly only gov reps, and of that mainly education - Education reps identified needs in shelter for student dormitories, teacher accommodations, etc. - Didn’t appear to have storng communication between agencies there, although there were some programming overlaps and gaps identified - Gaps include boundary areas, local coordination and NGO focal point. - Anyone interested in being Tanna focal point? Care Int to ask. |  |  |  |  |  |  |  |  |  |  |  |
| 3Ws - 20,000 HH reached for tarpaulin distributions - Gap areas identified continue to be informal settlements, island communities, vulnerable groups, including what we’ve heard from Women’s Information Centers. - We’ll take info from Womens Info Centers to add to feedback collection database. - We can be used as a resource for info, mapping, etc. - SCA has extra toolkits, will work to identify agency toolkit needs, or affected community needs for toolkits - May 28th/29th 2000 more tarps coming in |  |  |  |  |  |  |  |  |  |  |  |
| Butterfly Trust Training Update - Feedback from Ian (Butterfly) on pilot training program - Issues, from Ian: - Tools – Quality an issue, may not hold up to hard use. - Equipment/Materials – Designed to be used for softer wood maybe, lighter use. Not durable enough. - Building practices – common building practices haven’t been followed, comprimising safety. - Training – Short training program may not be appropriate to actually build back safer, may be more systemic issues. - Ian - Maybe we need more awarenss training then. Long term, high quality training for both traditional and modern building systems is needed. - Dave – Might mean we update the training concept to focus more on training the trainers, like RTC and VIT, to be more comprehensive and longer term. - Xavier – maybe we can have a working group to agree on training principles - Challenges exist with matching these long term ideals with realities of current project implementation. Question of how to adapt both. |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learned - There will be government lessons learned process, as well as cluster one. Open forum for lessons learned: - Paul – ability to pull out the “good stories” of survival, things that work, “give voice to the people”. Helps to work with the trauma. - Adam – Continuity in cluster leadership has been good, availability is good. Also, we may need comms budget to get out messaging. - Paul – We need to get more gov, communities involved in cluster meeting – need more ni-Van cluster presence. - Paul – We should include “What would we do better” for next disaster in Vanuatu. - Dave – We should maybe leave shelter cluster here for permanent Vanuatu presence - We should have better communications to get out resources, information from cluster, cluster website - Siobhan – Shelter cluster is seen as inclusive and aware of cross cutting themes, intercluster needs. That would be good to be translated to other clusters, and/or to a permanent shelter cluster in country. - Ian – Focus energy on good stories for recovery. |  |  |  |  |  |  |  |  |  |  |  |
| Matasso IDPs - Matasso group wil have shelter NFI needs, will distribute needs list to agencies who could spare items. |  |  |  |  |  |  |  |  |  |  |  |
| ### 4. Action Items |  |  |  |  |  |  |  |  |  |  |  |
| Action |  |  |  |  |  |  |  | Owner |  |  | Due Date |
| Training TWiG/workshop |  |  |  |  |  |  |  |  |  |  | May 12th, 2pm |
| Shelter Cluster meeting |  |  |  |  |  |  |  |  |  |  | May 14th, 3pm |
| ### 5. Next Meeting (if applicable) |  |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  | Time: |  |  | Location: |  |  |  |  |
| Objective: |  |  |  |  |  |  |  |  |  |  |  |