## Slide 1
Vanuatu Shelter Cluster meeting
4th June 2015
PWD main office – conference room

## Slide 2
1. Introduction
2. IM update
3. Updates and discussion
  Shelter Lessons Learned workshop key outputs
  Building Back Safer Technical Working Group (TWiG) key outputs
  Shelter cluster, preparedness and recovery timeframes
  Communication With Communities (CWC)
  Cash/vouchers programming?
  VAT for shelter material
  2,000 tarps process
4. Partners update and issues
5. AOB
Agenda

## Slide 3
2.IM update – distribution as 01/06
INITIAL TOTAL CASELOAD (Damaged & Destroyed HH) | 13 574
HAP target | 18 000
Total HH for Tarps | 24 147
Total HH for Shelter Awareness | 5 166
Total HH for Shelter Reconstruction Activities | 1 101
Total HH for Shelter Repair Materials | 6 637
Total HH for Shelter Tool Kits | 14 707
Total HH for Kitchen Sets | 9 971
Total HH for Blankets | 17 228
Total HH for Solar Lamp | 3 271

## Slide 4
What worked well?
Relatively quick establishment of the shelter cluster, starting from scratch, and placing it clearly in the NDMO cluster system.
Whilst the establishment of an official shelter cluster was new to Vanuatu, its operation was assisted greatly (albeit indirectly) at Provincial and community level through well organised and managed PDC’s and CDC’s.
In addition, communities themselves commenced reconstruction of emergency shelter / housing immediately. This is a key strength of the Vanuatu humanitarian response mechanism
3.1 Shelter Lessons Learned workshop

## Slide 5
Clear and early division of geographical working areas to Agencies (notwithstanding some gaps in PV) and also evacuation centres provided clarity and supported planning at Agency level.
Good co-operation, openness, sharing of resources and flexibility between different partners such as donors, govt., NGO’s amongst cluster partners who were “solution orientated”.
IM – mapping and 3W’s enabled identification of duplications and gaps, resulting in positive collective action taken by cluster partners to resolve issues. Information is consistently updated and shared
3.1 Shelter Lessons Learned workshop

## Slide 6
Consistency of shelter cluster meetings (time and location), and low “churn” of shelter cluster personnel. (E.g. Tom and Ryan in place for a good length of time).
Good link between shelter cluster and camp management working group who worked together (and with other clusters) to facilitate the prompt, proper and orderly closure of evacuation centres.
Basic shelter trainings at community level in safe shelter awareness (although this has not been implemented widely as yet).
Establishment of a regional shelter cluster in Tanna.
3.1 Shelter Lessons Learned workshop

## Slide 7
What Could be Improved?
Data management both at cluster level and national level. This was exemplified by the out of date census information that misinformed the initial assessments.
Moving forward, it was also felt that the cluster demand for Agency information (3W’s) was onerous, particularly early in the response.
Allied to this, there were too many expensive and unnecessary assessments, when the data was largely available from PDC / CDC.
Too many coordination meetings held early on (3 per week) with unclear objectives.
3.1 Shelter Lessons Learned workshop

## Slide 8
What Could be Improved?
Delays and expense of importing and distributing materials.
Two – way Knowledge capture and transfer to reduce risk of knowledge loss through international personnel “churn”.
Stronger connection between shelter activities and existing projects – e.g. GoV infrastructure business plan.
3.1 Shelter Lessons Learned workshop

## Slide 9
Governance structure of the Shelter cluster needs to be clarified / rationalised when moving into recovery phase. There are a number of GoV Ministries / Departments involved in housing beyond emergency response, but not clear how they come together.
Evacuation centre preparedness in terms of identification of centres, physical standards, EC management training. Overall, there is a need for a functioning CCCM cluster.
3.1 Shelter Lessons Learned workshop

## Slide 10
Increased need for ongoing training and raising awareness with respect to principles of building codes integrated with traditional construction methods, and reinvigoration of local materials.
This should be tied to Pacific partnerships to learn from what is / has happened in other countries.
Shelter early recovery needs to be included in the cluster discussions much sooner in the response.
Gender sensitivity of the shelter cluster.
3.1 Shelter Lessons Learned workshop

## Slide 11
AP1: Develop Common cluster baseline
AP2: Explore on skilling up PWD trainers pool
AP3: Explore funding scheme at RTC level
AP4: Map and invite vocational training institution for Next TWiG
AP6: Inputs on traditional construction technics
AP7: TWiG to be convened on Tuesday 2PM, all 3 weeks
AP8: Send pictures of partners of activities to document Shelter cluster PAM response
3.2 Building Back Safer Technical Working Group (TWiG) key outputs

## Slide 12
3.3 Shelter cluster, preparedness and recovery timeframes
HAP, till 31/07 – PWD Shelter Cluster Lead, IFRC co Lead
Cyclone season start in November. El Nino might also impact Vanuatu.
Strategic Advisory Group to be convened in second half of June (TBC) to address governance of the Shelter Cluster, cluster strategy concerning recovery and preparedness frameworks

## Slide 13
DRAFT Recovery framework:1 of priorities for reconstruction and reconstruction activity is: Rebuild/repair/upgrade private housing and infrastructure.
Who will take the lead?
Ministry of Internal Affairs
Ministry of Lands and Natural Resources
Who will support?
Prime Minister’s Office
Ministry of Finance and Economic Management
Ministry of Infrastructure and Public Utilities
Provincial Government Councils
Municipal Government Councils
Malvatumauri
Island Council of Chiefs

## Slide 14
3.4 Communication With Communities (CWC)

## Slide 15
3.5 Cash/vouchers programming?

## Slide 16
Clarification on VAT exemption for shelter material will end on June 12th
After discussion with NDMO director, it would not concern relief and donated goods.
3.6 VAT for shelter material

## Slide 17
3.7 2,000 Tarps process
The 2,000 tarps provided by Australian Red Cross to respond to Shelter Cluster call are available from today.
NDMO - 470 tarps
Vanuatu Red Cross - 600 tarps
Care International - 860 tarps
Butterfly Trust - 20 tarps
VSDP - 50 tarps

## Slide 18
4. Partners update and issues

## Slide 19
5. AOB
Lessons Learned in Protection (WASH, Shelter, Food Security, Cash for Work Activities) Session on Wednesday June 10 from 9am to 10.30am at the Vanuatu Institute of Technology, Port Vila