Minutes of the shelter cluster meeting held on 15th January, 9.00 AM at NRC office:

Members Present:

- Mohamed Hassan.                   HINNA.

- Abdiweli Shukri Khalif             REACH.

- Maryan Mohamud Aden           SYPD.

- Mohamed Ibrahim Qandac       SCC.

- Abdi Hassan Hamud                 DBG/DKH   .

- Munira Mohamud Ali                SSWC.

- Imadi Abdi Aziz                         ORDO.

- Shukri Isse Ali                          ACTED.

- Nurta Mohamed                      UNHCR.

- Mohamud Abdullahi               ACF.

- Abukar Addoow                      SOHDA.

- Abdullahi Ayanle                     NRC.

- Badar Abdigadir                       NRC.

Agenda;

- Introduction

- Updates.

- Rolling out the 4W matrix.

- Upcoming eviction assessment.

- Templates for Website per region.

- Shelter Typology.

- AOB.

Action points:

- All the partners to follow up with the eviction and report before the notice period of the eviction for purpose of the pre eviction assessment.

- HINNA, ACF, NRC to complete the data using the online 4w matrix by close of business and on Monday for the activities from September 2014.

- SYPD, DBG, SOHDA to fill the shelter typology form for these three projects as test (CGIs, Tents, ESKs).

- ACTED to provide information with the cluster partners on the new arrivals from Middle shabelle.

- REACH to support the cluster wherever necessary.

| Agenda | Issues Discussed |
| --- | --- |
| Introduction: | The meeting commenced with introduction of all partners. |
| Updates: | The following updates were provided by the following Partners: - NRC distributed 42 tents and 42 NFI kits to the families in Bil&Hidig camp in Wadajir after being affected by Fire, the camp hosts 183 HHs of which 42 families being assisted by NRC.ACF promised to share this with their offices since they are also our emergency partners and see if they can support the rest who are living in old tents provided by NRC in 2013. - SOHDA is also planning to distribute 500 tents that compose (5 blankets, ground sheets, 2 mosquitoes, 10 litres jerry cans, kitchen sets, and thirst and station kit, 2 solar lamps laminate at the settlements Wadajir and Wardigley. - SYPD is planning to construct 91 CGI shelters in Marka-Lower Shebelle, and 91 in Beletweyne in Hiraan region funded by CHF. - DBG is planning to distribute 40,000 ESKs to the IDPs along k7 to k13 in Banadir region. - ACF distributed 153 emergency kits at IDP camps at Maslax area and 110 at Tredish area in Banadir. - ACTED highlighted some new arrivals in 77 area from middle Shebelle due to Al shabab militant’s tension and promised to share it with the cluster and also who are ready to go back to their area of origin if supported. |
| Rolling out of the 4w matrix: | The training of the 4W matrix together with the cluster members went out successfully and the following partners promised to complete their data as from September 2014, NRC, ACF and HINNA who had any activities to report. |
| Upcoming eviction assessment: | As the eviction trends are significantly increasing in Mogadishu, the shelter cluster and the protection cluster will like to capture information as much as possible and more information within the course of the coming weeks. |
| Templates for Website per region. | All the partners promised to send report and factsheets, HLP, needs assessment, Monitoring and evaluation to the emails in the document. |
| Shelter Typology | The cluster partners reviewed the documents and welcomed the information, at the moment we agreed to test three typologies with: DBG ESKs( Emergency shelter kits) SYPD CGIs ( corrugated galvanized Iron sheets) SOHDA Tents. |
| AOB | The partners agreed to share any relevant information to the cluster coordinator. |
| Adjournment | The meeting was adjourned at 12:30PM and the next meeting was scheduled on 15th February. |