Shelter Cluster Meeting Minutes.

Sunday 09th August 2015.

DBG Office.

Members Present:

- Mohamed Hassan.                   HINNA.

- Imadi Abdiaziz                        REACH.

- Abdinur Ibrahim                      SYPD.

- Alinuur Mohamed Ali              UNOCHA.

- Mohamed Mohamud Ali           AVORD.

- Mohamud Abdullahi                ACF.

- Omar Mohamed                       DBG.

- Mohamed Abdirahin                DBG.

- Nurta Mohamed                      UNHCR.

- Abdullahi Ahmed Ayanle          NRC.

Agenda;

- Introduction

- Updates from members.

- Reporting on 4W matrix.

- Upcoming on the tri cluster assessment.

- Resource Mobilisation.

- AOB

| Agenda | Issues Discussed |
| --- | --- |
| Introduction: | The meeting commenced with introduction of all partners. |
| Updates from Members: | The following updates were provided by the following Partners: - SYPD are in preparation of providing shelters/NFI to 220 HHs.in kunturwarey. They are providing shelter kits to 120 HHs, and 100 ESKs and NFI kits. - NRC distributed 1000 NFI kits in July at IDPs in Sarakusta and 250 of the beneficiaries were Yemen refugees. - ACF distributed Emergency package including cash to evicted IDPs in Sarkusta. - DBG/DKH are also starting the CHF shelter project of providing Emergency shelter and NFIs to 2002 HHs in Both Darkenly and Deynile specifically newly formed IDPs as of 10th August. |
| Reporting on the 4w matrix: | - It was discussed and agreed that members with ongoing projects to report timely on the 4w matrix either on line or on the sheet which ever way. |
| Update on the upcoming tri cluster assessment: | - REACH in collaboration with the shelter cluster are planning to carry out full needs assessment and infrastructure mapping exercise throughout Mogadishu upto K23, this will include typical assessment with Wash, Education and shelter cluster. |
| Resource Mobilisation. | Below are some organisation that have stocks for preposition use. - NRC 1000 NFI kits and 200 family tents. - ACF 700 emergency packages. - DRC ( blankets) - SCUK ESKs 300 and 500 NFI kit. - UNICEF will be confirmed. |
| AOB | Hinna and ACF pointed out new arrivals due to the offensives in Gedo, Middle Juba and Bay . - ACF( 40HH arrived in Al cadala area from Diinsor and Salagle) - HINNA (306HH and 280HH in arrived in Mubarak and Awdeegle umbrellas in Sarakusta area from Buale. |