### Global shelter cluster working group

### Shelter Projects 2015-2016

### DRAFT meeting minutes

### Dial in 10th June 2016

### Meeting Minutes

Date and venue: June 10th, 2016 – IOM and Dial in

Participants:

Miguel Urquia (UNHCR), 			Joseph Ashmore (IOM),

Jake Zarins (Habitat for Humanity), 		Brenda Rose Daniel (World Vision),

James Kennedy (independent/IOM), 		Charles Parrack (Cendep),

Oyvind Nordlie (NRC), 				Sandra d’Urzo (IFRC),

Lee Malany (USAID OFDA)

Apologies: Alberto Piccioli (IOM), Charles Setchell (USAID OFDA), Jamie Richardson (CRS), Esteban Leon (UNHABITAT).

### Overview,

The meeting focussed on critical path actions:

- Review of the questionnaire results

- Review of submissions to date

- Review of data collection form

### Abstracts and case study inclusion

- ACTION: all to continue encouraging field offices to submit case studies.

- DECISION: extend time to contribute abstracts

- DECISION: maintain limit of at least 500 households served by project UNLESS it highlights a significant issue that cannot be highlighted by other projects.

- ACTION to increase analysis of case study submissions – include basic statistics on reginal and type of crisis.

- DISCUSSION: missing: Syria response, ensure regional representation, and maintain conflict natural disaster. Aim to get lessons from Balkans response as this is missing in historical case studies.

### Data collection

- ACTION: all to review case study data collection form and forward to IOM with comments by wed 15th.

- DECISION: move “strengths and weaknesses” to the end of the form”. TWG to independently review case studies to identify strengths and weaknesses.

- RECOMMENDATION: include HQ level representative to co0tnact re: case study content

- ACTION: IOM to re- circulate key words (see below). All to comment on them

- ACTION: IOM add a date field in case study write ups for contributors to add their own key words.

- ACTION: IOM and SC IM team: work on wording for credit for use of images. This will be included in the data collection form

Other

- ACTION: IOM further clarify peer review process

- ACTION IOM to investigate potential partners to receive Bruo Happold funds.

- RECOMMENDATION: from survey, it appears balance of opinion pieces/ historical case studies, and the available formats is good. Further work is required to ensure and convey transparency of peer review process.

- ACTION Move website to shelterprojects.org now that the domain is available.

- RECOMMENDATION: hold fuller discussion on opinion pieces at a later date.

Next meeting TBC.

### Annex 1 – Keywords / Categories for case studies

Context:

Climate,

Urban / Rural,

Natural disaster / conflict,

Complex emergency

Support Methods:

Cash / vouchers,

NFI Distribution (household items, construction materials, tools),

Loans,

Advocacy/Legal,

Site planning,

Infrastructure,

Training,

Structural assessment,

Guidelines/materials/mass communications

Shelter type:

Emergency shelter,

Transitional shelter,

Host family support,

Rental support,

Core housing,

Housing repair and retrofitting

Settlement option:

Non displaced / returns,

Dispersed self-settled,

Short term land/house/apartment,

Unplanned camps,

Collective centres,

Hosting,

Planned and managed camps/relocation sites,

Resettlements,

Urban neighbourhoods

Aspect:

Environment,

Gender,

Risk reduction,

Participation,

Coordination,

Protection,

Accessibility,

Training/Capacity building,

Advocacy,

Other…