## Slide 1
http://sheltercluster.org/response/iraq
Sub-National Shelter & NFI Cluster Coordination meeting for Centre & South
Agenda
Review of action points from previous meeting
Information Management updates (Full RASP/Rapid RASP – ODK and Reporting for Mosul response)
Technical Guidance updates
Ongoing Emergency Response
Governorate and Agencies Updates C&S
Update on Logistics (Warehousing & Distribution)
Update on IHPF Process
Update on Mosul Operational Planning including ConOps, Central Planning Map, Screening Centres,
AOB
Monday, 10th October 2016

## Slide 2
Review of action points from previous meeting
Share link for Ongoing Emergency Response of Qayyarah / Shirqat Crisis Google Sheet with partners- Done
UNHCR to share info on the construction of a “Transit Center” located out-side Al-Hajaj Camp on Google Sheet -Done
Partners to share plans of intervention and stocks - Ongoing
Partners planning to operate in the four quadrants of the Mosul Operational Plan to submit their project proposals for IHPF - Done
OCHA sends out a summary/overview/snapshot of the quadrant plans to assist cluster partners with proposals.- Done
Share the assessment of camps, sites and potential capacity by UNHCR and Government – Ravi to Update
Share the information with respect to the return of IDPs in Salah Al-Din with Protection Cluster for further action-Ravi to Update
Share link for Ongoing Emergency Response of Fallujah Crisis Google Sheet with partners- Ravi to Update

## Slide 3
http://sheltercluster.org/response/iraq
Inter sector Full RASP/Rapid RASP – ODK
Information Management – Full RASP/Rapid RASP – ODK

## Slide 4
http://sheltercluster.org/response/iraq
Partners will be requested to report distribution activities, capturing the following information:
Reporting Date | Quantity
Reporting Focal Point | Units
Contact Phone | Activity Start Date
Governorate | Activity End Date
District | Completed to date
QUADRANT | Status
Location | # of HH at site
Settlement Typology | # of individuals reached
Type of Relief | # of individuals reached
Activity | Place of Origin of Beneficiaries (District level)
Information Management – Reporting for Mosul response

## Slide 5
Lessons learned from Anbar highlight that a lack of clarity on site names, locations, displaced population figures etc. often caused:
  duplication of assistance
  issues in identifying and responding to critical gaps
For Mosul response, capturing GPS coordinates will enable reliable identification and verification of site names and locations. Will support:
  Reliable and timely gaps analysis to determine requirements, gaps, partner capacity etc.
Information Management – Reporting for Mosul response

## Slide 6
Creation of simple Kobo form, capturing key information + GPS points is most effective method. Allows for:
  GPS location
  Real-time reporting on activities (program staff complete form at distribution location, upload to server once in area with Wi-Fi)
  Reporting requests completed in 5 minutes at distribution
Information Management – Reporting for Mosul response

## Slide 7
http://sheltercluster.org/response/iraq
Salah al-Din : IOM, UNHCR, ISHO, RIRP, Muslim Aid, INTERSOS, Mercy Hands for Humanitarian Aid, Mercy Corps & Christian Aid
Erbil : IOM, UNHCR, ACTED, NRC, BCF, ERC, IRW, PWJ, French Red Cross, Qandil, Medair, ZOA, Christian Aid, DRC, INTERSOS, Mercy Corps, CRS, Reach National & Dorcas
Quadrant III (10 Partners)
Quadrant II (26 Partners)
Quadrant IV (15 Partners)
Quadrant I (19 Partners)
Dahuk : IOM, UNHCR, NRC, Qandil, BRHA, LWF, Save the Children, Samaritan Purse, CRS, Dorcas, Caritas, PWJ, JEN, GRC, CAPNI, CARE, Medair, IRCS, IBC, ACTED, WHH, Mission East, PIN, ZOA, French Red Cross & DRC
Ninewa : IOM, UNHCR, BCF, PWJ, Mission East, French Red Cross, Qandil, ACTED, PIN & DRC
Kirkuk : IOM, UNHCR, DRC, Mission East, NRC, IRCS, Save the Children & Reach National
Mosul preparedness / NFI Partners / blue: current operational Partners & red: interested to join Mosul response

## Slide 8
http://sheltercluster.org/response/iraq
Mosul preparedness / Shelter Partners / blue: current operational Partners & red: interested to join Mosul response
Salah al-Din : IOM, UNHCR, ISHO, RIRP, INTERSOS & Muslim Aid
Erbil : IOM, UNHCR, ACTED, ZOA, Dorcas, NRC, Medair, INTERSOS, CRS & DRC
Ninewa : IOM, UNHCR, Qandil, ACTED, PIN & DRC
Quadrant III (6 Partners)
Quadrant II (16 Partners)
Quadrant I (10 partners)
Dahuk : IOM, UNHCR, CRS, NRC, PWJ, KURDS, CARE, Qandil, WHH, UN-Habitat, Medair, ACTED, Dorcas, ZOA, PIN & DRC
Kirkuk : IOM, UNHCR, NRC, CRS, Save the Children, IRD, Reach National & DRC
Quadrant IV (12 Partners)

## Slide 9
Shelter Cluster is maintaining a matrix of Mosul preparedness (and response) activities by agency to get an overview of the resources available or in the pipeline.
Information Management – Reporting for Mosul response

## Slide 10
Technical Guidance Updates – Arabic Version of NFI Guidance

## Slide 11
Technical Guidance Updates – Emergency Shelter Kit Training

## Slide 12
Technical Guidance Updates – Emergency Shelter Kit Training
PPT Pictures from Emergency Shelter Kit Guidance – Workshop on ESK held on Oct. 5th in Dahuk

## Slide 13
Ongoing Emergency Response
Camp Condition Report - WHH

## Slide 14
Governorate and Agencies Updates Centre and South

## Slide 15
Update on Logistics (Warehousing & Distribution)

## Slide 16
Update on Logistics (Service Request Form)

## Slide 17
Updates on Humanitarian Pooled Fund Process – Mosul Preparedness
Total Shelter and NFI proposals: 25 (Incl. 11 multi-cluster)
Total budget: USD 24.5 million
After Cluster SAG review
Total approved proposals: 16 (5 multi-cluster) with initial budget: US $17.5 million
Revised budget: US $14.2 million
Last week the Advisory Board of the IHPF sanctioned a budget of US $13 million for the Shelter/NFI Cluster recommended proposals.
As such, we have secured funding for 16 Cluster partners of which 12 partners are specifically engaging in prepositioning shelter materials and NFIs.

## Slide 18
Humanitarian Pooled Fund – Mosul Preparedness

## Slide 19
Update on Mosul Operational Planning including ConOps, Central Planning Map, Screening Centres

## Slide 20
Update on Mosul Operational Planning including ConOps, Central Planning Map, Screening Centres

## Slide 21
Update on Mosul Operational Planning including ConOps, Central Planning Map, Screening Centres

## Slide 22
Update on Mosul Operational Planning including ConOps, Central Planning Map, Screening Centres
Madan: 800 people
Kaherta: 800 people
Kahreez: 400 people
Narghzlia: 800 people
Protection Issues

## Slide 23
http://sheltercluster.org/response/iraq
AOB