## Slide 1
http://sheltercluster.org/response/iraq
Sub-National Shelter & NFI Cluster Coordination meeting for Centre & South
Agenda
Review of action points from previous meeting
Information Management updates
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool
IHPF update
Governorate and Agencies Updates C&S
AOB
Monday, 19th October 2016

## Slide 2
Review of action points from previous meeting
Share report on IED incident at the stadium to emphasise danger faced during site assessments – Done
Share protection report on IDP returns in Sayeed Ghareeb/ Salah A Din for partners to take appropriate action – Done
Full RASP / Rapid RASP: update partners on the process and share the Kobo link once available – Done
Mosul Preparedness – Cluster Master Sheet / Partner Sheet: IMO to prepare partners google sheet and Consolidate the preparedness matrix – In process
Special S-NFI Cluster Mosul response tool / Update partners / partners encourage reporting their Mosul interventions using cluster specific tool – In process

## Slide 3
Review of action points from previous meeting
Inter cluster Mosul response matrix: Cluster IMO to provide update based on Cluster specific Mosul response tool – Starting soon
Work with Partners , practically where to conduct a workshop of Emergency Shelter Kit Guidance for partners in C&S – In process
Have a bilateral meeting with IOM on IEC materials/ videos – In process
Share assessment reports in respective areas of operation with the shelter cluster – Cluster follow up
Mosul response: For Coordination purposes, partners are encouraged to provide information on any agency working on shelter related activities in your respective AoR but not known to the cluster – Cluster follow up
Visibility for shelter and NFI partners – Cluster follow up

## Slide 4
http://sheltercluster.org/response/iraq
Information Management – Cluster achievement Jan. – Sept. 16
Chart: NFI monthly response trend against target
| Jan.16 | Feb.16 | Mar.16 | Apr.16 | May.16 | Jun.16 | Jul.16 | Aug.16 | Sept.16
 | 0.14096 | 0.10379 | 0.088186 | 0.03071 | 0.038488 | 0.17748 | 0.036802 | 0.040257 | 0.055959
Chart: Shelter monthly response trend against target
| Jan.16 | Feb.16 | Mar.16 | Apr.16 | May.16 | Jun.16 | Jul.16 | Aug.16 | Sept.16
 | 0.0090891 | 0.023791 | 0.019451 | 0.0072438 | 0.0104 | 0.027929 | 0.021635 | 0.040507 | 0.020648
Chart: Shelter & NFI monthly response trend against target
| Jan.16 | Feb.16 | Mar.16 | Apr.16 | May.16 | Jun.16 | Jul.16 | Aug.16 | Sept.16
NFI | 0.14096 | 0.10379 | 0.088186 | 0.03071 | 0.038488 | 0.17748 | 0.036802 | 0.040257 | 0.055959
Shelter | 0.0090891 | 0.023791 | 0.019451 | 0.0072438 | 0.0104 | 0.027929 | 0.021635 | 0.040507 | 0.020648
 | Target (HHs) | NFI reached HHs and %tage |  | Shelter reached HHs and %tage | 
Country wide | 196,536 | 134,026 | 68% | 34,463 | 18%
KR-I | 46,719 | 13,419 | 29% | 4,006 | 9%
Centre & South | 149,816 | 120,607 | 81% | 30,457 | 20%
Funding status (from FTS _ Oct. 18th 2016): 37% of 180 million. – 2016 HRP underfunded

## Slide 5
Partner sheet:
Till Oct. 18th 2016, the cluster has provided individual google sheet to 40 cluster partners engaged in Mosul Preparedness and Response
Data requested
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool

## Slide 6
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool
Cluster master sheet:
Consolidated from partner sheet
Information sharing – Analysis, Infographics – Advocacy for Fund raising

## Slide 7
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool

## Slide 8
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool
Total Camps: 10
Ready to receive IDPs: 7 Camps
Under construction: 3 Camps
To be assessed: 1
Emergency Sites: 14 :

## Slide 9
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool
CCCM (Camps and Emergency Sites Master list) & Shelter and NFI (Preparedness Master Sheets & Summary Sheet):
  http://bit.ly/mosul_camps_masterlist
Rapid RASP – real time data upload & IOM DTM Daily update.
  http://bit.ly/Mosul_RapidRasp_data
CCCM assessments -Live-feed 24/7 Map
  http://arcg.is/2ecS904

## Slide 10
Creation of simple Kobo form, capturing key information + GPS points is most effective method. Allows for:
  GPS location
  Real-time reporting on activities (program staff complete form at distribution location, upload to server once in area with Wi-Fi)
  Reporting requests completed in 5 minutes at distribution
  Update: REACH has completed the response matrix and now migrating the matrix into Kobo Form
Mosul Preparedness & Response Updates: Partner sheet, Cluster master sheet, Response tool

## Slide 11
Updates on Humanitarian Pooled Fund Process – Mosul Preparedness
Total Shelter and NFI proposals: 25 (Incl. 11 multi-cluster)
Total budget: USD 24.5 million
After Cluster SAG review
Total approved proposals: 16 (5 multi-cluster) with initial budget: US $17.5 million
Revised budget: US $14.2 million
Last week the Advisory Board of the IHPF sanctioned a budget of US $13 million for the Shelter/NFI Cluster recommended proposals.
As such, we have secured funding for 16 Cluster partners of which 12 partners are specifically engaging in prepositioning shelter materials and NFIs.

## Slide 12
Governorate and Agencies Updates Centre and South

## Slide 13
http://sheltercluster.org/response/iraq
AOB