## Slide 1
http://sheltercluster.org/response/iraq
Sub-National Shelter & NFI Cluster Coordination meeting for KR-I
Agenda
New Cluster Team Members and Introductions
Update on 2017 HRP and planning process
Information Management Update
Review Mosul preparedness against response
Pre-planning of activities & Gap analysis
Governorate and Agencies Updates
AOB
Wednesday, 21st December 2016

## Slide 2
1. Cluster Team Structure
Ryan Smith
Roving Cluster Coordinator (Duhok) - Zone 2 Focal Point
Catholic Relief Services
+964 (0) 751 755 8451
coordroving.iraq@sheltercluster.org
Richard Evans - UNHCR National Cluster Coordinator - Zone 4 Focal Point +964 (0) 771 994 5694 coord.iraq@sheltercluster.org Michel Tia - IOM Information Management Officer - National +964 (0) 750 021 1720 im2.iraq@sheltercluster.org Cornelius Weira - IOM Sub National Co-Chair - Centre and South Mobile +964 (0) 751 234 2548 coord4.iraq@sheltercluster.org Surge Capacity - Phil Duloy - Shelter Box - Bo Hurkmans - UNHCR | Michael Gloeckle - NRC National Co-Chair - Technical Coordinator - Zone 1 Focal Point +964 (0) 750 878 7793 coord2.iraq@sheltercluster.org Ryan Smith - Catholic Relief Services Dahuk & Zone 2 Focal Point +964 (0) 751 755 8451 coordroving.iraq@sheltercluster.org

## Slide 3
2. Update on HRP
An update was shared by the Cluster on website – http://www.sheltercluster.org/documents/hrp-update-shelter-and-nfi-cluster
Key dates:
OPS is open as of 17th December 2016 to start entering projects
15th January 2017 - OPS closes
26th January 2017 – finalisation of projects
Next Steps:
OCHA training
Cluster meetings to finalise strategy and activities
Review information needs, start to write narrative
Internal meetings to discuss scale, location and activities for 2017

## Slide 4
http://sheltercluster.org/response/iraq
November 2016 - IM products: dashboard/Infographics
  The update will be released very soon together with a consolidated 4W matrix and the analysis tool.
3. Information Management Update
Chart: NFI monthly response trend against target
| Jan.16 | Feb.16 | Mar.16 | Apr.16 | May.16 | Jun.16 | Jul.16 | Aug.16 | Sept.16 | Oct.16 | Nov.16
 | 0.14096 | 0.10379 | 0.088186 | 0.03071 | 0.038488 | 0.17748 | 0.036802 | 0.040257 | 0.055959 | 0.031877 | 0.11086
Chart: Shelter monthly response trend against target
| Jan.16 | Feb.16 | Mar.16 | Apr.16 | May.16 | Jun.16 | Jul.16 | Aug.16 | Sept.16 | Oct.16 | Nov.16
 | 0.0090891 | 0.023791 | 0.019451 | 0.0072438 | 0.0104 | 0.027929 | 0.021635 | 0.040507 | 0.020648 | 0.01473 | 0.11515
Chart: Shelter & NFI
| Jan.16 | Feb.16 | Mar.16 | Apr.16 | May.16 | Jun.16 | Jul.16 | Aug.16 | Sept.16 | Oct.16 | Nov.16
NFI | 0.14096 | 0.10379 | 0.088186 | 0.03071 | 0.038488 | 0.17748 | 0.036802 | 0.040257 | 0.055959 | 0.031877 | 0.11086
Shelter | 0.0090891 | 0.023791 | 0.019451 | 0.0072438 | 0.0104 | 0.027929 | 0.021635 | 0.040507 | 0.020648 | 0.01473 | 0.11515
 | 162,079 | HHs Reached (with Basic NFI Kits distributions) | 59,990 | HHs Reached (with Shelter interventions)
Response | 82% | of Cluster 2016_HRP Target | 31% | of Cluster 2016_HRP Target
GAP | 34,457 | Represent 18% | 136,546 | Represent 69%

## Slide 5
http://sheltercluster.org/response/iraq
Mosul responses have to be reported also into Activity Info which is the inter-cluster reporting platform.
Deadline to report your country wide - Dec.16 achievements is Jan. 5th 2017.
Remember that all IM products and other relevant cluster supporting tool are available on the cluster webpage: http://sheltercluster.org/response/iraq
3. Information Management Update

## Slide 6
http://sheltercluster.org/response/iraq
Preparedness: 45 Partners are involved – but 37 partners are constantly updating their preparedness stocks. 8 partners are still not sharing their information.
Current preparedness infographic is been revised to reflect preparedness and response on one page document.
Updated infographic (preparedness & response) will be shared through the website:
http://sheltercluster.org/mosul-dashboard
Updated 4W will be shared through the website:
http://sheltercluster.org/mosul-operational-presence
4. Review Mosul preparedness against response

## Slide 7
4. Review Mosul preparedness against response

## Slide 8
4. Review Mosul preparedness against response

## Slide 11
4. Review Mosul preparedness against response
Not started: No funding or no access to the location to implement
In pipeline: Purchase order signed / funding secured
In stock: In country and in warehouse
Pre-positioned: In sub-warehouse or at a set location (camp etc.) ready for distribution
Planned: Distribution plan for coming two weeks (when and where)
Completed: Distributed/implemented, should be uploaded via Kobo form
To be removed
In progress

## Slide 12
Is there a coordination gap between Preparedness & Reported Response?
5. Pre planning and Gap Analysis
Reported Shelter / NFI Need – (e.g. IDP call centre, assessments, field visits)
‘Need’ received by Cluster
Is it a Gap that needs to be filled?
Is it a need that will be covered by an active partner with resources?

## Slide 13
Partner update on issues of concern
(no reporting on figures …..)
6. Governorate and Agencies Updates

## Slide 14
  Tent replacement:
    REACH survey
  Others:
http://sheltercluster.org/response/iraq
7. AOB