Location: 	Ned Colt Room, UNAMI

Time: 	11:30 – 12:30

Present: 	Ivy, ICRC, DRC, IOM, Erbil JCC, ACTED, UNHCR, Mercy Hands, CRS, Peace Winds Japan (PWJ), QRCS, GAiN, CARE, Qandil, EADE, ZOA, ADRA, WVI

Minutes:	For additional information – see Power Point presentation

| Agenda Item | Key Points | Action Points |
| --- | --- | --- |
| Agenda | - New Cluster Team Members and Introductions - Update on 2017 HRP and planning process - Information Management - Cluster Technical Guidelines – upcoming guidelines - Access Issues to East Mosul - Areas of Activity within the Zones - Governorate and Agencies Updates - AOB |  |
| 1. New Cluster Team Members and Introductions | - New structure was presented. - Special thanks to IOM, CRS, NRC and UNHCR for providing staff for the cluster - See PP presentation for contact details |  |
| 2. Update on 2017 HRP and planning process | - No significance changes to guidelines and timelines since presented at Cluster meeting on 21st December - The cluster will send out guidance about how to divide up first (Emergency shelter & NFI) vs second line (upgrading, stabilizing) vs full cluster response - On 18th & 19th reviewing projects to begin, committee made up of UN, INGOs, national NGO to grade. Looking for nominations | - Send nominations to Richard Evans to be on the HRP Panel |
| 3. Information Management updates | - New Features on S/NFI Cluster website, including dashboard/infographics introduced - Now showing MOMD stocks - Now breaking down information between pipeline and available stock to help partners identify gaps. It’s possible to reflect stocks that aren’t allocated to a particular zone by using the “flexible” category - Targets for Shelter and NFI shared: reached and gaps (end of year stats) - Preparedness Master Sheet has been updated (45 partners have their own google sheets, of which only 37 are sharing) - An interactive Operational Presence map has been created, displaying interventions to District level. - The Mosul preparedness sheet has been updated to better reflect the status of partners’ activities. When provided, this information enables the cluster partners and team to identify and address needs. - Because Kobo was developed as a separate system for Mosul, the planned activities were improved to better reflect partners’ planning. (removed the “in progress” category). - Discussion on gas vs kerosene and safety guidelines | - Please update your Google sheets showing your preparedness stocks - Please include access issues in the notes column within preparedness sheet for the time being. If required, SCT-IM can add it as a new category. - Cluster to review gas vs kerosene and provide some draft guidance |
| 4. Cluster Technical Guidelines – upcoming guidelines | - Many technical guidelines (NFI, ESK etc.) already on the website already and more being planned - - See PP presentation for details | - Any ideas or needs for technical guidance – please send to Michael Gloeckle - Review tent guideline and send back for details |
| 5. Access Issues to East Mosul | - Three questions put up to start discussion about access to east Mosul, from different roads. - General desire to try and access the population who are still in Mosul rather than wait for them to come out. - Members wanted more guidance on whether areas were ‘safe’ or not - Requests to customize distribution modalities to each area, work closely with other stakeholders, to do relevant distribution. | - Request to partners to share any distributions guidelines - Request to partners to provide any further details about obstacles, barriers etc. |
| 6. Areas of Activity within the Zones | - Introduction of the wedge map, see PP presentation for details - Explanation of Zone 2 approach as well, and how that is more micro coordination within a wedge. - Wedge would work as well for mass outflow into ISF wedge areas | - Request to partners to share Areas of Activity with the Cluster so we can put agencies against wedges |
| 7. & 8. Governorate and Agencies Updates & AOB | - The Cluster and EJCC provided an update on the camps - Ninewa Governorate planning 33,000 new plots in emergency camps – might need support for NFIs - Cluster again stressed reasons why we need partners to have fully updated preparedness sheets - Highlighted EUCPM stocks coming in and request for who can use them, responsibly - Discussion on camp names, how activities are carried out, management, etc. |  |

Next Meeting: Wednesday, 18 January 2017, 11:30 – 12.30

Attachments:

- Power-point Presentation

- Areas of Activity Map

- Draft of Tent Guidelines