Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA conference room, Dahuk

Date and time: 		11.15am, 6th June 2017

Attendance: 	UNHCR, Mission East, DRC, ACTED, DORCAS, IRCS, BRHA, CARE, NRC, FRC, JEN, PWJ, CRS, IOM, UNICEF, Malteser, OCHA, Civil Defense, Qandil, REACH Iraq, REACH, Tearfund, Medair

| Agenda Item | Key Points | Actions |
| --- | --- | --- |
| Update on previous action points | - Please inform S/NFI shelter with any updates on funds for summarization - UNHCR compiling lists of summarization needs in camps and coordinating with BRHA - Anyone interested in working in area around Badush, please contact Geraldine from ACF - Distribution guidelines updated and shared with partners |  |
| Mosul response camp populations | - Only 2,600 plots left in Southern camps - Populations in Nargiziliya continuing to decrease with few arrivals in the North - Summerization in emergency camps coming progressing well with MoDM, PWJ and potentially other actors - Gap for clothing, jerry cans and cool boxes - Summerisation for new arrivals to existing camps will be covered by MoDM - UNHCR urges discussion on consolidate of camps when a minimum threshold is reached | - Check MoDM is on the mailing list and invite representative (Masoud) for future meetings |
| Needs in existing camps | - Thanks to all who contributed to mapping of needs in existing camps - 192 needs identified, bulk of them under S/NFI, and have been prioritized by color (green highest), based on SPHERE standards, number of people affected and likelihood to return - Cluster looking for partners with funding for priority interventions - Needs list will be shared with partners in relevant clusters in the coming week. Can be used to show to donors, etc. - Cluster will meet with donors to also highlight needs to them - Fire prevention meeting has been held but only one partner attending | - NGOs to discuss funding possibilities to existing camps in your respective organizations - Schedule conversation with UNHCR on replacement of tents in camps - UNHCR to share analysis of past incidents related to fire with partners before second meeting on 11th June at 11am in BRHA conference room. |
| Newly Retaken Areas inside Peshmerga lines | - Korsabad – 790 BESKs distributed by ACTED, 250 water tanks (NRC) and cash intervention pending, blanket distribution of all new returnees by DORCAS. DORCAS will cover future returnees coming back. - Village cluster 6 (Daraweesh, Xara Tappa and others) covered by Mission East. - Bareema: Issues with ERWs causing harm to returnees. Area contaminated with undetectable IEDs. 327 UXOs found so far. As many as 16 fatalities caused in recent months. - S/NFI recommends immediate hold on all activities in Bareema until further notice, pending OCHA guidance. See slide in meeting presentation for all action points. - Cluster is finishing analysis on outstanding areas of distribution and will match partners to needs according to stock levels, security etc. - Info on specific locations: - Bashiqua: NRC planning assessments in Bashiqua for shelter rehab - Khatara: NRC finalizing assessments and ready to cover rehabilitation of 90 HHs - Kefrij: DRC investigating accessibility with Peshmerga. - 2,500 gas stoves available with World Vision | - Cluster and OCHA to finalise Barima action points - Cluster to share outstanding area of distribution with partners - DRC to contact Geraldine from ACF regarding Kifrij - Cluster to share CSV file of Ninewa villages |
| Update from national level | - Safe distribution guidelines has been released by protection, food and S/NFI cluster and will be shared with all partners. - Cluster working on template for household level assessments for war damaged buildings - Cluster will meet with donors next week - Amendment to agenda and meeting minutes process defined in presentation | - Partners to send Laurence points to advocate for with donors |
| AOB | - N/a | - Time and date of next meeting to be announced following consultation with BRHA and CCCM Cluster |
| Areas outside of Peshmerga lines | Alamuk area/Badoosh/Sheikh Mohammed: - MEDAIR conducted health based RNA (no urgent SNFI needs except complementary kitchen sets) - Assessment in Al Mohammed (3km north of Qawsiyat) by MEDAIR – Food is most urgent need (ACF distributed hygiene kits), HH specific distribution of emergency shelter kits. Tal Afar: - Rapid territorial shifts with very limited humanitarian access. Malteser distributed 1000 NFI kits in the area, with an additional 1000 scheduled for next week. More distributions to follow pending more assessments. Good coordination with Peshmerga and militia there. - 40.000 HHs in informal camp between Talafar and potential for movement South to Hammam Al-Alil camps - French Red Cross will be IHPF partner for working in that area - Area will be analysed by cluster based on DTM info for allocating new areas to partners | - Mission East to coordinate with MEDAIR for kitchen sets - Laurence to communicate to Food Cluster need - Cluster to conduct Tel Afar mapping |

Next meeting:		TBC

Minute rotation: 	Completed – UNHCR, ACTED, PIN, Tearfund, WHH, Mission East

Upcoming DORCAS. DRC, Medair and REACH