### Global Shelter Cluster Working Group

### Shelter Projects 2015-2016

### Dial in call 08 February 2017

### Meeting minutes

Date and venue: 08 February, 2017 – Dial in call, 13:00-14:00 CET

Participants:

Alberto Piccioli (IOM/Project Consultant),	Miguel Urquia (UNHCR),

Joseph Ashmore (IOM), 				Alice Obrecht (ALNAP)

Charles Parrack (Cendep),			James Kennedy (independent/IOM),

Sandra d’Urzo (IFRC).

Apologies: Seki Hirano (CRS), Oyvind Nordlie (NRC), Charles Setchell (USAID OFDA), Jake Zarins (Habitat for Humanity), Tom Newby (CARE), Brenda Rose Daniel (World Vision).

### Agenda

- Final Table of Contents

- Next steps

- Final layout option

- Dissemination

- Article for Forced Migration Review

- AOB

### Actions

- Yemen: Alberto and Miguel will try getting shelter cluster data on assistance, to produce a short overview of the crisis, losing the case study.

- Tanzania and Nigeria case studies: Alberto to review latest version and discuss inclusion with working group.

- Regional crises: Alberto to add a paragraph and if possible a map in the introduction highlighting the major crises and their regional impacts.

- Malawi floods 2015: Miguel, Sandra, Alberto to follow up within own organizations to find more information on the flood response and complete the overview.

- Chile, case study on fire in Valparaiso, 2014-2016: Alberto to share with Charles for a first review, by the end of the week.

- Opinion pieces: Max 3-4 will be included. Please find attached the one on self-recovery and knowledge exchange that I mentioned during the call. Any volunteer for reviewing it and providing some comments for the author? Deadline end of this week.

- (Donor) visibility: Miguel to clarify ECHO visibility. Logos of main donors should go in the acknowledgements page, GSC logo on front and back covers.

- Printing: End of April deadline for printing and possibly to ship the books. Possible locations: Geneva (UNHCR and then distributed amongst those based in GVA), Washington (TBC). Shipping to other agencies/locations (e.g. London/UK locations) to be discussed. Alberto to follow up with Brenda.

- Layout: change colors to align with GSC website.

- Article for Forced Migration Review: IOM to share submitted version with the working group.

Next meeting to be held in March/April to discuss any final issue and dissemination.