Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA conference room, Dahuk

Date and time: 		11.00am, 9th January 2017

Attendance: 	UNHCR, BRHA, Dorcas, PWJ, Medair, OCHA, IOM, GRC, IRCS, ACTED, ACF, DRC, WHH, Tearfund, CRS, NRC, Mission East, Malteser, IOM & Dijla

| Agenda Item | Minutes | Actions |
| --- | --- | --- |
| Mosul Response Camp Populations | - Mosul Response camp are now consolidated - UNHCR update: 4 IDP families are moving from Nargazilia to Garmawa. - UNHCR: significant returns already occurring leading to plans for camp consolidation and decommissioning to ensure an effective use of resources. CCCM cluster and ICCG collaborating to document and feedback on best practices and beneficiary inclusion. |  |
| Winter (camp and out of camp) | - An urgent meeting to be called with MODM to clarify capacity to address winter NFI needs - Kerosene: 72,000 increased to 108,000L/day received from federal government, but delivery is inconsistent. Camps covered: Dawudiya, Bersivy 1&2, Sheikhan, Mamliyan, Mamrashan, Essian, Bajid Kandala, Khanke (in progress) Remaining: Kabartu 1&2, Sharya - Sharya and Bersive 1 – tent covers in need of changing no extensions possible - Sheikhan is possible to go further than just replacing covers - PWJ: Tender for NFI beginning - Teskharab Big and Small Partner updates on out of camp projects - Medair: Has begun distributions of winter NFIs in Sinjar - Tearfund: Assessing feasibility of clothing intervention in Zakho for 750-1000/HH. BRHA – Target one location given financial constraints. - Qandil: Response information and referrals submitted to cluster. Qandil continuing process of verifying HH needs in Zummar and Rabea. Qandil Dohuk distribution in progress, 5 days, 2000 HH. - UNHCR: Zakho (7,187 beneficiaries, $200) and Khanke (2,703 beneficiaries, $200) - ICRC: Sinjar Mountain, implemented next week for approx. 1,962 HH. - CRS: Shariya area $200 transfers for winterization for approx. 2,800 HH. - Mission East: could have limited items around Ninewa - GRC: MPCA for 1,250 HH, currently in verification process, distribution in late Jan Needs - Shekhan and Khanke orphanage of IDP and refugee in need of NFI. ME to review potential response. - Zakho response soon to close if no partners are willing to pursue the remaining scattered cases | - BRHA, MoDM, UNHCR and SC to meet on winter NFI - BRHA to follow up on re-use electric transformers in camps - BRHA to provide cost information on sub standard camps - OCHA to pass request to Baghdad for more consistent kerosene supply - Tearfund: Follow up with Laurence on available for winter NFI - Laurence: Send DRC database with info on vulnerable Ninewa villages to Kenga - Laurence: Follow up on potential for CRS clothing in Garmawa - Laurence: Updates on rehabilitation of housing (CRS, NRC, PWJ, Acted) meeting and coordination with UNDP/Habitat |
| Updates | - DRC received OFDA funding until August for various shelter interventions - Movement to make the S/NFI cluster meeting monthly passes |  |

Minute rotation: 	Completed - ACTED, UNHCR, UNHCR, Tearfund

Upcoming – ACF, PWJ, DRC & Medair

Previous rotation - UNHCR, ACTED, PIN, Tearfund, WHH, Mission East, DORCAS, DRC, Medair and REACH

Next meeting:		6th Feb 2018