Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA conference room, Dahuk

Date and time: 		11.00am, 6th February 2018

Attendance: 	UNHCR, BRHA, Dorcas, PWJ, Medair, OCHA, IOM, GRC, IRCS, ACTED, ACF, DRC, WHH, Tearfund, CRS, NRC, Mission East, Malteser, IOM & Dijla

| Agenda Item | Minutes | Actions |
| --- | --- | --- |
| Camps | - BRHA: Distribution of kerosene done in all camps with only Shariya remaining. Distribution will complete this week and then move out of camps. - UNHCR has provide WNFI to Dawodiya camp, Kabarto and Shariya camp - Shariya camp needs more secondary covers. This was provided by UNHCR but complaints were raised over the size. UNHCR and GRC to discuss with community to understand their choice of UNHCR plastic sheets now or GRC ones later. |  |
| Winter (camp and out of camp) | - Medair: 1,953 WNFI distributed in Sinjar area and will add 792 kits WNFI to Tilkaif returnee area. - Tearfund: BRHA to provide the list of Zakho for distribution of NFI including cloths - ICRC has completed cash for SNFI during winter on Sinjar Mountain - CRS: 200 USD per family was provided for the families in Sharia centre - Mission east: has Gas bottle (number need to check) and looking for the places where is small number need in population (any organisations can contact Mission East). Consideration should be shown to ongoing replacement of gas bottles. - JEN: an issue with timing for WNFI provision. Expected distribution by the end of next week. - ACF: distributed 1,400 NFI kits in Wana and Badoush area - ACTED: due to security situation and they change WNFI projects from Hawija to Zummar and Talafar area. CAMP: - WHH & GRC interested to support repairs of 21 caravans in the camps. Out of camp - ACTED: have undertaken various assessments in the TA, Zummar and Wana area and are planning a distribution in Majarin for 1,360HH. - CRS: Multisector assessment done in Bashiqa, Bartella and Qaraqosh - CRS: 102 (SOK) for houses in Bashiqa city, for those who intent to go back to their home |  |
| Updates | - Updating the Shelter/NFI content and will be shared with partners for any comment - There will be new area coordinator from ACTED from the end of Feb. |  |

Minute rotation: 	Completed - ACTED, UNHCR, UNHCR, Tearfund, ACF

Upcoming – PWJ, DRC & Medair

Previous rotation - UNHCR, ACTED, PIN, Tearfund, WHH, Mission East, DORCAS, DRC, Medair and REACH

Next meeting:		6th March 2018