Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA conference room, Dahuk

Date and time: 		11.30am, 8th of May 2018

Attendance: 	UNHCR, BRHA, PWJ, CHF, LWR, GRC, Medair, CRS, OCHA, JEN, NRC, IOM, PWJ, Mission East, UNICEF

| Agenda Item | Minutes | Actions |
| --- | --- | --- |
| Flooding | Needs in camps: - Kabarto1 6 tents affected by the rain & need 2 NFIs. - Kabarto2 10 tents including 8 families affected by the storm. - Garmawa 70-90 families evacuated to a school, 37 tents damaged, 23 available in Garmawa, 14 tents need and secured from MoMD. - Shikhan camp, 1 rub hall damaged, 53 tents damaged and requires replacement. 200 plus cases recorded in need of plastic sheets. NFIs can’t be delivered (first tents replacement) - Sharia, pending assessment - BRHA requested UNHCR to instruct KURDS to take action since its responsible for care & maintenance Out of camp: - Sinjar we have received information from ICRC, DORCAS and JEN of damage to tents. ICRC reported 200 tents damaged. | - MoDM confirm tents in Nargazlia warehouse can be used, need installation (cement, sand, and concrete blocks for the base), NRC, GRC, KURDS, CRS to check availability of resources - MoDM to support flood response with tents, JEN or ICRC to support. |
| Camps | - Around 150 caravans need maintenance of the floors in Mamrashan. Dawudiya and Rwange now also mentioned. SC to follow up with UNHCR. - UNHCR conducting need assessment by KURDS following | - Follow up with WHH and GRC to take action - UNHCR to share their priorities of camp projects for discussion within two weeks. |
| Out of Camp needs and responses | - UNHCR through Human Appeal will expand their cash for shelter programme in Telafar - CRS have expanded their team and are finishing projects in Bybokht, Tobzawa, Kabarli, and are seeking other villages. The cluster is supporting with villages around Bashiqa town to balance work in the town centre. - DRC confirmed to work in three villages; Filfail, Kivrok, Hiqol Aldawajen. It’s possible they will expand towards Wana or Batnaya. - 520 Arab families returned to destroyed villages along the Iraq – Syria boarder. - IOM continue to plan for 225 houses for Telafar town - ACTED have started their vouchers based projects in Khorsebad. 41 houses completed - NRC, updates on Teskhirab Kabeer & Sagheer. 60% done, assessment ongoing - UNDP continues with 500 houses in Sinjar and Sinouni - New tool for rehab developed by UNHABITAT. National cluster encouraging to use this tool to avoid duplication and help for future plan. | - The cluster and CRS to meet and discuss new villages around Bashiqa. - OCHA/ DPWG to share GPS coordinates for the villages - Meet with NRC for upcoming rehab projects - Cluster to share UNHab tools |
| Summer | - Review of Climatisation guidelines – completed and waiting for SAG review Priorities: 1st - cool boxes and jerry cans 2nd - shading and clothing 3rd – mechanical cooling - BRHA has supported to define needs in camps. Currently AWG and fans. - The SNFI, CCCM, & WASH clusters are working to combine all camp and out of camp information into a strategic and later operational coordination tool. - Medair already have area of operation. ACTED & PWJ to discuss place of intervention. | - Climatisaion guidelines to be shared - BRHA & SC to discuss with MoMD about summer support and AWC including water and electricity |
| National updates | - The cluster requested to form a new SAG. An update on this will come very soon. - The first work of the SAG is to review all the reviewed guidelines; - Rehab minimum standards and WDS categories - War damaged shelter repairs standard BoQ - Commons indicators and MCNA questions - Climatisation guidelines - pending - Kerosene position paper - pending - Settlement typologies - pending - Balance resources for camps and non-camps/ resources are shrinking / partners to understand who are extremely in need/ - MoDM provided air coolers for all IDPs, standardize intervention and stick to minimum intervention and IDPs to sustain |  |
| Key updates | - UNHCR Mosul office will be involved in responses in Northern Ninewa - MoMD to start sending kerosene 200L per family for non-camp … continue of winterization in Semel and Akre - Lack of cash working group, OCHA 12th June meeting for partners who have cash modality to discuss |  |

Minute rotation: 	Completed - ACTED, UNHCR, UNHCR, Tearfund, ACF, Medair

Upcoming – DRC, OCHA, NRC

Previous rotation - UNHCR, ACTED, PIN, Tearfund, WHH, Mission East, DORCAS, DRC, Medair and REACH

Next meeting:		5th of June 2018